3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants relating to construction, earthworks and excavation as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants relating to construction, earthworks and excavation as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Manston Thorne Limited | 620 | TT27715 | Easement Right or Privilege | Caution against first registration in relation to rights contained in a Deed of Easement for Underground Service Media dated 4 August 2014 |  | Category 2 | No Agent Known | Yes | REP1-238 | [6 empty] | Not SU | No agreement on final version |  | 08.10.2025- Negotiations for Protective Provisions will take place now the Statement of Common Ground has been drafted | Heads of Terms negotiations not commenced |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 | Caution against first registration | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 | K903084 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Environment Agency | 703 | K335437 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Erik Martin Collins | 1341 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Tanya Collins | 1342 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Erik Martin Collins | 1341 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Tanya Collins | 1342 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants relating to construction, earthworks and excavation as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/83 | Kent Sheet 3 | 12 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/83 | Kent Sheet 3 | 12 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Right of entry and rights to maintain underground electric lines and associated supports as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Rights of access with or without vehicles, plant apparatus and equipment and the right to park vehicles as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage underground electric lines and associated supports and not to install any other service media as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/91 | Kent Sheet 2 | 114 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Lloyds Bank plc | 38 | K564173 | Mortgage | as mortgagee to Ian Peter Alan Smith in respect of a legal charge dated 24 April 2019 registered under title K564173 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Lloyds Bank plc | 38 | K564173 | Restrictive Covenant | No disposition of the part of the registered estate tinted pink on the title plan by the proprietor of the registered estate or by the proprietor of any registered charge, not being a charge registered before the entry of this restriction, is to be register |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K564173,TT44561 | Restrictive Covenant | Restrictive covenant to not submit any claim in respect of physical factors under Part 1 of the Land Compensation Act 1973 in respect of the road scheme as contained in a Transfer dated 2 October 2015 for the benefit of neighbouring land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 | K564173 | Easement Right or Privilege | Unknown rights as contained in a Deed dated 15 November 1996 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 | K564173 | Restrictive Covenant | Unknown restrictive covenants as contained in a Deed dated 15 November 1996 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jillian Rosemary Smith | 3174 | K564173 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate, or by the proprietor of any registered charge, is to be registered without a certificate signed by Jillian Rosemary Smith of Netherhale Farm, Canterbury Road, St Nicolas a |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Ramsgate Town Council | 3194 | K564173 | Easement Right or Privilege | Rights relating to the laying of a water main and the supply of water as contained in an Agreement dated 27 June 1899 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Royal Mail Group Limited | 3242 | K564173 | Easement Right or Privilege | Rights relating to an overhead telegraph line and the erections and maintenance of one telegraph post as contained in a Wayleave Consent dated 25 October 1948 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | South East Kent Electrical Limited | 3270 | K564173 | Easement Right or Privilege | Rights relating to the laying of one or more underground lines and any necessary underground ancillary apparatus as contained in a Wayleave Consent dated 8 November 1939 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Guy Miles Alan Smith | 3271 | K564173,TT61402 | Easement Right or Privilege | Rights relating to service media and rights to enter upon the retained land for the purposes of inspecting, cleansing, maintaining and repairing service apparatus and all other rights and quasi-rights which are still capable of being enforced as contained |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert Garry Alderman | 3273 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Carole Ann Alderman | 3274 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Julian Paul Randall | 3275 | K564173,K67607,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Barbara Marion Randall | 3276 | K564173,K67607 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Patrick Golding | 3277 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jane Louise Golding | 3278 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher John Randall | 3279 | K564173,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 |  | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | South East Kent Electrical Limited | 3270 | K745070 | Easement Right or Privilege | Rights relating to the laying of one or more underground lines and any necessary underground ancillary apparatus as contained in a Wayleave Agreement dated 8 November 1939 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K564173 | Mortgage | as mortgagee to Ian Peter Alan Smith in respect of a legal charge dated 24 April 2019 registered under title K564173 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K564173 | Restrictive Covenant | No disposition of the part of the registered estate tinted pink on the title plan by the proprietor of the registered estate or by the proprietor of any registered charge, not being a charge registered before the entry of this restriction, is to be register |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K564173,TT44561 | Restrictive Covenant | Restrictive covenant to not submit any claim in respect of physical factors under Part 1 of the Land Compensation Act 1973 in respect of the road scheme as contained in a Transfer dated 2 October 2015 for the benefit of neighbouring land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K564173 | Easement Right or Privilege | Unknown rights as contained in a Deed dated 15 November 1996 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K564173 | Restrictive Covenant | Unknown restrictive covenants as contained in a Deed dated 15 November 1996 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jillian Rosemary Smith | 3174 | K564173 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate, or by the proprietor of any registered charge, is to be registered without a certificate signed by Jillian Rosemary Smith of Netherhale Farm, Canterbury Road, St Nicolas a |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ramsgate Town Council | 3194 | K564173 | Easement Right or Privilege | Rights relating to the laying of a water main and the supply of water as contained in an Agreement dated 27 June 1899 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Royal Mail Group Limited | 3242 | K564173 | Easement Right or Privilege | Rights relating to an overhead telegraph line and the erections and maintenance of one telegraph post as contained in a Wayleave Consent dated 25 October 1948 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South East Kent Electrical Limited | 3270 | K564173 | Easement Right or Privilege | Rights relating to the laying of one or more underground lines and any necessary underground ancillary apparatus as contained in a Wayleave Consent dated 8 November 1939 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Guy Miles Alan Smith | 3271 | K564173,TT61402 | Easement Right or Privilege | Rights relating to service media and rights to enter upon the retained land for the purposes of inspecting, cleansing, maintaining and repairing service apparatus and all other rights and quasi-rights which are still capable of being enforced as contained |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Garry Alderman | 3273 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Carole Ann Alderman | 3274 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Julian Paul Randall | 3275 | K564173,K67607,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Barbara Marion Randall | 3276 | K564173,K67607 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Patrick Golding | 3277 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Louise Golding | 3278 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher John Randall | 3279 | K564173,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 |  | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/98 | Kent Sheet 2 | 889 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Thanet District Council | 167 | TT29616 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Easement Right or Privilege | Rights relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Restrictive Covenant | Restrictive covenants relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Pfizer Limited | 131 | K410629 | Easement Right or Privilege | Rights relating to the construction, maintenance and use of a ground pipe for the conveyance of trade effluent as contained in a Conveyance dated 26 April 1954 for the benefit of unknown land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mining Remediation Authority | 866 | K410629 | Easement Right or Privilege | Rights relating to the working, getting and carrying away by underground workings coal and other minerals as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mining Remediation Authority | 866 | K410629 | Restrictive Covenant | Restrictive covenant not to erect buildings as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Thanet District Council | 167 | TT29616 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Easement Right or Privilege | Rights relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Restrictive Covenant | Restrictive covenants relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of way as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | TT29616 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 | TT29616 | Easement Right or Privilege | Rights relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 | TT29616 | Restrictive Covenant | Restrictive covenants relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of way as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/17 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/18 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Belle Isle Holdings Limited | 3565 | K838948 | Easement Right or Privilege | Right of way and rights relating to service media as contained in a Transfer dated 5 April 2002 for the benefit of Ebbsfleet Farm House |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pfizer Limited | 131 | K410629 | Easement Right or Privilege | Rights relating to the construction, maintenance and use of a ground pipe for the conveyance of trade effluent as contained in a Conveyance dated 26 April 1954 for the benefit of unknown land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Easement Right or Privilege | Rights relating to the working, getting and carrying away by underground workings coal and other minerals as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Restrictive Covenant | Restrictive covenant not to erect buildings as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K811125,K816144,TT165118 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K708841 | Easement Right or Privilege | Rights relating to a water pipe as contained in a Deed dated 2 November 1994 for the benefit of unknown land |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K708841 | Easement Right or Privilege | Rights relating to laying and maintaining water pipe apparatus as contained in a Deed dated 27 June 1995 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K708841 | Restrictive Covenant | Restrictive covenants to not damage or interfere with a water pipe and restrictive covenants relating to service media, construction, planting of vegetation, use of heavy machinery and vehicles and earthworks as contained in a Deed dated 2 November 1994 f |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K708841 | Easement Right or Privilege | Rights to lay, construct and maintain electric lines, poles and stays and fell and lop timber as contained in a Deed dated 13 April 2011 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dawn Randell | 287 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caron Susan Walsh | 300 | K684903,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K708841,K816144 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Phillip Martin Randell | 651 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K811125,K816144,TT165118 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 | K708841,K816144 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Kent Sheet 2 | 711 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K56551 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/24 | Kent Sheet 2 | 711 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K56551 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | South Eastern Power Networks plc | 263 | K651171 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103427 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nigel Stewart Daw | 1015 | K719550,K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrew Kevin Charles Cracknell | 1019 | K111468 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Acorn Homes (Group) Limited | 2316 | TT46646 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Dorcas Muriel Daw | 2370 | K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4326 | [6 empty] | Not SU |  |  | 08.10.2025- Please see PIL Ref 2520 for Owner of Quex Park Farm | Heads of Terms negotiations ongoing |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrew William Johnson | 3566 |  | Easement Right or Privilege | Right of access |  | Category 2 |  | No | [13 empty] | 2026-01-09
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Easement Right or Privilege | Right of access |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Water Services Limited | 411 | K273192 | Easement Right or Privilege | Rights of access with or without vehicles or apparatus relating to a water main and the right to uninterrupted passage of water through the said water main as contained in a Deed dated 12 December 1977 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Water Services Limited | 411 | K273192 | Restrictive Covenant | Restrictive covenants not to permit or suffer any thing which might cause damage to a water main or obstruct access to the works as contained in a Deed dated 12 December 1977 |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Disposal Company (Richborough) Limited | 914 | K987175,K273192 | Easement Right or Privilege | Rights to access, maintain and use a rising main as contained in a Conveyance dated 17 August 1966 for the benefit of K987175 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cornerstone Telecommunications Infrastructure Limited | 3254 | TT70483,K273192 | Easement Right or Privilege | Rights relating to access and use of a telecommunication site as contained in a Lease dated 24 August 2017 for the benefit of TT70483 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | National Grid Electricity Transmission plc | 7 | TT103427 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Nigel Stewart Daw | 1015 | K719550,K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Andrew Kevin Charles Cracknell | 1019 | K111468 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Acorn Homes (Group) Limited | 2316 | TT46646 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Dorcas Muriel Daw | 2370 | K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | The Quex Park Estates Company Limited | 2568 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4326 | [6 empty] | Not SU |  |  | 08.10.2025- Please see PIL Ref 2520 for Owner of Quex Park Farm | Heads of Terms negotiations ongoing |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Andrew William Johnson | 3566 |  | Easement Right or Privilege | Right of access |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Thanet District Council | 167 | TT29616 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Easement Right or Privilege | Rights relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Restrictive Covenant | Restrictive covenants relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cornerstone Telecommunications Infrastructure Limited | 3254 | TT70483,K273192 | Easement Right or Privilege | Rights relating to access and use of a telecommunication site as contained in a Lease dated 24 August 2017 for the benefit of TT70483 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K355424,K524623,K563834 | Easement Right or Privilege | Right of entry and rights to maintain and use drainage ditches as contained in a Transfer dated 8 May 2008 for the benefit of adjoining land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K563834 | Easement Right or Privilege | Right of entry with or without vehicles and equipment and rights relating to the construction and maintenance of electric lines and the felling of trees as contained in a Deed date 26 April 1991 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K355424,K524623,K563834 | Easement Right or Privilege | Right of entry and rights to maintain and use drainage ditches as contained in a Transfer dated 8 May 2008 for the benefit of adjoining land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K563834 | Easement Right or Privilege | Right of entry with or without vehicles and equipment and rights relating to the construction and maintenance of electric lines and the felling of trees as contained in a Deed date 26 April 1991 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 | K563834 | Restrictive Covenant | Restrictive covenants not to erect structures, plant timber or alter ground level within 5 metres of electric lines nor allow vehicles or machinery to pass under electric lines unless there is at least 2 metres of clear space as contained in a Deed dated |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K808893 | Easement Right or Privilege | Right of entry and rights to; lay and maintain electric lines, fell trees and break up ground surface as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K808893 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K355424,K524623,K563834 | Easement Right or Privilege | Right of entry and rights to maintain and use drainage ditches as contained in a Transfer dated 8 May 2008 for the benefit of adjoining land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K563834 | Easement Right or Privilege | Right of entry with or without vehicles and equipment and rights relating to the construction and maintenance of electric lines and the felling of trees as contained in a Deed date 26 April 1991 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 | K563834 | Restrictive Covenant | Restrictive covenants not to erect structures, plant timber or alter ground level within 5 metres of electric lines nor allow vehicles or machinery to pass under electric lines unless there is at least 2 metres of clear space as contained in a Deed dated |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K465344,K524623,K463319,TT934 | Restrictive Covenant | Restrictive covenant not to use the said property for any purpose which might be or grow to be a nuisance or annoyance as contained in a Conveyance dated 18 June 1948 for the benefit of adjoining land |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K524623,K563834 | Restrictive Covenant | Restrictive covenant not to use the said property for any purpose which might be or grow to be a nuisance or annoyance as contained in a Conveyance dated 18 June 1948 for the benefit of adjoining land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Discovery Park Limited | 635 | K524623,TT23413 | Restrictive Covenant | Restrictive covenant not to use the said property for any purpose which might be or grow to be a nuisance or annoyance as contained in a Conveyance dated 18 June 1948 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K987175 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 17 May 1950 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K987175 | Easement Right or Privilege | Rights to lay and use a sewer drain for the benefit of K987175 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K750977 | Easement Right or Privilege | Rights to pass and repass with or without vehicles as contained in a Conveyance dated 17 May 1950 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310,K834466 | Easement Right or Privilege | Right of entry and right to maintain and reconnect a water pipe and to the free passage of water through an underground pipe as contained in a Transfer dated 22 December 1999 for the benefit of adjoining land |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Kent Sheet 4 | 2,818 square metres, or thereabouts, of agricultural land situated to the north east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Kent Sheet 4 | 2,818 square metres, or thereabouts, of agricultural land situated to the north east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310,K834466 | Easement Right or Privilege | Right of entry and right to maintain and reconnect a water pipe and to the free passage of water through an underground pipe as contained in a Transfer dated 22 December 1999 for the benefit of adjoining land |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pfizer Limited | 131 | K410629 | Easement Right or Privilege | Rights relating to the construction, maintenance and use of a ground pipe for the conveyance of trade effluent as contained in a Conveyance dated 26 April 1954 for the benefit of unknown land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Easement Right or Privilege | Rights relating to the working, getting and carrying away by underground workings coal and other minerals as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Restrictive Covenant | Restrictive covenant not to erect buildings as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310,K834466 | Easement Right or Privilege | Right of entry and right to maintain and reconnect a water pipe and to the free passage of water through an underground pipe as contained in a Transfer dated 22 December 1999 for the benefit of adjoining land |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Easement Right or Privilege | Right of entry relating to electrical apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K839921 | Restrictive Covenant | Restrictive covenants not to interfere with the electrical apparatus; not to erect any buildings; not to store any goods within 15m of the electrical towers; not to carry out any excavations; and not to raise the levels of the land as contained in a Gener |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Thanet District Council | 167 | TT29616 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Easement Right or Privilege | Rights relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Gas Networks plc | 547 | TT29616 | Restrictive Covenant | Restrictive covenants relating to gas pipes and apparatus as contained in a Deed dated 15 December 2011 |  | Category 2 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU rights in land | Draft under discussion |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K56551 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K56551 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Stonelees Development Limited | 36 | K617169,K940968 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K617169,K985109 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 September 2011 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K56551 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K56551 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/28 | Kent Sheet 3 | 234 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Restrictive Covenant | Restrictive covenants not to damage or obstruct access to service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media and manhole covers and not to allow vehicles exceeding three tons in weight to travel across manholes as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K56551 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K56551 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/105 | Kent Sheet 2 | 1,603 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K518470 | Easement Right or Privilege | Right of entry with or without vehicles, plant and equipment and rights relating to the use and maintenance of electric cables as contained in a Deed dated 26 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Nemo Link Limited | 771 | K518470 | Easement Right or Privilege | Right of entry with or without vehicles, plant and equipment and rights relating to the use and maintenance of electric cables as contained in a Deed dated 26 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Thanet District Council | 167 | K708841 | Easement Right or Privilege | Rights relating to a water pipe as contained in a Deed dated 2 November 1994 for the benefit of unknown land |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Thanet District Council | 167 | K708841 | Restrictive Covenant | Restrictive covenants to not damage or interfere with a water pipe and restrictive covenants relating to service media, construction, planting of vegetation, use of heavy machinery and vehicles and earthworks as contained in a Deed dated 2 November 1994 f |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | South Eastern Power Networks plc | 263 | K708841 | Easement Right or Privilege | Rights to lay, construct and maintain electric lines, poles and stays and fell and lop timber as contained in a Deed dated 2 November 1994 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | South Eastern Power Networks plc | 263 | K708841 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines nor erect buildings or plant trees within 1.5 metres of electric lines or that encroach upon the foundations of poles and stays nor obstruct vehicular access to poles and stays as contain |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 17 December 2012 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | K838442 | Mortgage | as mortgagee to James Bedford Pace and Alexandra Ruth Pace in respect of a legal charge dated 28 September 2020 registered under title K838442 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Phillip Martin Randell | 651 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Struan Gordon Robertson | 494 | K755310 | Easement Right or Privilege | Right of access |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Struan Gordon Robertson | 494 | K755310 | Easement Right or Privilege | Right of access |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Easement Right or Privilege | Right of access |  | Category 2 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | Yes | RR-4494 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions have not been requested. Assumed to rely on the standard provisions contained within the DCO. | No Heads of Terms Required |  | 2026-01-09
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 | as reputed owner | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K478221 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 | K478221 | Easement Right or Privilege | Rights relating to access and maintenance of water apparatus as contained in a Deed dated 12 February 2001 |  | Category 2 | N/A | No |  |  |  |  | Open Space |  |  | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 | K478221 | Restrictive Covenant | Restrictive covenant relating to access and maintenance of water apparatus as contained in a Deed dated 12 February 2001 |  | Category 2 | N/A | No |  |  |  |  | Open Space |  |  | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | K478221,TT39040 | Easement Right or Privilege | Rights of access and support, rights relating to service media and drainage and right of entry relating to maintenance as contained in a Lease dated 8 July 2015 for the benefit of title number TT39040 |  | Category 2 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K478221 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric cables as contained in a Deed dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/103 | Kent Sheet 3 | 30 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 | as reputed owner | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/103 | Kent Sheet 3 | 30 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K478221 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | K478221,TT39040 | Easement Right or Privilege | Rights of access and support, rights relating to service media and drainage and right of entry relating to maintenance as contained in a Lease dated 8 July 2015 for the benefit of title number TT39040 |  | Category 2 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K478221 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric cables as contained in a Deed dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/105 | Kent Sheet 3 | 112 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 | as reputed owner | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/105 | Kent Sheet 3 | 112 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 | as reputed owner | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/107 | Kent Sheet 3 | 7,957 square metres, or thereabouts, of scrubland, cycle way, path and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K478221 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/107 | Kent Sheet 3 | 7,957 square metres, or thereabouts, of scrubland, cycle way, path and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | K478221,TT39040 | Easement Right or Privilege | Rights of access and support, rights relating to service media and drainage and right of entry relating to maintenance as contained in a Lease dated 8 July 2015 for the benefit of title number TT39040 |  | Category 2 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/107 | Kent Sheet 3 | 7,957 square metres, or thereabouts, of scrubland, cycle way, path and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K478221 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric cables as contained in a Deed dated 5 July 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No |  |  |  |  | National Trust |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K811125,K816144,TT165118 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K708841 | Easement Right or Privilege | Rights relating to laying and maintaining water pipe apparatus as contained in a Deed dated 27 June 1995 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dawn Randell | 287 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caron Susan Walsh | 300 | K684903,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K708841,K816144 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 22 October 1991 for the benefit of Ebbsfleet Farm |  | Category 2 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. Bespoke Protective Provisions under negotiations | No Heads of Terms Required |  | 2025-10-08
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Phillip Martin Randell | 651 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | TI Projectco 2 Limited | 3531 | K708841 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease land as contained in an Agreement dated 25 April 2024 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK346948 | Easement Right or Privilege | Rights relating to the maintenance of electric lines as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK346948 | Restrictive Covenant | Restrictive covenants relating to land use and to not interfere with or damage electric lines as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sandra June Ketley | 2158 | SK346948,SK166451 | Easement Right or Privilege | Rights relating to service media and maintenance of a septic tank as contained in a Deed dated 17 June 2021 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | Not SU |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity cables and works as contained in a Deed dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Restrictive Covenant | Restrictive covenants relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Martin Cotter | 761 | SK259100 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral Notice in respect of an Option Agreement for the grant of easements for cables dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK244913 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements for drains dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK151617 | Easement Right or Privilege | Unilateral notice in respect of Option Agreement dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK276346 | Mortgage | as mortgagee to Emma May Alexandra Heald and Andrew Michael Hilliard Heald in respect of a legal charge dated 30 July 2012 registered under title SK276346 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | St. Edmundsbury and Ipswich Diocesan Board of Finance | 1326 | SK276346 | Restrictive Covenant | Restrictive covenant not to use the property other than for agricultural purposes and not to erect permanent or temporary structures as contained in a Transfer dated 17 November 2010 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | C. Hoare & Co. | 262 | SK276346 | Mortgage | as mortgagee to Emma May Alexandra Heald and Andrew Michael Hilliard Heald in respect of a legal charge dated 30 July 2012 registered under title SK276346 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | St. Edmundsbury and Ipswich Diocesan Board of Finance | 1326 | SK276346 | Restrictive Covenant | Restrictive covenant not to use the property other than for agricultural purposes and not to erect permanent or temporary structures as contained in a Transfer dated 17 November 2010 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK312683 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Anglian Water Services Limited | 82 | SK350290 | Easement Right or Privilege | Rights granted relating to a water pipe as contained in a Deed dated 8 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Anglian Water Services Limited | 82 | SK350290 | Restrictive Covenant | Restrictive covenants relating to a water pipe as contained in a Deed dated 8 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network |  |  | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK150493,SK400140 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK150493,SK407557 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK150493,SK404369 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Bondgrip Limited | 216 | SK323368,SK383769 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 | SK350196 | Easement Right or Privilege | Rights relating the use and maintenance of pipes and drains as contained in a Deed dated 15 October 1999 |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 | SK350196 | Restrictive Covenant | Restrictive covenants to only use land as a footpath or for agricultural purposes and to not erect structures, plant trees or interfere with the vertical or lateral support of pipes as contained in a Deed dated 15 October 1999 |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK350196 | Easement Right or Privilege | Rights relating the use and maintenance of pipes and drains as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK350196 | Restrictive Covenant | Restrictive covenants to only use land as a footpath or for agricultural purposes and to not erect structures, plant trees or interfere with the vertical or lateral support of pipes as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK290870 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christine Louise Fincham | 133 | SK140659,SK290870 | Easement Right or Privilege | Right of entry and rights relating to water pipes as contained in a Conveyance dated 14 August 1989 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Eastern Power Networks plc | 254 | SK290870 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1987 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anthony Leonard Rupert Fincham | 415 | SK140659,SK290870,RTS Notices | Easement Right or Privilege | Right of entry and rights relating to water pipes as contained in a Conveyance dated 14 August 1989 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Rights relating to service media, boundary fences and support as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK312683 | Easement Right or Privilege | Rights granted relating to a water pipe as contained in a Deed dated 8 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK312683 | Restrictive Covenant | Restrictive covenants not to use land except as a footpath or for agricultural or horticultural purposes or as a garden, not to erect buildings or plant trees, not to alter the depth of land and not to withdraw vertical or lateral support from water pipes |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Nicholas Nigel Green | 170 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity cables and works as contained in a Deed dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Martin Cotter | 761 | SK259100 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK312683,SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Bondgrip Limited | 216 | SK323368,SK383769 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Hilary June Hatfield | 470 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Hilary June Hatfield | 470 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Bondgrip Limited | 216 | SK323368,SK383769 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Bondgrip Limited | 216 | SK323368,SK383769 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Hilary June Hatfield | 470 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Hilary June Hatfield | 470 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Bondgrip Limited | 216 | SK323368,SK383769 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hilary June Hatfield | 470 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy Charles David Hatfield | 586 | SK241684,SK323368 | Restrictive Covenant | Restrictive covenants not to obstruct service media as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sophia Frances Peto | 678 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | East Suffolk Council | 548 | SK292493,SK354374 | Easement Right or Privilege | Rights reserved relating to services as contained in a Transfer dated 10 June 2014 |  | Category 2 | N/A | Yes | RR-1420 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | East Suffolk Council | 548 | SK292493,SK354374 | Restrictive Covenant | Restrictive covenant not to use the property for any purpose other than amenity land and nature reserve and ensure that land is kept open to the public at all times as contained in a Transfer dated 10 June 2014 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-1420 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lisa Gail Hasler | 57 | SK254614,SK304349 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 25 April 2008 for the benefit of 2 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Steven Neil Pammenter | 92 | SK254614,SK326983 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 7 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Karen Pammenter | 129 | SK254614,SK326983 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 7 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janet Jennaway | 155 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Olivia Jane Nicholson | 163 | SK254614,SK335127 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 November 2011 for the benefit of 11 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kathryn Alison Hawkins | 175 | SK254614,SK361255 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 8 July 2015 for the benefit of 10 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | John Duthie Eric Butcher | 176 | SK254614,SK316573 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 27 April 2009 for the benefit of 3 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jens Haustrup | 191 | SK254614,SK326643 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 4 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jenifer Mary Jennaway | 282 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Graham McKirdy | 299 | SK254614,SK366967 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 11 March 2016 for the benefit of 5 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Glenda Haustrup | 361 | SK254614,SK326643 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 4 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | John Graham Panrucker | 432 | SK254614,SK374354 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 July 2016 for the benefit of 6 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul William Hawkins | 446 | SK254614,SK361255 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 8 July 2015 for the benefit of 10 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Judith Mary McKirdy | 449 | SK254614,SK366967 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 11 March 2016 for the benefit of 5 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Richard Pearce | 577 | SK254614,SK355713 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 4 September 2014 for the benefit of 9 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Simon Bernard Nicholson | 578 | SK254614,SK335127 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 November 2011 for the benefit of 11 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Frances Margaret Panrucker | 621 | SK254614,SK374354 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 July 2016 for the benefit of 6 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jane Taylor | 714 | SK254614,SK322506 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 26 February 2010 for the benefit of 1 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Shane Louis Hasler | 729 | SK254614,SK304349 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 25 April 2008 for the benefit of 2 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Richard William Jennaway | 735 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Suffolk County Council | 755 | SK254614 | Restrictive Covenant | Restrictive covenant that the dwelling house shall not be disposed of separately from the adjoining land and shall be occupied by a person employed locally in agriculture or forestry as contained in an Agreement dated 16 August 1989 |  | Category 2 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Peter Henry Marshall | 3569 | SK254614,SK327038 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 12 Chapel Barn Lodges |  | Category 2 |  | No | [13 empty] | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK292493,SK354374 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 10 June 2014 for the benefit of adjoining land |  | Category 2 | John Coates, Bidwells | Yes | RR-4651 REP1-158 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Neil Copinger Mahony | 174 | SK198325,SK210743 | Easement Right or Privilege | Right of way as contained in a Deed dated 17 October 1996 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK210743 | Restrictive Covenant | No disposition of the part of the registered estate tinted yellow by the proprietor of the registered estate is to be registered without a certificate signed by ScottishPower Renewables (UK) Limited |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Flagship Housing Limited | 554 | SK379333 | Restrictive Covenant | Restriction against disposition of the freehold estate |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493,SK379333 | Easement Right or Privilege | Right to pass and repass and unknown rights as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK379333,SK400140 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK379333,SK400140 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katarzyna Ewa Clark | 3492 | SK379333,SK400140 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK379333,SK402512 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK379333,SK402512 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Cox | 3497 | SK379333,SK402512 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK379333,SK403456 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK379333,SK403456 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Keely Maria Holcombe | 3499 | SK379333,SK403456 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK379333,SK407557 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Zara Alice Smith | 3500 | SK379333,SK407557 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK379333,SK408279 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK379333,SK408279 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Margaret Woodbine | 3504 | SK379333,SK408279 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK379333,SK407307 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK379333,SK407307 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Dunn | 3505 | SK379333,SK407307 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK379333,SK404369 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK379333,SK404369 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard Stuart Kay | 3511 | SK379333,SK404369 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK379333,SK404369 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK379333,SK404369 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lorraine Ruth Kay | 3512 | SK379333,SK404369 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Barclays Bank plc | 66 | SK328388 | Restrictive Covenant | Restrictive covenants to only use land as a bird sanctuary and/or nature reserve and to erect boundary posts as contained in a Conveyance dated 16 October 1950 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The Public Trustee | 825 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land | as Personal Representative to the Estate of Terence James Martin Haworth | Category 2 | No Agent Known | Yes | RR-5322 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Pamela Tile | 1205 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK292493,SK354374 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 10 June 2014 for the benefit of adjoining land |  | Category 2 | John Coates, Bidwells | Yes | RR-4651 REP1-158 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Public Trustee | 825 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land | as Personal Representative to the Estate of Terence James Martin Haworth | Category 2 | No Agent Known | Yes | RR-5322 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
6/6 | Suffolk Sheet 6 | 143 square metres, or thereabouts, of car park, scrubland and path situated to the east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK292493,SK354374 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 10 June 2014 for the benefit of adjoining land |  | Category 2 | John Coates, Bidwells | Yes | RR-4651 REP1-158 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Reginald Anthony Wainwright | 303 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Edmund Michael Wood | 451 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lady Patricia Ann Hopkins | 533 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lady Patricia Ann Hopkins | 533 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sir Michael John Hopkins | 556 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Georgeta Catargiu | 1270 |  | Restrictive Covenant | Restrictive covenant not to keep or breed pigs or poultry or erect buildings for the breeding or keeping of livestock as contained in an Assent dated 18 May 2000 for the benefit of adjoining land | As Personal Representative to the Estate of Martin Peter Handscombe | Category 2 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. |  |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Joel Hopkins | 2746 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Abigail Hopkins | 2747 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | Yes | RR-0010 | [10 empty] | No Heads of Terms Required |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sarah Younger | 2748 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK210743 | Restrictive Covenant | No disposition of the part of the registered estate tinted yellow by the proprietor of the registered estate is to be registered without a certificate signed by ScottishPower Renewables (UK) Limited |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK210743 | Restrictive Covenant | No disposition of the part of the registered estate tinted yellow by the proprietor of the registered estate is to be registered without a certificate signed by ScottishPower Renewables (UK) Limited |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Stephen Arthur Roberts | 161 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Wendy Lynn Skinner | 334 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Paul Jonathan Skene Smith | 706 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | Yes | REP2-098 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Roger Alfred Stanley Skinner | 734 | SK307876,SK317263,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions requested and under negotiation | No Heads of Terms Required |  | 2025-10-08
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Simon Jonathan Haskell | 1822 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Katherine Jane Haskell | 1823 | SK336019,SK227448 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 12 October 1987 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Reginald Anthony Wainwright | 303 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edmund Michael Wood | 451 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lady Patricia Ann Hopkins | 533 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lady Patricia Ann Hopkins | 533 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sir Michael John Hopkins | 556 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Joel Hopkins | 2746 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Abigail Hopkins | 2747 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | Yes | RR-0010 | [10 empty] | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Younger | 2748 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pamela Tile | 1205 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Restrictive Covenant | Restrictive covenants relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK151617 | Easement Right or Privilege | Unilateral notice in respect of Option Agreement dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK151617 | Easement Right or Privilege | Unilateral notice in respect of Option Agreement dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09

## Category 2 Unknowns
South East Anglia Link: Detailed Land and Rights Negotiations Tracker - Category 2 interests
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | PIL Name | PIL Reference/Land Referencing PartyID | Title Number(s) | Interest Type | Interest Description | Party Interest capacity | Category | Agent/ representative (if any) | Relevant Representation | When available Relevant representation reference number | When available Written representation reference number | Other document reference number | Applicant's response references | Special category (allotment, National Trust etc) (Select from drop down list) | Crown | Special category - other information including confirmation of status | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Summary of Negotation Status | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1820 | K410629 | Restrictive Covenant | Covenant to supply sand and ballast extracted from land as contained in a Deed dated 27 November 1946 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-09
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1840 | K410629 | Easement Right or Privilege | Rights to make use of any passages not being less than one hundred feet below the surface for the purpose of working and carrying away coal or other minerals lying within or under land as contained in a Conveyance dated 31 March 1922 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-10
2/46 | Kent Sheet 2 | 26 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-11
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-12
2/48 | Kent Sheet 2 | 11 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-13
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-14
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-15
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-16
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-17
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-18
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-19
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-20
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-21
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | [8 empty] | Not SU |  |  | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-22
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | [8 empty] | Not SU |  |  | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-23
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-24
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-25
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-26
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-27
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-28
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2755 | K57595 | Easement Right or Privilege | Rights relating to water supply as contained in a Transfer dated 31 July 1992 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-29
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-30
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-31
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-01
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-02
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1629 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-03
2/77 | Kent Sheet 2 | 288 square metres, or thereabouts, of track and scrubland situated to the south west of Boxlees Hill, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1629 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-04
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1629 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-05
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3269 | K628577 | Easement Right or Privilege | Rights to pass and repass and rights relating to service media as contained in a Transfer dated 18 February 1987 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-06
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3269 | K628577 | Easement Right or Privilege | Rights to pass and repass and rights relating to service media as contained in a Transfer dated 18 February 1987 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-07
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 959 | TT29616 | Easement Right or Privilege | Rights relating to service media and rights of light and air as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-08
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 961 | TT29616 | Restrictive Covenant | Restrictive covenant relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1715 | TT29616 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-10
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1820 | K410629 | Restrictive Covenant | Covenant to supply sand and ballast extracted from land as contained in a Deed dated 27 November 1946 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-11
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1840 | K410629 | Easement Right or Privilege | Rights to make use of any passages not being less than one hundred feet below the surface for the purpose of working and carrying away coal or other minerals lying within or under land as contained in a Conveyance dated 31 March 1922 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-12
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 959 | TT29616 | Easement Right or Privilege | Rights relating to service media and rights of light and air as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-13
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 961 | TT29616 | Restrictive Covenant | Restrictive covenant relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-14
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1715 | TT29616 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-15
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-16
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 959 | TT29616 | Easement Right or Privilege | Rights relating to service media and rights of light and air as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-17
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 961 | TT29616 | Restrictive Covenant | Restrictive covenant relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-18
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1715 | TT29616 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-19
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-20
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-21
2/17 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-22
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1010 | K868267 | Easement Right or Privilege | Right of entry and right to retain landscaping area as contained in a Deed dated 6 May 1993 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-23
2/18 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2266 |  | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-24
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-25
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1820 | K410629 | Restrictive Covenant | Covenant to supply sand and ballast extracted from land as contained in a Deed dated 27 November 1946 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-26
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1840 | K410629 | Easement Right or Privilege | Rights to make use of any passages not being less than one hundred feet below the surface for the purpose of working and carrying away coal or other minerals lying within or under land as contained in a Conveyance dated 31 March 1922 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-27
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-28
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2268 | TT103427 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-01
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3268 | K273192 | Restrictive Covenant | Restrictive covenant not to excavate any sand or ballast as contained in a Deed dated 27 November 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-02
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 2268 | TT103427 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-03
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 959 | TT29616 | Easement Right or Privilege | Rights relating to service media and rights of light and air as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-04
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 961 | TT29616 | Restrictive Covenant | Restrictive covenant relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-05
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1715 | TT29616 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-06
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3268 | K273192 | Restrictive Covenant | Restrictive covenant not to excavate any sand or ballast as contained in a Deed dated 27 November 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-07
4/3 | Kent Sheet 4 | 47 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 865 | K405978 | Easement Right or Privilege | Power to let down surface, whether built upon or not, for the benefit of subjacent mines and minerals interests |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-08
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3266 | K563834 | Easement Right or Privilege | Rights relating to a pipe as contained in a Deed dated 23 May 1966 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-09
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 839 | K377019 | Rent Charge | Annual rent charge of £10 in favour of the Trustees of the Careys Charity |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-10
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 864 | K377019 | Easement Right or Privilege | Power to let down surface, whether built upon or not, for the benefit of subjacent mines and minerals interests |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-11
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1274 | K563834 | Restrictive Covenant | Covenants relating to the extraction and excavation of sand or ballast as contained in a Deed dated 27 December 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-12
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3266 | K563834 | Easement Right or Privilege | Rights relating to a pipe as contained in a Deed dated 23 May 1966 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-13
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 839 | K377019 | Rent Charge | Annual rent charge of £10 in favour of the Trustees of the Careys Charity |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-14
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 864 | K377019 | Easement Right or Privilege | Power to let down surface, whether built upon or not, for the benefit of subjacent mines and minerals interests |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-15
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1274 | K563834 | Restrictive Covenant | Covenants relating to the extraction and excavation of sand or ballast as contained in a Deed dated 27 December 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-16
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3266 | K563834 | Easement Right or Privilege | Rights relating to a pipe as contained in a Deed dated 23 May 1966 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-17
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 930 | K465344 | Restrictive Covenant | Restrictive covenant not to use the said property for any purpose which might be or grow to be a nuisance or annoyance as contained in a Conveyance dated 18 June 1948 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-18
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 808 | K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-19
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1820 | K410629 | Restrictive Covenant | Covenant to supply sand and ballast extracted from land as contained in a Deed dated 27 November 1946 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-20
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1840 | K410629 | Easement Right or Privilege | Rights to make use of any passages not being less than one hundred feet below the surface for the purpose of working and carrying away coal or other minerals lying within or under land as contained in a Conveyance dated 31 March 1922 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-21
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 959 | TT29616 | Easement Right or Privilege | Rights relating to service media and rights of light and air as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-22
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 961 | TT29616 | Restrictive Covenant | Restrictive covenant relating to a water supply pipe as contained in a Deed dated 22 March 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-23
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1715 | TT29616 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-24
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 944 | K518470 | Restrictive Covenant | Restrictive covenant relating to excavation of sand and ballast as contained in a Deed dated 27 November 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-25
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 973 | K518470 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 18 June 1948 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-26
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 944 | K518470 | Restrictive Covenant | Restrictive covenant relating to excavation of sand and ballast as contained in a Deed dated 27 November 1946 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-27
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 973 | K518470 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 18 June 1948 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-28
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-29
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-30
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-31
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-01
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-02
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 1010 | K868267 | Easement Right or Privilege | Right of entry and right to retain landscaping area as contained in a Deed dated 6 May 1993 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-03
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-04
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1010 | K868267 | Easement Right or Privilege | Right of entry and right to retain landscaping area as contained in a Deed dated 6 May 1993 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-05
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-06
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1005 | K838442 | Restrictive Covenant | Restrictive covenants to not grow or erect anything of a height more than 0.9 metres adjoining a roadside as contained in a Transfer dated 7 April 1992 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-07
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2259 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-08
3/103 | Kent Sheet 3 | 30 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2259 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-09
3/105 | Kent Sheet 3 | 112 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2259 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-10
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2259 | TT52585 | Easement Right or Privilege | Caution against first registration in respect of rights as contained in a Deed of Grant dated 5 July 2016 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-12
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3525 | SK313281 | Restrictive Covenant | The land is subject to such restrictive covenants and rentcharges as may have been imposed thereon before 16 December 2008 and are still subsisting and capable of being enforced |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-13
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1676 | SK346948 | Easement Right or Privilege | Rights relating to a water supply pipe as contained in a Deed dated 27 May 1987 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-14
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1677 | SK346948 | Restrictive Covenant | Covenant to maintain a water supply pipe as contained in a Deed dated 27 May 1987 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-15
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-16
7/31 | Suffolk Sheet 7 | 1,362 square metres, or thereabouts, of public adopted highways (B1121 and A12, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3534 | SK348406 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 15 September 1937 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-17
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1193 | SK328388 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 3 July 1978 for the benefit of adjoining land |  | Category 2 | No Agent Known | [8 empty] | Not SU |  |  | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-18
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1644 | SK328388 | Easement Right or Privilege | Right to pass and repass as contained in a Conveyance dated 9 August 1982 for the benefit of neighbouring land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-19
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1645 | SK328388 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 9 August 1982 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-20
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-21
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-22
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-23
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-24
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-25
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-26
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-27
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-28
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-29
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-30
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-01
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-02
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-03
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-04
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-05
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-06
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-07
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-08
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-10
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-11
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-12
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-13
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-14
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-15
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-16
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-17
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-18
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-19
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-20
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-21
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-22
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-23
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-24
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-25
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-26
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-27
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-28
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-29
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-30
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-31
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-01
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-02
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-03
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-04
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-05
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 956 | SK382238 | Restrictive Covenant | Restrictive covenants not to cause a nuisance, erect advertising hoardings or any buildings other than brick dwellinghouses and to not extract sand or gravel as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-06
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1064 | SK382238 | Restrictive Covenant | Restrictive covenants to maintain boundary fences and hedges and to not; use land for any purpose other than as a private dwellinghouse, erect advertising signs, place huts, sheds or caravans on land, keep livestock or use land as dog kennels, excavate sa |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-07
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3527 | SK150493 | Easement Right or Privilege | Rights relating to water supply as contained in a Conveyance dated 16 March 1990 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-08
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3528 | SK150493 | Easement Right or Privilege | Rights relating to maintenance of water pipes as contained in a Deed dated 3 April 1948 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-09
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-10
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-11
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-12
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-13
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-14
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-15
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1221 | SK307283 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence and no san |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-16
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3527 | SK150493 | Easement Right or Privilege | Rights relating to water supply as contained in a Conveyance dated 16 March 1990 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-17
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3528 | SK150493 | Easement Right or Privilege | Rights relating to maintenance of water pipes as contained in a Deed dated 3 April 1948 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-18
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-19
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-20
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-21
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 956 | SK382238 | Restrictive Covenant | Restrictive covenants not to cause a nuisance, erect advertising hoardings or any buildings other than brick dwellinghouses and to not extract sand or gravel as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-22
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1064 | SK382238 | Restrictive Covenant | Restrictive covenants to maintain boundary fences and hedges and to not; use land for any purpose other than as a private dwellinghouse, erect advertising signs, place huts, sheds or caravans on land, keep livestock or use land as dog kennels, excavate sa |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-23
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3524 | SK311340 | Restrictive Covenant | The land is subject to such restrictive covenants and rentcharges as may have been imposed thereon before 16 December 2008 and are still subsisting and capable of being enforced |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-24
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-25
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-26
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-27
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3527 | SK150493 | Easement Right or Privilege | Rights relating to water supply as contained in a Conveyance dated 16 March 1990 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-28
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3528 | SK150493 | Easement Right or Privilege | Rights relating to maintenance of water pipes as contained in a Deed dated 3 April 1948 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-29
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1221 | SK307283 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence and no san |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-30
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-01
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-02
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-03
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-04
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1221 | SK307283 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence and no san |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-05
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-06
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-07
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1220 | SK307283 | Restrictive Covenant | Restrictive covenants not to construct the main building of any house within forty feet of the western property boundary and to not be a nuisance as contained in a Conveyance dated 27 April 1927 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-08
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1221 | SK307283 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence and no san |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-09
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-10
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-11
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1221 | SK307283 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence and no san |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-12
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-13
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-14
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-15
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-16
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-17
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-18
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-19
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1217 | SK307283 | Restrictive Covenant | Restrictive covenants not to erect buildings other than a brick dwelling house and outbuildings, not to be a nuisance and not to place advertisement hoardings or caravans on the land as contained in a Conveyance dated 9 November 1931 for the benefit of un |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-20
7/25 | Suffolk Sheet 7 | 21 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3534 | SK348406 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 15 September 1937 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-21
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-22
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-23
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-24
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1193 | SK328388 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 3 July 1978 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-25
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1644 | SK328388 | Easement Right or Privilege | Right to pass and repass as contained in a Conveyance dated 9 August 1982 for the benefit of neighbouring land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-26
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1645 | SK328388 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 9 August 1982 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-27
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-28
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-29
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-30
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-31
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-01
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-02
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-03
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1304 | SK254614 | Restrictive Covenant | Restrictive covenants that no buildings shall be used as a lunatic asylum, convalescent home, factory or any business which shall be a nuisance and no advertisement hoarding, caravan or dwelling shall be placed on the land except as a residence as contain |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-04
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-05
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-06
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-07
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1321 | SK210743 | Restrictive Covenant | Restrictive covenants as may have been imposed before 5 February 1973 and are still subsisting and capable of being enforced |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-08
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1521 | SK210743 | Easement Right or Privilege | Rights of way |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-10
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-12
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-13
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3529 | SK379333 | Easement Right or Privilege | Rights relating to maintenance of water pipes as contained in a Deed dated 3 April 1948 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-14
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-15
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1193 | SK328388 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 3 July 1978 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-16
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1644 | SK328388 | Easement Right or Privilege | Right to pass and repass as contained in a Conveyance dated 9 August 1982 for the benefit of neighbouring land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-17
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1645 | SK328388 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 9 August 1982 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-18
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-19
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-20
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-21
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1180 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-22
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1182 | SK329337 | Easement Right or Privilege | Right of way as contained in an Agreement dated 5 October 1988 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-23
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-24
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-25
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-26
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-27
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-28
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-29
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-30
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-31
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-01
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1321 | SK210743 | Restrictive Covenant | Restrictive covenants as may have been imposed before 5 February 1973 and are still subsisting and capable of being enforced |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-02
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1521 | SK210743 | Easement Right or Privilege | Rights of way |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-03
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-04
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-05
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-06
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-07
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-08
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1321 | SK210743 | Restrictive Covenant | Restrictive covenants as may have been imposed before 5 February 1973 and are still subsisting and capable of being enforced |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-09
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1521 | SK210743 | Easement Right or Privilege | Rights of way |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-10
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-12
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-13
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-14
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-15
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-16
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-17
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-18
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-19
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1920 | SK336019 | Easement Right or Privilege | Unknown rights and covenants as contained in a Lease dated 10 January 1996 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-20
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-21
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1287 | SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-22
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1291 | SK257795 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-23
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-24
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-25
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1180 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-26
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1182 | SK329337 | Easement Right or Privilege | Right of way as contained in an Agreement dated 5 October 1988 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-27
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1183 | SK329337 | Restrictive Covenant | Unknown restrictive covenants as contained in a Conveyance dated 9 February 1932 for the benefit of unknown land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-28
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1193 | SK328388 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 3 July 1978 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-29
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1644 | SK328388 | Easement Right or Privilege | Right to pass and repass as contained in a Conveyance dated 9 August 1982 for the benefit of neighbouring land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-30
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1645 | SK328388 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 9 August 1982 for the benefit of adjoining land |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-01
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-02
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-03
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-04
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-05
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-06
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-07
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-08
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-10
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1354 | SK194564 | Easement Right or Privilege | Rights granted relating to removing game shot from the land transferred to the south of land in this title as contained in a Transfer dated 3 September 1996 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-12
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1004 | SK350290 | Easement Right or Privilege | Rights of way and service media as contained in a Conveyance dated 12 October 1987 |  | Category 2 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-13

## Table Comparison of Changes
Plot | Plan reference | Category | Removed | Added | Changed
1/1 | Kent Sheet 1 | CAT 2 | Judith Cracknell Clive Robert Stevens Christopher Russell John Domvile Barradale | Andrew William Johnson Unknown
1/10 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/10 | Kent Sheet 1 | CAT 1 |  | Unknown
1/100 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell - Webster Jill Gooch Thomas William Riddell-Webster
1/11 | Kent Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/11 | Suffolk Sheet 1 | CAT 2 |  | Unknown
1/12 | Kent Sheet 1 | CAT 1 |  | Unknown
1/13 | Kent Sheet 1 | CAT 1 |  | Unknown
1/14 | Kent Sheet 1 | CAT 1 |  | Unknown
1/14 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '229 square metres, or thereabouts, of public footpath (023) and overhead telecommunication lines situated to the south of The Manor House, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/15 | Kent Sheet 1 | CAT 2 | Anglian Water Services Limited
1/15 | Kent Sheet 1 | CAT 1 |  | Unknown
1/16 | Kent Sheet 1 | CAT 1 |  | Unknown
1/17 | Kent Sheet 1 | CAT 1 |  | Unknown
1/17 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '26244 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/18 | Kent Sheet 1 | CAT 1 |  | Unknown
1/19 | Suffolk Sheet 1 | CAT 2 |  | Northumbrian Water Limited
1/19 | Kent Sheet 1 | CAT 1 |  | Unknown
1/2 | Suffolk Sheet 1 | CAT 2 |  | Gordon Young Unknown
1/2 | Kent Sheet 1 | CAT 2 | Christopher Russell John Domvile Barradale Clive Robert Stevens Judith Cracknell | Andrew William Johnson
1/2 | Kent Sheet 1 | CAT 2 |  | Unknown
1/20 | Kent Sheet 1 | CAT 1 |  | Unknown
1/21 | Kent Sheet 1 | CAT 1 |  | Unknown
1/22 | Kent Sheet 1 | CAT 1 |  | Unknown
1/3 | Kent Sheet 1 | CAT 1 |  | Unknown
1/31 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '19733 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage' to '19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage'
1/32 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '3405 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk Class 7. Compulsory Acquisition of Rights - Mitigation' to '673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation'
1/33 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/4 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/4 | Kent Sheet 1 | CAT 1 |  | Unknown
1/45 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '4046 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk Class 7. Compulsory Acquisition of Rights - Mitigation' to '4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation'
1/47 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '2904 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk Class 5. Compulsory Acquisition of Rights - Access' to '2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access'
1/49 | Suffolk Sheet 1 | CAT 2 | HSBC Bank plc HSBC UK Bank plc Ian Charles Rix James Henry Rogers National Grid Electricity Transmission plc ScottishPower (UK) Renewables Limited |  | Description of land and rights requested changed from '52906 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System' to '29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System'
1/49a | Suffolk Sheet 1 | CAT 2 |  | Ian Charles Rix James Henry Rogers National Grid Electricity Transmission plc ScottishPower (UK) Renewables Limited
1/5 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown | Description of land and rights requested changed from '420 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk Class 5. Compulsory Acquisition of Rights - Access' to '419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access'
1/5 | Kent Sheet 1 | CAT 1 |  | Unknown
1/58 | Suffolk Sheet 1 | CAT 2 | HSBC Bank plc
1/6 | Kent Sheet 1 | CAT 1 |  | Unknown
1/60 | Suffolk Sheet 1 | CAT 2 |  |  | Description of land and rights requested changed from '208 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk Class 7. Compulsory Acquisition of Rights Mitigation' to '7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights Mitigation'
1/62 | Suffolk Sheet 1 | CAT 2 | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster HSBC Bank plc Jill Gooch Thomas William Riddell-Webster
1/63 | Suffolk Sheet 1 | CAT 2 | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster HSBC Bank plc Jill Gooch Thomas William Riddell-Webster
1/64 | Suffolk Sheet 1 | CAT 2 | HSBC Bank plc |  | Description of land and rights requested changed from '1793 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk Class 5. Compulsory Acquisition of Rights - Access' to '1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access'
1/66 | Suffolk Sheet 1 | CAT 2 | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster HSBC Bank plc Jill Gooch Thomas William Riddell-Webster
1/67 | Suffolk Sheet 1 | CAT 2 | HSBC Bank plc
1/69 | Suffolk Sheet 1 | CAT 2 | HSBC UK Bank plc
1/7 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/7 | Kent Sheet 1 | CAT 1 |  | Unknown
1/70 | Suffolk Sheet 1 | CAT 2 | HSBC UK Bank plc
1/71 | Suffolk Sheet 1 | CAT 2 | HSBC UK Bank plc
1/72 | Suffolk Sheet 1 | CAT 2 | HSBC UK Bank plc
1/73 | Suffolk Sheet 1 | CAT 2 | HSBC UK Bank plc
1/75 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/76 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/77 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/78 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/79 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/8 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/8 | Kent Sheet 1 | CAT 1 |  | Unknown
1/80 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/81 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/82 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/83 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/84 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited
1/85 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/86 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/87 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/9 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas | Gordon Young Unknown
1/9 | Kent Sheet 1 | CAT 1 |  | Unknown
1/90 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/92 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster Jill Gooch Thomas William Riddell-Webster
1/93 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster Jill Gooch Thomas William Riddell-Webster
1/94 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster Jill Gooch Thomas William Riddell-Webster
1/95 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster Jill Gooch Thomas William Riddell-Webster
1/99 | Suffolk Sheet 1 | CAT 2 |  | Anglian Water Services Limited Cadent Gas Limited Colonel Michael Lawrence Riddell-Webster Jill Gooch Thomas William Riddell-Webster
2/1 | Kent Sheet 2 | CAT 1 |  | Unknown
2/10 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/10 | Kent Sheet 2 | CAT 1 |  | Unknown
2/101 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/102 | Suffolk Sheet 2 | CAT 2 |  | Lloyds Bank plc Robert Andrew Barr Unknown
2/102 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/103 | Suffolk Sheet 2 | CAT 2 |  | Lloyds Bank plc Robert Andrew Barr Unknown
2/103 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/104 | Suffolk Sheet 2 | CAT 2 |  | Lloyds Bank plc Robert Andrew Barr Unknown
2/104 | Kent Sheet 2 | CAT 1 |  | Unknown
2/104 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/105 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/107 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/108 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/109 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/11 | Suffolk Sheet 2 | CAT 2 | Fiona Clare Cramb HSBC UK Bank plc Ian Charles Rix James Henry Rogers National Grid Electricity Transmission plc Nicholas Nigel Green
2/11 | Kent Sheet 2 | CAT 1 |  | Unknown
2/110 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/111 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/112 | Suffolk Sheet 2 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
2/12 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/12 | Kent Sheet 2 | CAT 1 |  | Unknown
2/125 | Kent Sheet 2 | CAT 2 |  | Unknown
2/125 | Kent Sheet 2 | CAT 1 |  | Unknown
2/126 | Kent Sheet 2 | CAT 2 |  | Unknown
2/126 | Kent Sheet 2 | CAT 1 |  | Unknown
2/13 | Kent Sheet 2 | CAT 1 |  | Unknown
2/132 | Kent Sheet 2 | CAT 2 |  | Unknown
2/132 | Kent Sheet 2 | CAT 1 |  | Unknown
2/133 | Kent Sheet 2 | CAT 2 |  | Unknown
2/133 | Kent Sheet 2 | CAT 1 |  | Unknown
2/138 | Kent Sheet 2 | CAT 1 |  | Unknown
2/139 | Kent Sheet 2 | CAT 1 |  | Unknown
2/14 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/14 | Kent Sheet 2 | CAT 1 |  | Unknown
2/140 | Kent Sheet 2 | CAT 1 |  | Unknown
2/142 | Kent Sheet 2 | CAT 1 |  | Unknown
2/144 | Kent Sheet 2 | CAT 2 |  | Unknown
2/145 | Kent Sheet 2 | CAT 2 |  | Unknown
2/147 | Kent Sheet 2 | CAT 2 |  | Unknown
2/149 | Kent Sheet 2 | CAT 2 |  | Unknown
2/15 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/150 | Kent Sheet 2 | CAT 2 |  | Unknown
2/152 | Kent Sheet 2 | CAT 2 |  | Unknown
2/153 | Kent Sheet 2 | CAT 2 |  | Unknown
2/154 | Kent Sheet 2 | CAT 2 |  | Unknown
2/16 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/16 | Kent Sheet 2 | CAT 2 |  | Unknown
2/162 | Kent Sheet 2 | CAT 1 |  | Unknown
2/163 | Kent Sheet 2 | CAT 1 |  | Unknown
2/164 | Kent Sheet 2 | CAT 1 |  | Unknown
2/165 | Kent Sheet 2 | CAT 1 |  | Unknown
2/167 | Kent Sheet 2 | CAT 1 |  | Unknown
2/17 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/17 | Kent Sheet 2 | CAT 2 |  | Unknown
2/173 | Kent Sheet 2 | CAT 1 |  | Unknown
2/174 | Kent Sheet 2 | CAT 1 |  | Unknown
2/177 | Kent Sheet 2 | CAT 1 |  | Unknown
2/178 | Kent Sheet 2 | CAT 1 |  | Unknown
2/179 | Kent Sheet 2 | CAT 1 |  | Unknown
2/18 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc
2/18 | Kent Sheet 2 | CAT 2 |  | Unknown
2/180 | Kent Sheet 2 | CAT 1 |  | Unknown
2/182 | Kent Sheet 2 | CAT 1 |  | Unknown
2/183 | Kent Sheet 2 | CAT 1 |  | Unknown
2/2 | Kent Sheet 2 | CAT 1 |  | Unknown
2/20 | Suffolk Sheet 2 | CAT 2 | HSBC UK Bank plc National Grid Electricity Transmission plc
2/20a | Suffolk Sheet 2 | CAT 2 | Lloyds Bank plc Robert Andrew Barr | Unknown
2/21 | Kent Sheet 2 | CAT 1 |  | Unknown
2/22a | Suffolk Sheet 2 | CAT 2 |  | Andrea Jane McMillan Dominic Richard Upton Mark Cosgrove Zoe Est Cosgrove
2/24 | Kent Sheet 2 | CAT 1 |  | Unknown
2/27 | Kent Sheet 2 | CAT 1 |  | Unknown
2/28 | Kent Sheet 2 | CAT 1 |  | Unknown
2/29 | Kent Sheet 2 | CAT 1 |  | Unknown
2/3 | Kent Sheet 2 | CAT 1 |  | Unknown
2/31 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/4 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/4 | Kent Sheet 2 | CAT 1 |  | Unknown
2/41 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/41 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/44 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/44 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/46 | Kent Sheet 2 | CAT 2 |  | Unknown
2/47 | Kent Sheet 2 | CAT 2 |  | Unknown
2/48 | Kent Sheet 2 | CAT 2 |  | Unknown
2/49 | Kent Sheet 2 | CAT 2 |  | Unknown
2/5 | Suffolk Sheet 2 | CAT 2 | HSBC Bank plc
2/5 | Kent Sheet 2 | CAT 1 |  | Unknown
2/50 | Kent Sheet 2 | CAT 2 |  | Unknown
2/50 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/50 | Kent Sheet 2 | CAT 1 |  | Unknown
2/50 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/51 | Kent Sheet 2 | CAT 2 |  | Unknown
2/51 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/51 | Kent Sheet 2 | CAT 1 |  | Unknown
2/51 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/52 | Kent Sheet 2 | CAT 2 |  | Unknown
2/52 | Kent Sheet 2 | CAT 1 |  | Unknown
2/53 | Kent Sheet 2 | CAT 2 |  | Unknown
2/53 | Kent Sheet 2 | CAT 1 |  | Unknown
2/54 | Kent Sheet 2 | CAT 2 |  | Unknown
2/54 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/54 | Kent Sheet 2 | CAT 1 |  | Unknown
2/54 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/55 | Suffolk Sheet 2 | CAT 2 | Lloyds Bank plc Robert Andrew Barr | Unknown
2/55 | Kent Sheet 2 | CAT 2 |  | Unknown
2/55 | Kent Sheet 2 | CAT 1 |  | Unknown
2/56 | Kent Sheet 2 | CAT 2 |  | Unknown
2/57 | Kent Sheet 2 | CAT 2 |  | Unknown
2/59 | Kent Sheet 2 | CAT 2 |  | Unknown
2/59 | Kent Sheet 2 | CAT 1 |  | Unknown
2/6 | Suffolk Sheet 2 | CAT 2 | HSBC Bank plc
2/6 | Kent Sheet 2 | CAT 1 |  | Unknown
2/60 | Kent Sheet 2 | CAT 2 |  | Unknown
2/60 | Kent Sheet 2 | CAT 1 |  | Unknown
2/61 | Kent Sheet 2 | CAT 2 |  | Unknown
2/63 | Kent Sheet 2 | CAT 2 |  | Unknown
2/63 | Kent Sheet 2 | CAT 1 |  | Unknown
2/66 | Kent Sheet 2 | CAT 2 |  | Unknown
2/66 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/67 | Kent Sheet 2 | CAT 2 |  | Unknown
2/68 | Kent Sheet 2 | CAT 2 |  | Unknown
2/7 | Suffolk Sheet 2 | CAT 2 | HSBC Bank plc
2/7 | Kent Sheet 2 | CAT 1 |  | Unknown
2/74 | Kent Sheet 2 | CAT 2 |  | Unknown
2/77 | Kent Sheet 2 | CAT 2 |  | Unknown
2/78 | Suffolk Sheet 2 | CAT 2 | Andrew Michael Hilliard Heald Emma May Alexandra Heald ScottishPower (UK) Renewables Limited
2/78a | Suffolk Sheet 2 | CAT 2 |  | Andrew Michael Hilliard Heald Emma May Alexandra Heald ScottishPower (UK) Renewables Limited
2/78b | Suffolk Sheet 2 | CAT 2 |  | Andrew Michael Hilliard Heald Emma May Alexandra Heald ScottishPower (UK) Renewables Limited
2/8 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/8 | Kent Sheet 2 | CAT 1 |  | Unknown
2/81 | Kent Sheet 2 | CAT 2 |  | Unknown
2/84 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/85 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/87 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/88 | Suffolk Sheet 2 | CAT 2 | Lloyds Bank plc Robert Andrew Barr
2/89 | Suffolk Sheet 2 | CAT 2 | Lloyds Bank plc Robert Andrew Barr
2/9 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/9 | Kent Sheet 2 | CAT 1 |  | Unknown
2/90 | Suffolk Sheet 2 | CAT 2 |  | Unknown
2/90 | Kent Sheet 2 | CAT 1 |  | Unknown
2/90 | Suffolk Sheet 2 | CAT 1 |  | Unknown
2/91 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/92 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/93 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/93 | Kent Sheet 2 | CAT 1 |  | Unknown
2/94 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/94 | Kent Sheet 2 | CAT 1 |  | Unknown
2/95 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/95 | Kent Sheet 2 | CAT 1 |  | Unknown
2/96 | Suffolk Sheet 2 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
2/96 | Kent Sheet 2 | CAT 1 |  | Unknown
2/99 | Kent Sheet 2 | CAT 1 |  | Unknown
3/1 | Offshore Sheet 3 | CAT 2 | Coal Authority Pfizer Limited
3/1 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/1 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/10 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/10 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/101 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Unknown
3/102 | Kent Sheet 3 | CAT 2 |  | Kent Wildlife Trust Nemo Link Limited Southern Water Services Limited Thanet District Council
3/102 | Kent Sheet 3 | CAT 1 |  | Unknown
3/103 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Unknown
3/104 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council
3/104 | Kent Sheet 3 | CAT 1 |  | Unknown
3/105 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Unknown
3/106 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Unknown
3/107 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council
3/107 | Kent Sheet 3 | CAT 1 |  | Unknown
3/108 | Kent Sheet 3 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
3/109 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
3/109 | Kent Sheet 3 | CAT 1 |  | Unknown
3/11 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/11 | Kent Sheet 3 | CAT 1 |  | Unknown
3/11 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/110 | Kent Sheet 3 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
3/110 | Kent Sheet 3 | CAT 1 |  | Unknown
3/111 | Kent Sheet 3 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
3/112 | Kent Sheet 3 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
3/12 | Kent Sheet 3 | CAT 2 |  | Unknown
3/12 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/12 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/13 | Kent Sheet 3 | CAT 2 |  | Unknown
3/13 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/13 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/14 | Kent Sheet 3 | CAT 2 |  | Unknown
3/14 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/14 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/15 | Kent Sheet 3 | CAT 2 |  | Unknown
3/15 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/15 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/16 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/16 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/17 | Suffolk Sheet 3 | CAT 2 | Robert Andrew Barr | Unknown
3/17 | Kent Sheet 3 | CAT 1 |  | Unknown
3/19 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/19 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/2 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/2 | Kent Sheet 3 | CAT 1 |  | Unknown
3/2 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/20 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/20 | Kent Sheet 3 | CAT 1 |  | Unknown
3/20 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/20a | Kent Sheet 3 | CAT 1 |  | Unknown
3/21 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/21 | Kent Sheet 3 | CAT 1 |  | Unknown
3/21 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/22 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/22 | Kent Sheet 3 | CAT 1 |  | Unknown
3/22 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/23 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/24 | Suffolk Sheet 3 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
3/25 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/26 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/27 | Suffolk Sheet 3 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
3/27 | Kent Sheet 3 | CAT 1 |  | Unknown
3/28 | Suffolk Sheet 3 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
3/28 | Kent Sheet 3 | CAT 1 |  | Unknown
3/29 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/3 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/3 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/30 | Suffolk Sheet 3 | CAT 2 | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead
3/31 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/32 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/33 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/36 | Suffolk Sheet 3 | CAT 2 | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/36 | Kent Sheet 3 | CAT 1 |  | Unknown
3/37 | Kent Sheet 3 | CAT 1 |  | Unknown
3/38 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/38 | Kent Sheet 3 | CAT 1 |  | Unknown
3/39 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/39 | Kent Sheet 3 | CAT 1 |  | Unknown
3/4 | Kent Sheet 3 | CAT 2 |  | Unknown
3/4 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/4 | Kent Sheet 3 | CAT 1 |  | Unknown
3/4 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/40 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/40 | Kent Sheet 3 | CAT 1 |  | Unknown
3/41 | Suffolk Sheet 3 | CAT 2 |  | Lloyds Bank plc Robert Andrew Barr Unknown
3/41 | Kent Sheet 3 | CAT 1 |  | Unknown
3/41 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/42 | Suffolk Sheet 3 | CAT 2 |  | Lloyds Bank plc Robert Andrew Barr Unknown
3/42 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/43 | Suffolk Sheet 3 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
3/44 | Suffolk Sheet 3 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
3/45 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Unknown Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/46 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Unknown Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/46 | Kent Sheet 3 | CAT 1 |  | Unknown
3/47 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Unknown Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings
3/47 | Kent Sheet 3 | CAT 1 |  | Unknown
3/48 | Suffolk Sheet 3 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
3/49 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/5 | Kent Sheet 3 | CAT 2 |  | Unknown
3/5 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/5 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/50 | Suffolk Sheet 3 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
3/51 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/52 | Suffolk Sheet 3 | CAT 2 |  | Blackheath Farms Limited C. Hoare & Co. David Winston Langmead Unknown
3/53 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/55 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/55 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/56 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/57 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/59 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/59 | Kent Sheet 3 | CAT 2 |  | Unknown
3/6 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/6 | Kent Sheet 3 | CAT 1 |  | Unknown
3/6 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/60 | Kent Sheet 3 | CAT 2 |  | Unknown
3/61 | Kent Sheet 3 | CAT 2 |  | Unknown
3/63 | Suffolk Sheet 3 | CAT 2 |  | Anglian Water Services Limited Blackheath Farms Limited Connie Amber Peck George William Barrington-Phillips Janette Nicola Packard Karen Mavis Greenham Laura Sunderland Lucinda Jane Fullerton Heald Mark Adrian Haines Megan Emma Stebbings Megan Emma Stebbings Michael Guy Hilliard Heald Paul Andrew Greenham Paul Gavin Shearer Rebecca Jane Willard Samuel John Townend Scott Daniel Flint ScottishPower (UK) Renewables Limited Tamara Dagma Suaris Townend William James Stebbings Unknown
3/65 | Kent Sheet 3 | CAT 2 |  | Unknown
3/68 | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited
3/68a | Kent Sheet 3 | CAT 2 | Kent Wildlife Trust Nemo Link Limited Southern Water Services Limited Thanet District Council
3/68b | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited
3/68c | Kent Sheet 3 | CAT 2 | Kent Wildlife Trust Nemo Link Limited Thanet District Council
3/68d | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited
3/69 | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited
3/7 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/7 | Kent Sheet 3 | CAT 1 |  | Unknown
3/7 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/70 | Kent Sheet 3 | CAT 2 | Kent Wildlife Trust Nemo Link Limited Thanet District Council
3/71 | Kent Sheet 3 | CAT 2 | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
3/72 | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
3/73 | Kent Sheet 3 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
3/74 | Kent Sheet 3 | CAT 1 |  | Unknown
3/75 | Kent Sheet 3 | CAT 1 |  | Unknown
3/76 | Kent Sheet 3 | CAT 1 |  | Unknown
3/8 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/8 | Kent Sheet 3 | CAT 1 |  | Unknown
3/8 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/9 | Suffolk Sheet 3 | CAT 2 |  | Unknown
3/9 | Kent Sheet 3 | CAT 1 |  | Unknown
3/9 | Suffolk Sheet 3 | CAT 1 |  | Unknown
3/90 | Kent Sheet 3 | CAT 2 |  | Unknown
3/97 | Kent Sheet 3 | CAT 2 |  | Unknown
3/98 | Kent Sheet 3 | CAT 1 |  | Unknown
4/1 | Kent Sheet 4 | CAT 1 |  | Unknown
4/10 | Kent Sheet 4 | CAT 2 |  | Unknown
4/10 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/11 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/12 | Suffolk Sheet 4 | CAT 2 |  | Abigail Hopkins Joel Hopkins Sarah Younger
4/14 | Kent Sheet 4 | CAT 2 |  | Unknown
4/14 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/15 | Kent Sheet 4 | CAT 2 |  | Unknown
4/15 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/16 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/17 | Kent Sheet 4 | CAT 2 |  | Unknown
4/17 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/18 | Kent Sheet 4 | CAT 2 | Helen Clare Mather | Belle Isle Holdings Limited Unknown
4/19 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/2 | Kent Sheet 4 | CAT 2 |  | Unknown
4/2 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/24 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/25 | Kent Sheet 4 | CAT 2 |  | Unknown
4/25 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/26 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/28 | Kent Sheet 4 | CAT 1 |  | Unknown
4/3 | Kent Sheet 4 | CAT 2 |  | Unknown
4/3 | Kent Sheet 4 | CAT 1 |  | Unknown
4/4 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/5 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/5 | Kent Sheet 4 | CAT 1 |  | Unknown
4/6 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/7 | Suffolk Sheet 4 | CAT 2 |  | Joel Hopkins
4/8 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/9 | Suffolk Sheet 4 | CAT 2 |  | Unknown
5/1 | Kent Sheet 5 | CAT 2 | The Marquess Conyngham
5/1 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/1 | Kent Sheet 5 | CAT 1 |  | Unknown
5/10 | Kent Sheet 5 | CAT 2 | Coal Authority | Mining Remediation Authority
5/10 | Kent Sheet 5 | CAT 2 |  | Unknown
5/10 | Kent Sheet 5 | CAT 2 |  | Unknown
5/10 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/10 | Kent Sheet 5 | CAT 1 |  | Unknown
5/11 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/12 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 2 | Coal Authority | Mining Remediation Authority
5/13 | Kent Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 2 |  | Unknown
5/13 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 1 |  | Unknown
5/15 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/16 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 2 | Coal Authority
5/18 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority
5/18 | Kent Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 2 |  | Unknown
5/18 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 1 |  | Unknown
5/19 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/2 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/2 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/20 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/20 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/21 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited | Unknown
5/22 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited | Unknown
5/23 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited | Unknown
5/24 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/25 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/25 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/26 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Kent Sheet 5 | CAT 1 |  | Unknown
5/27 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/27 | Kent Sheet 5 | CAT 1 |  | Unknown
5/27 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/28 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/28 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/28 | Kent Sheet 5 | CAT 1 |  | Unknown
5/29 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/29 | Kent Sheet 5 | CAT 1 |  | Unknown
5/29 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/3 | Kent Sheet 5 | CAT 2 | Barclays Security Trustee Limited Kent County Council Nemo Link Limited Personal Representative to the Estate of Carolyn Joy Marshall Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham The Public Trustee Vattenfall Wind Power Limited | Peter Henry Marshall
5/3 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/30 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/30 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/30a | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/31 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/31 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/32 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/32 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/33 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/34 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/34 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/35 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/36 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/37 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/37 | Kent Sheet 5 | CAT 1 |  | Unknown
5/38 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority Pfizer Limited Unknown
5/38 | Kent Sheet 5 | CAT 1 |  | Unknown
5/39 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/4 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/4 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/40 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/40 | Kent Sheet 5 | CAT 1 |  | Unknown
5/41 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/41 | Kent Sheet 5 | CAT 1 |  | Unknown
5/42 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/42 | Kent Sheet 5 | CAT 1 |  | Unknown
5/43 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/43 | Kent Sheet 5 | CAT 1 |  | Unknown
5/44 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/44 | Kent Sheet 5 | CAT 1 |  | Unknown
5/45 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/46 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/47 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/48 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited
5/5 | Kent Sheet 5 | CAT 2 | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/5 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/6 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/7 | Kent Sheet 5 | CAT 2 | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/7 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/8 | Kent Sheet 5 | CAT 2 | The Marquess Conyngham
5/8 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/9 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/9 | Kent Sheet 5 | CAT 1 |  | Unknown
6/1 | Kent Sheet 6 | CAT 2 |  | Unknown
6/1 | Suffolk Sheet 6 | CAT 2 |  | Unknown
6/2 | Kent Sheet 6 | CAT 2 |  | Unknown
6/3 | Kent Sheet 6 | CAT 2 |  | Unknown
6/4 | Kent Sheet 6 | CAT 2 |  | Unknown
6/4 | Kent Sheet 6 | CAT 1 |  | Unknown
6/5 | Kent Sheet 6 | CAT 2 |  | Unknown
6/6 | Kent Sheet 6 | CAT 2 |  | Unknown
6/6 | Kent Sheet 6 | CAT 1 |  | Unknown
7/13 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe Benhall Developments Limited Christine Elizabeth Dunn Christopher Gilbert Sneath Elizabeth Mary Sneath Eric Winston Woodbine Gary Mark Thompson Jacqueline Helen Thompson James Anthony Cox John Dunn Katarzyna Ewa Clark Keely Maria Holcombe Lorraine Cox Lorraine Ruth Kay Margaret Woodbine Richard Stuart Kay Zara Alice Smith Unknown
7/15 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe Benhall Developments Limited Christine Elizabeth Dunn Christopher Gilbert Sneath Elizabeth Mary Sneath Eric Winston Woodbine Gary Mark Thompson Jacqueline Helen Thompson James Anthony Cox John Dunn Katarzyna Ewa Clark Keely Maria Holcombe Lorraine Cox Lorraine Ruth Kay Margaret Woodbine Richard Stuart Kay Zara Alice Smith Unknown
7/16 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/17 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe Benhall Developments Limited Christine Elizabeth Dunn Christopher Gilbert Sneath Elizabeth Mary Sneath Eric Winston Woodbine Gary Mark Thompson Jacqueline Helen Thompson James Anthony Cox John Dunn Katarzyna Ewa Clark Keely Maria Holcombe Lorraine Cox Lorraine Ruth Kay Margaret Woodbine Richard Stuart Kay Zara Alice Smith Unknown
7/25 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/30 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/31 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/4 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe Benhall Developments Limited Christine Elizabeth Dunn Christopher Gilbert Sneath Elizabeth Mary Sneath Eric Winston Woodbine Gary Mark Thompson Jacqueline Helen Thompson James Anthony Cox John Dunn Katarzyna Ewa Clark Keely Maria Holcombe Lorraine Cox Lorraine Ruth Kay Margaret Woodbine Richard Stuart Kay Zara Alice Smith Unknown
4/12 | Suffolk Sheet 4 | CAT 2 |  | Joel Hopkins
1/76 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/77 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/78 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
`/79 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/80 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/81 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/82 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/83 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/84 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/85 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/92 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/93 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/94 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/95 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/99 | Suffolk Sheet 1 | CAT 2 |  | Amyas John Peto Anglian Water Services Limited Sophia Frances Peto
1/2 | Suffolk Sheet 1 | CAT 2 | Christopher Tullis Lucas
4/26 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/28 | Kent Sheet 4 | CAT 1 |  | Unknown
4/3 | Kent Sheet 4 | CAT 2 |  | Unknown
4/3 | Kent Sheet 4 | CAT 1 |  | Unknown
4/4 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/4 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/5 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/5 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/5 | Kent Sheet 4 | CAT 1 |  | Unknown
4/6 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/6 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/7 | Suffolk Sheet 4 | CAT 2 |  | Joel Hopkins
4/7 | Suffolk Sheet 4 | CAT 2 |  | Abigail Hopkins
4/7 | Suffolk Sheet 4 | CAT 2 |  | Sarah Younger
4/8 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/8 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/9 | Suffolk Sheet 4 | CAT 2 |  | Unknown
4/9 | Suffolk Sheet 4 | CAT 2 |  | Unknown
5/1 | Kent Sheet 5 | CAT 2 | The Marquess Conyngham
5/1 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/1 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/1 | Kent Sheet 5 | CAT 1 |  | Unknown
5/10 | Kent Sheet 5 | CAT 2 | Coal Authority
5/10 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority
5/10 | Kent Sheet 5 | CAT 2 |  | Unknown
5/10 | Kent Sheet 5 | CAT 2 |  | Unknown
5/10 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/10 | Kent Sheet 5 | CAT 1 |  | Unknown
5/11 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/12 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/12 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/12 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 2 | Coal Authority
5/13 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority
5/13 | Kent Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 2 |  | Unknown
5/13 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/13 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/13 | Kent Sheet 5 | CAT 1 |  | Unknown
5/15 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/16 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/16 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 2 | Coal Authority
5/18 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority
5/18 | Kent Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 2 |  | Unknown
5/18 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/18 | Kent Sheet 5 | CAT 1 |  | Unknown
5/19 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/2 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/2 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/2 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/20 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/20 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/21 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/21 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/21 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/21 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/22 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/22 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/22 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/23 | Suffolk Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/23 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/24 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/25 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/25 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/26 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/26 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/26 | Kent Sheet 5 | CAT 1 |  | Unknown
5/27 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/27 | Kent Sheet 5 | CAT 1 |  | Unknown
5/27 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/28 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/28 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/28 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/28 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/28 | Kent Sheet 5 | CAT 1 |  | Unknown
5/29 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/29 | Kent Sheet 5 | CAT 1 |  | Unknown
5/29 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/3 | Kent Sheet 5 | CAT 2 | Barclays Security Trustee Limited Kent County Council Nemo Link Limited Personal Representative to the Estate of Carolyn Joy Marshall Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham The Public Trustee Vattenfall Wind Power Limited
5/3 | Suffolk Sheet 5 | CAT 2 |  | Peter Henry Marshall
5/3 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/30 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/30 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/30 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/30 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/30 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/30a | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/30a | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/30a | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/31 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/31 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/31 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/31 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/31 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/32 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/32 | Suffolk Sheet 5 | CAT 1 |  | Unknown
5/33 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/33 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/33 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/34 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/34 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/34 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/34 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/34 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/34 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/34 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/34 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/34 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/35 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/35 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/35 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/35 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/36 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/36 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/36 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/36 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/37 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/37 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/37 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/37 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/37 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/37 | Kent Sheet 5 | CAT 1 |  | Unknown
5/38 | Kent Sheet 5 | CAT 2 |  | Mining Remediation Authority
5/38 | Kent Sheet 5 | CAT 2 |  | Pfizer Limited
5/38 | Kent Sheet 5 | CAT 2 |  | Unknown
5/38 | Kent Sheet 5 | CAT 2 |  | Unknown
5/38 | Kent Sheet 5 | CAT 1 |  | Unknown
5/39 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/39 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/39 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/39 | Kent Sheet 5 | CAT 2 |  | The Marquess Conyngham
5/4 | Kent Sheet 5 | CAT 2 | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited The Marquess Conyngham Vattenfall Wind Power Limited
5/4 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/40 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/40 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/40 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/40 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/40 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/40 | Kent Sheet 5 | CAT 1 |  | Unknown
5/41 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/41 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/41 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/41 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/41 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/41 | Kent Sheet 5 | CAT 1 |  | Unknown
5/42 | Kent Sheet 5 | CAT 2 |  | Kent County Council Nemo Link Limited Thanet District Council Thanet Offshore Wind Limited Vattenfall Wind Power Limited
5/42 | Kent Sheet 5 | CAT 1 |  | Unknown
5/43 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/43 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/43 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/43 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/43 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/43 | Kent Sheet 5 | CAT 1 |  | Unknown
5/44 | Kent Sheet 5 | CAT 2 |  | Kent County Council
5/44 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/44 | Kent Sheet 5 | CAT 2 |  | Thanet District Council
5/44 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/44 | Kent Sheet 5 | CAT 2 |  | Vattenfall Wind Power Limited
5/44 | Kent Sheet 5 | CAT 1 |  | Unknown
5/45 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/45 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/45 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/46 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/46 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/46 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/47 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/47 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/47 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/48 | Kent Sheet 5 | CAT 2 |  | Nemo Link Limited
5/48 | Kent Sheet 5 | CAT 2 |  | Thanet OFTO Limited
5/48 | Kent Sheet 5 | CAT 2 |  | Thanet Offshore Wind Limited
5/5 | Kent Sheet 5 | CAT 2 | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/5 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/5 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/5 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/6 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/7 | Kent Sheet 5 | CAT 2 | Nemo Link Limited Thanet OFTO Limited Thanet Offshore Wind Limited The Marquess Conyngham
5/7 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/8 | Kent Sheet 5 | CAT 2 | The Marquess Conyngham
5/8 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/9 | Suffolk Sheet 5 | CAT 2 |  | Unknown
5/9 | Kent Sheet 5 | CAT 1 |  | Unknown
6/1 | Kent Sheet 6 | CAT 2 |  | Unknown
6/1 | Suffolk Sheet 6 | CAT 2 |  | Unknown
6/1 | Suffolk Sheet 6 | CAT 2 |  | Unknown
6/1 | Suffolk Sheet 6 | CAT 2 |  | Unknown
6/2 | Kent Sheet 6 | CAT 2 |  | Unknown
6/3 | Kent Sheet 6 | CAT 2 |  | Unknown
6/4 | Kent Sheet 6 | CAT 2 |  | Unknown
6/4 | Kent Sheet 6 | CAT 2 |  | Unknown
6/4 | Kent Sheet 6 | CAT 1 |  | Unknown
6/5 | Kent Sheet 6 | CAT 2 |  | Unknown
6/5 | Kent Sheet 6 | CAT 2 |  | Unknown
6/6 | Kent Sheet 6 | CAT 2 |  | Unknown
6/6 | Kent Sheet 6 | CAT 1 |  | Unknown
7/13 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe
7/13 | Suffolk Sheet 7 | CAT 2 |  | Benhall Developments Limited
7/13 | Suffolk Sheet 7 | CAT 2 |  | Christine Elizabeth Dunn
7/13 | Suffolk Sheet 7 | CAT 2 |  | Christopher Gilbert Sneath
7/13 | Suffolk Sheet 7 | CAT 2 |  | Elizabeth Mary Sneath
7/13 | Suffolk Sheet 7 | CAT 2 |  | Eric Winston Woodbine
7/13 | Suffolk Sheet 7 | CAT 2 |  | Gary Mark Thompson
7/13 | Suffolk Sheet 7 | CAT 2 |  | Jacqueline Helen Thompson
7/13 | Suffolk Sheet 7 | CAT 2 |  | James Anthony Cox
7/13 | Suffolk Sheet 7 | CAT 2 |  | John Dunn
7/13 | Suffolk Sheet 7 | CAT 2 |  | Katarzyna Ewa Clark
7/13 | Suffolk Sheet 7 | CAT 2 |  | Keely Maria Holcombe
7/13 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Cox
7/13 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Ruth Kay
7/13 | Suffolk Sheet 7 | CAT 2 |  | Margaret Woodbine
7/13 | Suffolk Sheet 7 | CAT 2 |  | Richard Stuart Kay
7/13 | Suffolk Sheet 7 | CAT 2 |  | Zara Alice Smith
7/13 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/13 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/15 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe
7/15 | Suffolk Sheet 7 | CAT 2 |  | Benhall Developments Limited
7/15 | Suffolk Sheet 7 | CAT 2 |  | Christine Elizabeth Dunn
7/15 | Suffolk Sheet 7 | CAT 2 |  | Christopher Gilbert Sneath
7/15 | Suffolk Sheet 7 | CAT 2 |  | Elizabeth Mary Sneath
7/15 | Suffolk Sheet 7 | CAT 2 |  | Eric Winston Woodbine
7/15 | Suffolk Sheet 7 | CAT 2 |  | Gary Mark Thompson
7/15 | Suffolk Sheet 7 | CAT 2 |  | Jacqueline Helen Thompson
7/15 | Suffolk Sheet 7 | CAT 2 |  | James Anthony Cox
7/15 | Suffolk Sheet 7 | CAT 2 |  | John Dunn
7/15 | Suffolk Sheet 7 | CAT 2 |  | Katarzyna Ewa Clark
7/15 | Suffolk Sheet 7 | CAT 2 |  | Keely Maria Holcombe
7/15 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Cox
7/15 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Ruth Kay
7/15 | Suffolk Sheet 7 | CAT 2 |  | Margaret Woodbine
7/15 | Suffolk Sheet 7 | CAT 2 |  | Richard Stuart Kay
7/15 | Suffolk Sheet 7 | CAT 2 |  | Zara Alice Smith
7/15 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/15 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/16 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/17 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe
7/17 | Suffolk Sheet 7 | CAT 2 |  | Benhall Developments Limited
7/17 | Suffolk Sheet 7 | CAT 2 |  | Christine Elizabeth Dunn
7/17 | Suffolk Sheet 7 | CAT 2 |  | Christopher Gilbert Sneath
7/17 | Suffolk Sheet 7 | CAT 2 |  | Elizabeth Mary Sneath
7/17 | Suffolk Sheet 7 | CAT 2 |  | Eric Winston Woodbine
7/17 | Suffolk Sheet 7 | CAT 2 |  | Gary Mark Thompson
7/17 | Suffolk Sheet 7 | CAT 2 |  | Jacqueline Helen Thompson
7/17 | Suffolk Sheet 7 | CAT 2 |  | James Anthony Cox
7/17 | Suffolk Sheet 7 | CAT 2 |  | John Dunn
7/17 | Suffolk Sheet 7 | CAT 2 |  | Katarzyna Ewa Clark
7/17 | Suffolk Sheet 7 | CAT 2 |  | Keely Maria Holcombe
7/17 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Cox
7/17 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Ruth Kay
7/17 | Suffolk Sheet 7 | CAT 2 |  | Margaret Woodbine
7/17 | Suffolk Sheet 7 | CAT 2 |  | Richard Stuart Kay
7/17 | Suffolk Sheet 7 | CAT 2 |  | Zara Alice Smith
7/17 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/17 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/25 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/30 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/31 | Suffolk Sheet 7 | CAT 2 |  | Unknown
7/4 | Suffolk Sheet 7 | CAT 2 |  | Adam Peter Holcombe
7/4 | Suffolk Sheet 7 | CAT 2 |  | Christine Elizabeth Dunn
7/4 | Suffolk Sheet 7 | CAT 2 |  | Christopher Gilbert Sneath
7/4 | Suffolk Sheet 7 | CAT 2 |  | Elizabeth Mary Sneath
7/4 | Suffolk Sheet 7 | CAT 2 |  | Eric Winston Woodbine
7/4 | Suffolk Sheet 7 | CAT 2 |  | Flagship Housing Limited
7/4 | Suffolk Sheet 7 | CAT 2 |  | Gary Mark Thompson
7/4 | Suffolk Sheet 7 | CAT 2 |  | Ian Charles Rix
7/4 | Suffolk Sheet 7 | CAT 2 |  | Jacqueline Helen Thompson
7/4 | Suffolk Sheet 7 | CAT 2 |  | James Anthony Cox
7/4 | Suffolk Sheet 7 | CAT 2 |  | John Dunn
7/4 | Suffolk Sheet 7 | CAT 2 |  | Katarzyna Ewa Clark
7/4 | Suffolk Sheet 7 | CAT 2 |  | Keely Maria Holcombe
7/4 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Cox
7/4 | Suffolk Sheet 7 | CAT 2 |  | Lorraine Ruth Kay
7/4 | Suffolk Sheet 7 | CAT 2 |  | Margaret Woodbine
7/4 | Suffolk Sheet 7 | CAT 2 |  | Richard Stuart Kay
7/4 | Suffolk Sheet 7 | CAT 2 |  | Zara Alice Smith
7/4 | Suffolk Sheet 7 | CAT 2 |  | Unknown
6/3 | Suffolk Sheet 6 | CAT 1 |  | Northumbrian Water Limited (628)
7/7 | Suffolk Sheet 6 | CAT 1 | The King`s Most Excellent Majesty in Right of His Crown (458)
5/17 | Suffolk Sheet 5 | CAT 1 |  | Northumbrian Water Limited (628)
5/19 | Suffolk Sheet 5 | CAT 1 |  | Northumbrian Water Limited (628)
5/40 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/19,
1/2 | Kent Sheet 1 | CAT 1 | Clive Robert Stevens (2520), Christopher Russell John Domvile Barradale (2521) | Andrew William Johnson (3566)
2/36 | Kent Sheet 2 | CAT 1 | N/A | UK Power Networks Services (South East) Limited (1009)
2/39 | Kent Sheet 2 | CAT 1 | N/A | UK Power Networks Services (South East) Limited (1009)
2/40 | Kent Sheet 2 | CAT 1 | N/A | UK Power Networks Services (South East) Limited (1009)
2/41 | Kent Sheet 2 | CAT 1 | N/A | UK Power Networks Services (South East) Limited (1009)
2/42 | Kent Sheet 2 | CAT 1 | N/A | UK Power Networks Services (South East) Limited (1009)
3/66 | Kent Sheet 3 | CAT 1 | Southern Water Services Limited (411) | N/A
3/67 | Kent Sheet 3 | CAT 1 | N/A | N/A | plots have been Renumbered to 3/100
3/97 | Kent Sheet 3 | CAT 1 | N/A | Thanet District Council (167)
5/25 | Kent Sheet 5 | CAT 1 |  |  | Thanet District Council / Thanet OFTO Limited Description of land and rights requested changed from '65102 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent Class 3. Compulsory Acquisition of Rights - Underground Cable System' to '71,196 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent Class 3. Compulsory Acquisition of Rights - Underground Cable System'
3/100 |  |  |  |  | plots were previously 3/67
3/101 | Kent Sheet 3 | CAT 1 | Kent County Council (97) |  | plots were previously 3/68, some parties have been removed
3/102 | Kent Sheet 3 | CAT 1 | Kent County Council (97) |  | plots were previously 3/68a some parties have been removed
3/104 | Kent Sheet 3 | CAT 1 | Kent County Council (97) |  | plots were previously 3/68c some parties have been removed
3/68b | Kent Sheet 3 | CAT 1 | Kent County Council (97)
3/68d | Kent Sheet 3 | CAT 1 | Kent County Council (97)
3/107 | Kent Sheet 3 | CAT 1 | Kent County Council (97) |  | plots were previously 3/70 some parties have been removed
3/108 | Kent Sheet 3 | CAT 1 |  |  | plots were previously 3/71
3/109 | Kent Sheet 3 | CAT 1 |  |  | plots were previously 3/72
3/110 | Kent Sheet 3 | CAT 1 |  |  | plots were previously 3/73
3/112 | Kent Sheet 3 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
3/111 | Kent Sheet 3 | CAT 1 |  | Thanet OFTO Limited (152), UK Power Networks Services (South East) Limited (1009), Openreach Limited (3287) | new plot
3/97a | Kent Sheet 3 | CAT 1 |  | Kent County Council (97) , Thanet OFTO Limited (152), UK Power Networks Services (South East) Limited (1009), Openreach Limited (3287), Southern Water Services Limited (411) | new plot
3/99 | Kent Sheet 3 | CAT 1 |  | St. Augustine`s Golf Club (Ramsgate) Limited (553), Timothy John Deakin (313), Christopher Thomas (559), Gary Snell (642), The River Stour (Kent) Internal Drainage Board (1934), Southern Water Services Limited (411) | new plot
5/10 | Kent Sheet 5 | CAT 1 | Kent Wildlife Trust (498) - Occupation interest removed
5/27 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/2,
5/26 | Kent Sheet 5 | CAT 1
5/41 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/20
5/42 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/21
5/43 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/22
5/44 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/23
5/28 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/3, also class has changed to Class 8
5/29 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/4, area size has decreased to 2,065
5/30 | Kent Sheet 5 | CAT 1 |  |  | plots were previously 5/5
5/6 | Kent Sheet 5 | CAT 1 |  |  | Description of land and rights requested changed from '567816 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
5/26 | Kent Sheet 5 | CAT 1 |  |  | new plot
5/8 | Kent Sheet 5 | CAT 1 |  |  | Description of land and rights requested changed from '18138 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent. Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
5/9 | Kent Sheet 5 | CAT 1 |  |  | Description of land and rights requested changed from '4976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' to '3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
5/24 | Kent Sheet 5 | CAT 1 | Thanet District Council (167), Thanet OFTO Limited (152)
5/7 | Kent Sheet 5 | CAT 1 | Thanet District Council (167), Thanet OFTO Limited (152)
5/31 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/33 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/34 | Kent Sheet 5 | CAT 1 |  | The National Trust for Places of Historic Interest or Natural Beauty (237), Kent Wildlife Trust (498), National Grid Ventures Limited (3292) | new plot
5/35 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/36 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/37 | Kent Sheet 5 | CAT 1 |  | The National Trust for Places of Historic Interest or Natural Beauty (237), Kent Wildlife Trust (498) | new plot
5/38 | Kent Sheet 5 | CAT 1 |  | Kent Wildlife Trust (498) | new plot
5/39 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152), National Grid Ventures Limited (3292) | new plot
5/45 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/46 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/47 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/48 | Kent Sheet 5 | CAT 1 |  | Thanet District Council (167), Thanet OFTO Limited (152) | new plot
5/14 | Suffolk Sheet 5 | CAT 1 |  | Northumbrian Water Limited (628)
4/7 | Suffolk Sheet 4 | CAT 1 | Openreach Limited (3287) |  | Description of land and rights requested changed from '269479 square metres, or thereabouts, of grass land, scrubland, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Ash Covert, Suffolk Class 7. Compulsory Acquisition of Rights - Mitigation' to '62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation'
1/100 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/100 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/100 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/100 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/13 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/16 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/17 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/31 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/32 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/45 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/49a | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/49a | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/49a | Suffolk Sheet 1 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Cripps Trust Corporation Limited Freehold (as trustee to The Dowley Family Discretionary Settlement 2018)
1/74 | Suffolk Sheet 1 | CAT 1 |  | Emma Louise Dowley Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Laurence Justin Dowley Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/74 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/74 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/74 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/75 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/75 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/75 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/75 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/75 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/75 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/76 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/76 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/76 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/77 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/77 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Occupation
1/77 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/77 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/77 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Occupation
1/77 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/78 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/78 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Occupation
1/78 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/78 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/78 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Occupation
1/78 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/79 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Freehold
1/79 | Suffolk Sheet 1 | CAT 1 |  | Caroline Nichol Occupation
1/79 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Freehold
1/79 | Suffolk Sheet 1 | CAT 1 |  | Gerlinde Edmunds Occupation
1/80 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/80 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Occupation
1/81 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/81 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/81 | Suffolk Sheet 1 | CAT 1 |  | Openreach Limited Occupation
1/81 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/81 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Occupation
1/82 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/82 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Occupation
1/83 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/83 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Occupation
1/84 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/84 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Occupation
1/85 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/85 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Occupation
1/85 | Suffolk Sheet 1 | CAT 1 |  | Nathaniel Bacon Occupation
1/85 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/86 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/86 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/86 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Occupation
1/86 | Suffolk Sheet 1 | CAT 1 |  | Nathaniel Bacon Occupation
1/86 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/86 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/87 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/87 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/87 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Occupation
1/87 | Suffolk Sheet 1 | CAT 1 |  | Nathaniel Bacon Occupation
1/87 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/87 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/88 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/88 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/88 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/88 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/88 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/89 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/89 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/89 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/89 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/90 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/90 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/90 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Occupation
1/90 | Suffolk Sheet 1 | CAT 1 |  | Nathaniel Bacon Occupation
1/90 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/90 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/91 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/91 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/91 | Suffolk Sheet 1 | CAT 1 |  | James John Skellorn Freehold
1/91 | Suffolk Sheet 1 | CAT 1 |  | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/91 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/91 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/92 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/92 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/92 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/92 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/93 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/93 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/93 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/93 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/94 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/94 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/94 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/94 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/95 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/95 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/95 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/95 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/96 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/96 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/96 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/96 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/97 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/97 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/97 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/98 | Suffolk Sheet 1 | CAT 1 |  | Cadent Gas Limited Occupation
1/98 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/98 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/98 | Suffolk Sheet 1 | CAT 1 |  | Jane Ruth Van Lennep Freehold
1/98 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
1/98 | Suffolk Sheet 1 | CAT 1 |  | Robert Roy Jonas Nichol Freehold
1/98 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
1/98 | Suffolk Sheet 1 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
1/99 | Suffolk Sheet 1 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
1/99 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Freehold
1/99 | Suffolk Sheet 1 | CAT 1 |  | Ian Charles Rix Occupation
1/99 | Suffolk Sheet 1 | CAT 1 |  | Northumbrian Water Limited Occupation
2/100 | Suffolk Sheet 2 | CAT 1 |  | Essex and Suffolk Water Limited Occupation
2/100 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/100 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/100 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/100 | Suffolk Sheet 2 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
2/100 | Suffolk Sheet 2 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
2/100 | Suffolk Sheet 2 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
2/101 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/101 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/101 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/101 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/102 | Suffolk Sheet 2 | CAT 1 |  | Peter Murray Mann Freehold
2/102 | Suffolk Sheet 2 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
2/103 | Suffolk Sheet 2 | CAT 1 |  | Peter Murray Mann Freehold
2/103 | Suffolk Sheet 2 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
2/104 | Suffolk Sheet 2 | CAT 1 |  | Peter Murray Mann Freehold
2/104 | Suffolk Sheet 2 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
2/105 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/105 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/105 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/105 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/107 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/107 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/107 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/107 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/108 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/108 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/108 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/108 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/109 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/109 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/109 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/109 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/110 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/110 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/110 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/110 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/111 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/111 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/111 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/111 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/112 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
2/112 | Suffolk Sheet 2 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
2/112 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
2/112 | Suffolk Sheet 2 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
2/12 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/13 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/15 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner of part)
2/15 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/20 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/20 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/20a | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Blackheath Farms Limited Freehold
2/22a | Suffolk Sheet 2 | CAT 1 |  | Blackheath Farms Limited Occupation
2/22a | Suffolk Sheet 2 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Langley Dairies Limited Occupation
2/22a | Suffolk Sheet 2 | CAT 1 |  | National Grid Electricity Transmission plc Occupation
2/22a | Suffolk Sheet 2 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Sovereign Turf Limited Occupation
2/22a | Suffolk Sheet 2 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
2/22a | Suffolk Sheet 2 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
2/22a | Suffolk Sheet 2 | CAT 1 |  | West Country Trees Limited Occupation
2/35 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/36 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner of part)
2/40 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/42 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner of part)
2/43 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/46 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner of part)
2/47 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner of part)
2/49 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/5 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/52 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/55 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/55 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/57 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/57 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/58 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/58 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/59 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/59 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/6 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/60 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/61 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/61 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/63 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/64 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/65 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/65 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/66 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/68 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/69 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/7 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/70 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/71 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/72 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/77 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
2/77 | Suffolk Sheet 2 | CAT 1 |  | Pauline Violet Ellis Freehold
2/78 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold
2/78a | Suffolk Sheet 2 | CAT 1 |  | Ernest Alexander Tait Wright Freehold
2/78a | Suffolk Sheet 2 | CAT 1 |  | Ernest Alexander Tait Wright Occupation
2/78b | Suffolk Sheet 2 | CAT 1 |  | Ernest Alexander Tait Wright Freehold
2/78b | Suffolk Sheet 2 | CAT 1 |  | Ernest Alexander Tait Wright Occupation
2/79a | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold
2/8 | Suffolk Sheet 2 | CAT 1 |  | ScottishPower (UK) Renewables Limited Freehold (as reputed owner)
2/84 | Suffolk Sheet 2 | CAT 1 |  | Northumbrian Water Limited Occupation
3/18 | Suffolk Sheet 3 | CAT 1 |  | National Grid Electricity Transmission plc Occupation
3/41 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Freehold
3/41 | Suffolk Sheet 3 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
3/42 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Freehold
3/43 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
3/43 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
3/43 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
3/43 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
3/44 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
3/44 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
3/44 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
3/44 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
3/45 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/45 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/45 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/45 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/45 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/45 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/46 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/46 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/46 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/46 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/46 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/46 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/47 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/47 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/47 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/47 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/47 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/47 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/48 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
3/48 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
3/48 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
3/48 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
3/49 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/49 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/49 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/49 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/49 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/49 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/50 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
3/50 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
3/50 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
3/50 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
3/51 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/51 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/51 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/51 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/51 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/51 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/52 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Freehold
3/52 | Suffolk Sheet 3 | CAT 1 |  | Lucinda Jane Fullerton Heald Occupation
3/52 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Freehold
3/52 | Suffolk Sheet 3 | CAT 1 |  | Michael Guy Hilliard Heald Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/53 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/53 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/53 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/54 | Suffolk Sheet 3 | CAT 1 |  | June Bloomfield Freehold
3/54 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/54 | Suffolk Sheet 3 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/55 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/55 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/55 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/56 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/56 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/56 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/57 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/57 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/57 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/57 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/57 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/57 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/57 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/58 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/58 | Suffolk Sheet 3 | CAT 1 |  | Connie Amber Peck Freehold
3/58 | Suffolk Sheet 3 | CAT 1 |  | George William Barrington-Phillips Freehold
3/58 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/58 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/58 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
3/58 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/59 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/59 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/59 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/59 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/59 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/60 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/60 | Suffolk Sheet 3 | CAT 1 |  | EXA Networks Limited Occupation
3/60 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/60 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/60 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
3/60 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
3/61 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/61 | Suffolk Sheet 3 | CAT 1 |  | EXA Networks Limited Occupation
3/61 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/61 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/61 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
3/61 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
3/62 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/62 | Suffolk Sheet 3 | CAT 1 |  | June Bloomfield Freehold
3/62 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/62 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/62 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
3/62 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
3/62 | Suffolk Sheet 3 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/63 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Leasehold (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | Christopher Mann Occupation (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | EXA Networks Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | Langley Dairies Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Leasehold (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | Richard William Mann Occupation (trading as Mann Potatoes)
3/63 | Suffolk Sheet 3 | CAT 1 |  | Sovereign Turf Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
3/63 | Suffolk Sheet 3 | CAT 1 |  | West Country Trees Limited Occupation
3/64 | Suffolk Sheet 3 | CAT 1 |  | Blackheath Farms Limited Freehold
3/64 | Suffolk Sheet 3 | CAT 1 |  | EXA Networks Limited Occupation
3/64 | Suffolk Sheet 3 | CAT 1 |  | June Bloomfield Freehold
3/64 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/64 | Suffolk Sheet 3 | CAT 1 |  | Openreach Limited Occupation
3/64 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Freehold (as highway authority)
3/64 | Suffolk Sheet 3 | CAT 1 |  | Suffolk County Council Occupation (as highway authority)
3/64 | Suffolk Sheet 3 | CAT 1 |  | UK Power Networks Services (South East) Limited Occupation
1/12 | Suffolk Sheet 1 | CAT 1 | Caroline Nichol Freehold
1/12 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/12 | Suffolk Sheet 1 | CAT 1 | Gerlinde Edmunds Freehold
1/15 | Suffolk Sheet 1 | CAT 1 | Caroline Nichol Freehold
1/15 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/15 | Suffolk Sheet 1 | CAT 1 | Gerlinde Edmunds Occupation
1/15 | Suffolk Sheet 1 | CAT 1 | Openreach Limited Occupation
1/15 | Suffolk Sheet 1 | CAT 1 | Openreach Limited Occupation
1/32 | Suffolk Sheet 1 | CAT 1 | Openreach Limited Occupation
1/47 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/49 | Suffolk Sheet 1 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
1/54 | Suffolk Sheet 1 | CAT 1 | Cadent Gas Limited Occupation
1/54 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/54 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Freehold (as highway authority)
1/54 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Occupation (as highway authority)
1/55 | Suffolk Sheet 1 | CAT 1 | Robert Roy Jonas Nichol Freehold
1/55 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Freehold (as highway authority)
1/55 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Occupation (as highway authority)
1/60 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/61 | Suffolk Sheet 1 | CAT 1 | Cadent Gas Limited Occupation
1/61 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/61 | Suffolk Sheet 1 | CAT 1 | James John Skellorn Freehold
1/61 | Suffolk Sheet 1 | CAT 1 | Personal Representative to the Estate of Margaret Anne Bacon Freehold
1/61 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Freehold (as highway authority)
1/61 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Occupation (as highway authority)
1/62 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/62 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/62 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Occupation
1/63 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/63 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/63 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Occupation
1/64 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/65 | Suffolk Sheet 1 | CAT 1 | Cadent Gas Limited Occupation
1/65 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/65 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Freehold (as highway authority)
1/65 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Occupation (as highway authority)
1/66 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/66 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/66 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Occupation
1/68 | Suffolk Sheet 1 | CAT 1 | Cadent Gas Limited Occupation
1/68 | Suffolk Sheet 1 | CAT 1 | Essex and Suffolk Water Limited Occupation
1/68 | Suffolk Sheet 1 | CAT 1 | Ian Charles Rix Freehold
1/68 | Suffolk Sheet 1 | CAT 1 | Jane Ruth Van Lennep Freehold
1/68 | Suffolk Sheet 1 | CAT 1 | Robert Roy Jonas Nichol Freehold
1/68 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Freehold (as highway authority)
1/68 | Suffolk Sheet 1 | CAT 1 | Suffolk County Council Occupation (as highway authority)
2/11 | Suffolk Sheet 2 | CAT 1 | Ian Charles Rix Freehold
2/11 | Suffolk Sheet 2 | CAT 1 | Ian Charles Rix Freehold
2/20a | Suffolk Sheet 2 | CAT 1 | Peter Murray Mann Freehold
2/22 | Suffolk Sheet 2 | CAT 1 | National Grid Electricity Transmission plc Occupation
2/55 | Suffolk Sheet 2 | CAT 1 | Peter Murray Mann Freehold
2/78 | Suffolk Sheet 2 | CAT 1 | Ernest Alexander Tait Wright Freehold
2/78 | Suffolk Sheet 2 | CAT 1 | Ernest Alexander Tait Wright Occupation
2/86 | Suffolk Sheet 2 | CAT 1 | Essex and Suffolk Water Limited Occupation
2/86 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/86 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/86 | Suffolk Sheet 2 | CAT 1 | Suffolk County Council Freehold (as highway authority)
2/86 | Suffolk Sheet 2 | CAT 1 | Suffolk County Council Occupation (as highway authority)
2/86 | Suffolk Sheet 2 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
2/87 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/87 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/87 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/87 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/88 | Suffolk Sheet 2 | CAT 1 | Peter Murray Mann Freehold
2/88 | Suffolk Sheet 2 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
2/89 | Suffolk Sheet 2 | CAT 1 | Peter Murray Mann Freehold
2/89 | Suffolk Sheet 2 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
2/90 | Suffolk Sheet 2 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
2/91 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/91 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/91 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/91 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/92 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/92 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/92 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/92 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/93 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/93 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/93 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/93 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/94 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/94 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/94 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/94 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/95 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/95 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/95 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/95 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
2/96 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
2/96 | Suffolk Sheet 2 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
2/96 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Freehold
2/96 | Suffolk Sheet 2 | CAT 1 | Michael Guy Hilliard Heald Occupation
3/1 | Suffolk Sheet 3 | CAT 1 | Hilda Mary Chaston Freehold
3/17 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Freehold
3/24 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
3/24 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
3/24 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Freehold
3/24 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/35 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/35 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/26 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/26 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/26 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/26 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/26 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/26 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/27 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
3/27 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
3/27 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Freehold
3/27 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Occupation
3/28 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
3/28 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
3/28 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Freehold
3/28 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Occupation
3/29 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/29 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/29 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/29 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/29 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/29 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/30 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Freehold
3/30 | Suffolk Sheet 3 | CAT 1 | Lucinda Jane Fullerton Heald Occupation
3/30 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Freehold
3/30 | Suffolk Sheet 3 | CAT 1 | Michael Guy Hilliard Heald Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/31 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/31 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/31 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/32 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/32 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/32 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/33 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Leasehold (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Christopher Mann Occupation (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Langley Dairies Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Leasehold (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Peter Murray Mann Occupation (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Leasehold (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Richard William Mann Occupation (trading as Mann Potatoes)
3/33 | Suffolk Sheet 3 | CAT 1 | Sovereign Turf Limited Occupation
3/33 | Suffolk Sheet 3 | CAT 1 | West Country Trees Limited Occupation
3/34 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold
3/34 | Suffolk Sheet 3 | CAT 1 | EXA Networks Limited Occupation
3/34 | Suffolk Sheet 3 | CAT 1 | June Bloomfield Freehold
3/34 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/34 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/34 | Suffolk Sheet 3 | CAT 1 | Suffolk County Council Freehold (as highway authority)
3/34 | Suffolk Sheet 3 | CAT 1 | Suffolk County Council Occupation (as highway authority)
3/34 | Suffolk Sheet 3 | CAT 1 | UK Power Networks Services (South East) Limited Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/35 | Suffolk Sheet 3 | CAT 1 | Openreach Limited Occupation
3/36 | Suffolk Sheet 3 | CAT 1 | Blackheath Farms Limited Freehold Blackheath Farms Limited Occupation Christopher Mann Leasehold (trading as Mann Potatoes) Christopher Mann Occupation (trading as Mann Potatoes) Langley Dairies Limited Occupation Peter Murray Mann Leasehold (trading as Mann Potatoes) Peter Murray Mann Occupation (trading as Mann Potatoes) Richard William Mann Leasehold (trading as Mann Potatoes) Richard William Mann Occupation (trading as Mann Potatoes) Sovereign Turf Limited Occupation West Country Trees Limited Occupation
3/37 | Suffolk Sheet 3 | CAT 1 | Connie Amber Peck Freehold George William Barrington-Phillips Freehold Openreach Limited Occupation
1/1 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '9743 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' '2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/12 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '9743 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' '2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/14 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '229 square metres, or thereabouts, of public footpath (023) and overhead telecommunication lines situated to the south of The Manor House, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' '9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/17 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '26244 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' '25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/31 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '19733 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage' '19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage'
1/32 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '3405 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk Class 7. Compulsory Acquisition of Rights - Mitigation' '673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation'
1/33 | Suffolk Sheet 1 | CAT 1 |  |  | Description of land and rights requested: '70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure' '81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure'
1/1 | Offshore Sheet 1 | CAT 1 | The King`s Most Excellent Majesty in Right of His Crown Freehold
1/1 | Offshore Sheet 1 | CAT 1 | The King`s Most Excellent Majesty in Right of His Crown Occupation
2/1 | Offshore Sheet 2 | CAT 1 | The King`s Most Excellent Majesty in Right of His Crown Freehold
3/1 | Offshore Sheet 3 | CAT 1 | The King`s Most Excellent Majesty in Right of His Crown Freehold
3/1 | Offshore Sheet 3 | CAT 1 | Kent Wildlife Trust Freehold
3/1 | Offshore Sheet 3 | CAT 1 | Kent Wildlife Trust Occupation

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown Land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO
| Open space | SU kit and apparatus | No agreement on final version
| National Trust and Open Space | SU rights in land
Crown Land and Marquess Conyngham (reputed ownership)
Open Space and Crown Land
Other