2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of a lease for construction consolidation as contained in an Option Agreement dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK257795 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement for the grant of easements dated 16 March 2023 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Reginald Anthony Wainwright | 303 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edmund Michael Wood | 451 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lady Patricia Ann Hopkins | 533 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lady Patricia Ann Hopkins | 533 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sir Michael John Hopkins | 556 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Joel Hopkins | 2746 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Abigail Hopkins | 2747 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | Yes | RR-0010 | [10 empty] | No Heads of Terms Required |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Younger | 2748 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pamela Tile | 1205 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Easement Right or Privilege | Rights relating to electric lines and works as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | SK232978 | Restrictive Covenant | Restrictive covenant not to interfere with the electric lines or foundations as contained in a Deed dated 16 August 2002 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK198325,SK232978 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Easement Right or Privilege | Rights to connect to and receive a supply of water from a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK232978,SK346948 | Restrictive Covenant | Covenant to maintain a water pipe as contained in a Deed dated 27 May 1987 for the benefit of adjoining land |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-3978 | [6 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Anglian Water Services Limited | 82 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU rights in land |  |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Easement Right or Privilege | Rights of way and rights relating to the passage of water and soil as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Jill Gooch | 185 | SK114061,SK258213 | Restrictive Covenant | Restrictive covenants relating to erect or build on the land as contained in a Conveyance dated 20 January 1992 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU rights in land | Bespoke PPs |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Thomas William Riddell-Webster | 1666 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | SK363555 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 | SK363555 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate without a certificate signed by ScottishPower (UK) Renewables Limited or its conveyancers that the provisions of clause 8.4 of an Agreement dated 2 March 2022 have been com |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Restrictive Covenant | Restrictive covenants relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Mark Cosgrove | 79 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Zoe Est Cosgrove | 574 | SK187280,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK151617 | Easement Right or Privilege | Unilateral notice in respect of Option Agreement dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK151617 | Easement Right or Privilege | Unilateral notice in respect of Option Agreement dated 21 December 2022 |  | Category 2 | No Agent Known | Yes | REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown Land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO
| Open space | SU kit and apparatus | No agreement on final version
| National Trust and Open Space | SU rights in land
Crown Land and Marquess Conyngham (reputed ownership)
Open Space and Crown Land
Other