## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 4 Submission.
For:
The construction and operation of Sea Link Energy Cable.
Planning Inspectorate Reference ENO20026
11th February 2026

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Sea Link examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - Suffolk Onshore B - Kent Onshore C- Development Consents Order D - Physical Environment E - Benthic Ecology F - Marine Mammals G - Marine Ornithology H - Sufolk and Essex Coast & Heaths DL The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG rating | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 4a | Consultation, actions, progression | RAG Deadline 4b | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
Suffolk Onshore
NE1 | The HDD landfall works have not been sufficiently considered. | For the Suffolk landfall location, Natural England is concerned that: - no detailed botanical surveys have been carried out at Leiston-Aldeburgh SSSI, - the impact on protected coastal habitats should be assessed, - the effects of dewatering to the Leiston-Aldeburgh SSSI have not been fully considered, - further Ground Investigation surveys may be required, and - further clarifications are needed on the proposed measures to minimise potential frac-outs. | For the Suffolk landfall location, Natural England advises that further information is required to inform a Horizontal Directional Drilling (HDD) management plan | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3.
NE2 | Insufficient information to determine the extent of loss of land. | Natural England is concerned that there is insufficient information to determine the extent of loss of Best and Most Versatile land. | Natural England advises that further assessment work is provided to inform a robust soil management plan, which should be submitted into examination. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3.
NE3 | No letters of no impediment for bats | Natural England has not reviewed any draft licence documents for this project. The Applicant has not sought any Letters Of No Impediment from Natural England for bats. | We advise that the Applicant contacts Natural England’s licensing service | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3.
Kent Onshore
NE4 | Feasibility of Horizontal Directional Drilling (HDD). | Natural England is concerned that the Applicant has not considered all potential impacts to designated sites as a result of HDD installation, including impacts to designated saltmarsh habitats and hydrology. The access route used by contractors to facilitate HDD installation remains unclear. | Further assessment would be required post-consent to determine the viability of HDD installation. Relevant documents should also be updated to include commitment to access routes and to provide a full consideration of the hydrological impacts of HDD. | Uncertain |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, please see Appendix J3a [REP3A-028] to our Deadline 3a submissions |  | No change, please see Appendix J4 to our Deadline 4 submission
NE5 | In-combination assessment of Air Quality impacts. | Natural England advises that in combination impacts need to be considered within the DCO if in combination impacts are likely. It is not clear from the information provided if this is the case. | Natural England advises that I in order to provide clarity to the ExA regarding potential air quality impact pathways on designated site the applicant provides updated information on impacts and on the use of Non-Road Mobile Machinery. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change.
NE6 | Impacts to breeding bird assemblages | Natural England has outstanding concerns on impacts to breeding bird assemblages in Sandwich Bay to Hacklinge Marshes SSSI. | We recommend the implementation of a seasonal restriction on works likely to cause disturbance to breeding bird assemblages for which the site is designated. These measures should be secured within the REAC. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadlines 2 and 3.
NE28 | Release of contaminants and debris from degraded hover pad | Natural England has become aware of evidence relating to the potential release of contaminants and debris from further degradation of the hover pad. If this is the case then we would advise against the use of the hoverpad | We advise that further clarification and assessment of this issue is required. | It is possible this issue could be progressed with further provision of information. |  | New Issue |  | New Issue |  | New Issue |  | New issue raised at Deadline 4
Draft Development Consent Order
NE7 | The definition of commence within the draft consent. | The definition of commence within both the Development Consent Order (DCO) and Deemed Marine Licence (dML) allow for damaging works to be conducted prior to agreement on the pre commencement mitigation documents. | The definition should be updated. | It is possible this issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Partially resolved. A query remains on pre-lay grapnel runs. |  | No change.
NE8 | Arbitration | Article 62 includes that decisions made by the Secretary of State, Trinity House and the MMO may be subject to arbitration. The Secretary of State has determined on several occasions this was not appropriate. | The arbitration article should be appropriately updated. | It is possible this issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Resolved. The wording has been appropriately updated.
NE9 | Lack of monitoring requirements within the deemed Marine Licence(dML) | The dML does not include any provisions requiring monitoring, either pre commencement or post works. It is a standard approach to undertake surveys prior to works to identify features of conservation importance and, where possible, micro-site around them and where not possible to monitor their recovery. In addition, monitoring may be required where there remains residual concerns. | Natural England advises that conditions to secure pre and post works monitoring as required and set out in an In Principle Monitoring Plan (IPMP). | It is possible the issue could be progressed with changes to the DCO. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change.
Physical Environment
NE10 | Cable Protection adjacent to Goodwin Sands MCZ | It is not stated whether cable protection measures may be required directly adjacent to Goodwin Sands MCZ. Therefore, we are concerned that the potential presence of cable protection measures adjacent to the MCZ, over the lifetime of the Project, could affect sediment transport processes/pathways operating on and around the MCZ and in turn lead to morphological change at the MCZ. | Natural England advises that the Applicant should clarify whether cable protection measures may be required adjacent to Goodwin Sands MCZ. The WCS parameters for cable protection measures near/at the MCZ should be provided, and potential impacts to supporting sediment transport processes should be considered for the lifetime of the project. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change. Please see Appendix D3 [REP3-118] to our Deadline 3 submissions and Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change. Please see our detailed comments on indirect impacts to Goodwin Sands MCZ in Appendix D4 of our Deadline 4 submission.
NE11 | Need for more detailed analysis of morphological change. | Natural England highlights significant morphological change within Pegwell Bay including beach profile elevation at Pegwell Bay, progradation of Shell Ness and migration of the River Stour channel. | Natural England advises that a more detailed analysis of the longer-term morphological trends through the lifetime of the Project should be carried out to inform the cable burial and asset integrity assessment. | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change Please see Appendix D3 [REP3-118] to our Deadline 3 submissions and Appendix J3a [REP3A-028] to our Deadline 3a submission. |  | Concerns remain regarding coastal evolution at the Kent landfall. Need to establish a more robust baseline characterisation prior to installation to assess impacts against - Please also see our advice in Appendix D4.
NE12 | Missing information | Appendix 4.1.A misses several important information: - There is no mention of information on the dispersion model validation. - No detailed information of the hydrodynamic modelling and model that provided the tidal conditions. | Natural England advises that the Environmental Statement (ES) should be updated to include relevant information as described | It is possible this issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Deadline 1A, change request and 2. |  | No change. Please see Appendix D3 [REP3-118] to our Deadline 3 submissions. |  | No change.
Benthic Ecology
NE13 | Worst case scenario | There are a number of potential impacts on both intertidal and subtidal benthic habitats which have not been adequately considered or assessed within the Environmental Statement. | The Environmental Statement and relevant assessments are updated to consider all potential pathways of effects on intertidal and subtidal benthic habitats. Until resolved Natural England is unable to accept the conclusions within the MCZ assessment. | It is possible the issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE14 | Maximum design cable protection | Natural England has concerns that the Maximum Depth parameter figures for cable protection are ambiguous and lack of rationale. | Review of all relevant application documents once ambiguities in the maximum design / worst case scenario have been addressed. | It is possible the issue could be progressed with further provision of information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix D3 [REP-118] to our Deadline 3 submissions and Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE15 | Mitigation | Natural England notes that the Applicant has made no strong benthic mitigation commitments to avoid or reduce impacts to Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats. | Natural England advises that impacts to Section 41 NERC Habitats are avoided and due consideration is demonstrated. | It is possible this could be progressed with further commitments and information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE16 | Permanent loss of benthic habitats | Natural England is concerned that the Applicant has not committed to the removal of cable and scour protection at the point of decommissioning. | Due consideration should be given to the nature of the cable protection used and should favour engineering options with the greatest likelihood of successful removal at the Project’s end of life. A commitment to removal of all infrastructure associated with the development at decommissioning is secured within the DCO and an Outline Decommissioning Plan should also be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE17 | Inappropriate assessment of benthic receptors | Natural England disagree with the Applicant’s assessment of the sensitivity of a number of benthic receptors. | The Environmental Statement requires revisiting and updating with an appropriately considered and evidenced assessment of the sensitivity of receptors, including those identified within the Zone of Influence (ZoI). | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE18 | Assessment on Benthic Receptors incomplete. | Natural England advises that the Applicants Environmental Impact Assessment (EIA) has not considered potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures” (A4.23 – Communities on soft circalittoral rock) which were recorded throughout the Offshore Scheme site specific surveys. | Natural England is unable to agree with the conclusions of the EIA, Report to inform Appropriate Assessment (RIAA) and Marine Conservation Zone (MCZ) assessment until a transparent and comprehensive assessment of all impacts upon all benthic receptors has been provided for review. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3a [REP3A-027] to our Deadline 3a submission. |  | No change.
NE19 | Sandwave Levelling | Natural England considers that further assessment of impacts from sandwave levelling on benthic receptors is required. | Natural England advises that the ES, and where relevant, RIAA and MCZ assessments, are updated to consider all potential pathways of effect on features of conservation importance from sandwave levelling and deposition of sediment | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix C3a [REP3A-026] to our Deadline 3a submission and Appendix B3 [REP3-117] to our Deadline 3 submission. |  | No change. Please see our detailed comments in Appendix D4.
Marine Mammals
NE20 | Worst Case Scenario | While it is mentioned that a precautionary approach to estimating marine mammal abundances was recommended at the Statutory Consultation phase, it remains unclear if precautionary estimates have been considered. | Clarity is needed in the wording to demonstrate how a precautionary approach has been adopted in addition to use of updated survey data. | Potentially resolved with updated information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. I28 |  | No change. |  | No change.
NE21 | Use of summer months as WCS | Harbour porpoise are known to occupy the southern region of Southern North Sea (SNS) Special Area of Conservation (SAC) in which they are designated in winter months (October – March), therefore it cannot be assumed that SCANS survey data conducted in July is representative of the greatest abundance of all cetaceans likely to be encountered. | The assessment should be updated to consider peak abundances for each species as representative of the WCS. | Potentially resolved with updated information. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. |  | Uncertain. Further information from the applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this.
NE22 | Sufficiency of EIA | Natural England cannot currently agree with the conclusions of the EIA for the reasons outlined in Appendix F [REP3-119]. | Updated assessment should be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | Natural England notes that only minimal changes have been made in the EIA followowing our advice, thus we maintain our original advice.
NE23 | Sufficiency of HRA | Natural England cannot currently agree with the conclusions of the HRA for the reasons outlined in Appendix F [REP3-119]. | Updated assessment should be provided. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England do not see any evidence of the changes in the assessment. In-combination assestment is particularly poor and has not been improved at all. Specifically, to assess whether there will be significant noise disturbance within a harbour porpoise SAC, the applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. Please consulate the Guidance for assessing the significance of noise disturbance against Conservation Objectives of harbour porpoise SACs (England, Wales & Northern Ireland). |  | There has been insufficent updates to assessments, particularly the In-combination assessment. Key concerns remain significant noise disturbance within a harbour porpoise SAC. The Applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. |  | No change.
Marine Ornithology
NE24 | Seasonal restrictions for Red Throated Diver in the Outer Thames Estuary SPA. | Natural England considers that an AEOI on the red-throated diver (RTD) feature of the Outer Thames Estuary SPA cannot currently be ruled out. Further, given the existing levels of disturbance/displacement and those associated with consented and proposed projects, even if AEOI can be ruled alone, any additional disturbance/ displacement would add to cumulative/in-combination impacts. | We request that the November to March timing restriction on cable construction works is widened in scope, for example to include pre-construction clearance activities, in line with advice provided in Appendix G4: Marine Ornithology. In order to understand the appropriate level of mitigation for different project phases, a more detailed spatio-temporal assessment is needed. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, Deadline 1A, change requests and Deadline 2. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, Deadline 1A, change requests and Deadline 2. |  | No change please see Appendix G4 to Natural England's Deadline 4 submission.
NE27 | 2km buffer around the Outer Thames Estuary SPA | Natural England would note that the seasonal restriction at the moment only applies within the SPA itself. Natural England’s guidance on recent projects involving cable installation works is to include a 2km buffer from the seaward boundary of the OTE SPA, as vessels may disturb RTD up to 2km away. We would propose that this be included within an updated restriction and see this as an important component of any strategy to avoid AEoI. | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. | Uncertain. |  | New Issue |  | New Issue |  | New Issue |  | New issue raised at Deadline 4
Suffolk LVIA
NE25 | Further information needed to support impact assessment | Natural England is concerned that the project may have a significant impact (in EIA terms) on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and the Suffolk Heritage Coast. | Please see Table 2 of Appendix H3 [REP3-120] for our detailed comments, and the further information required. | Uncertain. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change |  | No change |  | No change
NE26 | Significant cumulative impact assessment | Natural England is concerned about the significant (in EIA terms) cumulative impact that the project’s construction phase will have on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. | Natural England advise that information is required on how this significant adverse effect will be addressed. | Uncertain. | Red | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. | Red | No change |  | No change please see Appendix H3 [REP3-120] to Natural England's Deadline 3 submission. |  | No change please see Appendix H3 [REP3-120] to Natural England's Deadline 3 submission.

## A - Suffolk Onshore
Point | Point Number(s) from Appendix A RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix A - Suffolk Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | A1 | Further information is required to inform a Horizontal Directional Drilling (HDD) management plan; in terms of access requirements at the landfall site to facilitate HDD; and to inform the feasibility of the HDD proposals. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
2 | A2, A16 | Further assessment work should be provided to inform a robust soil management plan. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
3 | A3, A17 | The Suffolk onshore scheme includes areas that appear to be of national significance for bats, due to the assemblage of species identified including Annex II Barbastelle Species. Given the prevalence of Barbastelles and other species in the area, we encourage the applicant to contact Natural England about potential impacts to bats, their roosts and/or their habitats for commuting/foraging/dispersal. The removal of hedgerows could disrupt key commuting routes for bats. The Applicant has not sought any Letters Of No Impediment from Natural England for bats. We advise that the Applicant contacts Natural England’s licensing service |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
4 | A1, A4 | Post consent botanical surveys should be secured and undertaken on the areas of Leiston-Aldeburgh SSSI within the development boundary, including the area intended for HDD. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at pre-Deadline, Deadlines 1 and 1A - this issue is resolved.
5 | A5 | Detailed vegetation surveys (following the NVC survey method) will need to be undertaken to support any change in proposed methodology or future variations undertaken along the cable route to provide baseline information. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
6 | A6 | An assessment of potential impacts to the protected coastal habitats should be undertaken including access along the trenchless cable route or to the exit pits be required by vehicles/ construction equipment during works. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
7 | A7 | Dewatering impacts should be assessed in relation to sensitive shingle habitats if additional GI boreholes are needed or if the additional GI surveys determine that a change in the depth of drilling is needed |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. Further evidence is required. See Appendix A3 [REP3-116] for detailed comments |  | No change |  | No change
8 | A8 | Any references to avoiding the Woodlark breeding season should read from September to January inclusive and any (noise) mitigation should be secured for this time period. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at Deadline 1 and 1A this issue is resolved. We note that in sections Ex1.5.3 and 7.2.17 the references to the woodlark breeding season have been changed from ‘March-August’ to ‘February-August’ inclusive, in line with our advice.
9 | A9 | The ES chapters and methodology should be amended to provide clarity that ‘nationally designated ecological sites with dust sensitive features’ should be classified as a high sensitivity air quality receptor only. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
10 | A7, A10 | Further information is required on the location and methods of any additional GI works which may be required prior to construction along the proposed cable alignment. An outline trenchless crossing (and associated works) method statement will be needed at the consent stage to inform decision making, with the submission and agreement of a final method statement by the LPA/MMO, secured as part of the DCO/dML prior to construction. Mitigation measures to avoid, reduce and mitigate impacts to shingle vegetation, shingle sediment matrix, and groundwater should be included within the method statement |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
11 | A11 | There are potential ecological risks if drilling equipment becomes stuck due to unknown London Clay depth or gravel/cobble layers. Further detail is required on how equipment would be retrieved without surface excavation. An outline method statement should be provided at the consenting stage to ensure that appropriate mitigation is available and can be implemented. In addition, a condition should secure submission and agreement of the final method statement prior to construction. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Further information provided at Deadlines 1 and 1A have been welcomed, however further information is required, in particular regarding the HDD in the event of it getting stuck. We also advise that a condition is needed to secure agreement of the method statement. For detailed comments please see Appendix A3 [REP3-116]. |  | No change |  | No change
12 | A12 | An outline HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Further information provided at Deadlines 1 and 1A have been welcomed, however further information is required and a condition needs to be secured for the final HDD management plan to be agreed in consultation with the relevant SNCB prior to construction. For detailed comments please see Appendix A3 [REP3-116]. |  | No change |  | No change
13 | A13 | In relation to designated features of Sandlings SPA, the “March to August” period should be amended to read “February to August” and mitigation measures secured (in line with previous comments on Woodlarks) |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | Following review of documents provided at Deadline 1 and 1A this issue is resolved. We note that in sections Ex1.5.3 and 7.2.17 the references to the woodlark breeding season have been changed from ‘March-August’ to ‘February-August’ inclusive, in line with our advice.
14 | Appendix A1 [REP1-154] Submitted D1. NE Ref 1 | Overarching comment on HRA Impacts to acid grassland, a key supporting habitat within the SPA and FLL are not clearly assessed within the HRA. This advice replaces comment A14 within Natural England’s relevant and written representations |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
15 | A15 | There should be a commitment to keeping the King Charles III England Coast Path (KCIIIECP) open and available during the construction period, where possible, through the use of management measures, such as controlled crossings and signage. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
16 | A16 | An outline soil management plan supported by relevant ALC survey data should be provided to address consenting risks and issues associated with disturbance/changes to agricultural land grade, raised in our relevant/written reps. [RR-3920] with a comment to submit and agree a final soil management plan in consultation with relevant SNCB prior to construction |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
17 | Appendix A1 [REP1-154] Submitted D1. NE Ref 2 | AS-007 - Habitats Regulations Assessment. The Applicants assessment (7.2.9) states that although breeding birds have not been recorded the compound field is “very likely” to be functionally linked land. Natural England agrees with this assessment. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
18 | Appendix A1 [REP1-154] Submitted D1. NE Ref 3 | AS-007 - Habitats Regulations Assessment. Natural regeneration is proposed to restore acid grassland after disturbance within the construction phase (Paragraph 4.2.4 of the Outline Landscape and Ecological Management Plan). Natural England supports this proposal but advises that it is essential to understand soil fertility and pH for successful restoration. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
19 | Appendix A1 [REP1-154] Submitted D1. NE Ref 4 | AS-007 - Habitats Regulations Assessment. One function of the restoration and enhancement (acid grassland) area appears to focus on providing habitat for bird species particularly Woodlark and Skylark, also invertebrates. It is not clear if the aim is to create priority habitat, because if the focus is habitat for bird species, then the grassland species composition may not be as crucial as the habitat structure. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
20 | Appendix A1 [REP1-154] Submitted D1. NE Ref 5 | AS-007 - Habitats Regulations Assessment. The nature, location, quantity, habitat type, timing and duration of possible impacts to acid grassland are clarified and clearly stated in one place. The quantity and location of acid grassland affected differs between documents. These details should be clarified within the oLEMP. Clarification is also needed on: -why the further 8ha of temporarily affected acid grassland is not included in the total amount of acid grassland temporarily affected by the project. -why the acid grassland is not being avoided by HDD as per requirements of the mitigation hierarchy. -which acid grassland parcels are functionally linked to the Sandlings SPA How in-combination impacts with the extension of Aldringham Golf Course, which lies within the red line boundary of the Sea Link project, have been assessed. Clarity on project timescales including maintenance acid grassland (e.g. Paragraph 8.2.6 of HRA) cites 30 years, however all other timescales appear to refer to 10 years. -The report concludes a temporary impact but this relies on successful reinstatement which, if it fails would become a long-term impact. Contingency is required should habitats fail to reinstate during the expected timeframes. The intended function of the 6ha area and how it would benefit both woodlark and nightjar in order to clarify the conclusions of the HRA |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | In Section 8.2.5 of Document 6.6 (D) Habitats Regulations Assessment Report (Tracked), the timescale for maintenance of the acid grassland creation/enhancement area has been updated from 30 years to 10 years. This is now consistent with other application documents which state a 10 years maintenance timescale. This clarifies one of the queries we raised within this point, but other queries are not yet resolved. Please refer to NE advice in Appendix A1 [REP1-154] submitted at Deadline 1, NE Ref 5.
21 | Appendix A1 [REP1-154] Submitted D1. NE Ref 6 | AS-007 - Habitats Regulations Assessment. Impacts from the construction compound (Suffolk). Assessment of the impact of light spilling into the SPA and surrounding areas used by nightjars and woodlark is required as this would extend into the breeding season whilst the compounds are in operation. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change |  | No change
22 | Appendix A1 [REP1-154] Submitted D1. NE Ref 7 | AS-007 - Habitats Regulations Assessment. Noise assessment Natural England advise that the noise contour map included in Appendix E Figure 3 requires additional clarification. This is because it appears to show noise as a uniform contour throughout the working corridor regardless of proposed activity. It is unclear how the impact of HDD for example or construction compounds has been considered in this assessment as it is likely that noise impacts would vary between these activities and this does not appear to be illustrated on the map presented. |  | New comment included at Deadline 1 (ref NE Appendix A1 [REP1-154]) |  | No change, pending review of documents submitted at Deadlines 2 and 3. |  | No change, pending review of documents submitted at Deadline 3. |  | No change, pending review of documents submitted at Deadline 3.

## B - Kent Onshore
Point | Point Number(s) from Appendix B RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix B - Kent Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | B1, B6 | Further assessment work is required to determine whether Horizontal Directional Drilling (HDD) is a viable mitigation method to avoid direct loss of Thanet Coast and Sandwich Bay Special Protection Area (SPA)/Ramsar site and Sandwich Bay Special Area of Conservation (SAC). Natural England strongly advises that geotechnical investigations should be provided to inform the consenting phase to give the Secretary of State the level of comfort required on the feasibility of this installation technique. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
2 | B1, B5, B11 | An outline intertidal and HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
3 | B1, B30-33 | Full consideration should be given to hydrological impacts of HDD, particularly upon the humid dune slacks feature of the Sandwich Bay SAC. The assessments should be updated. With groundwater investigations used to determine location of habitat mapped in relation to the two aquifers, and dewatering zones of influence to assess potential for impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
4 | B1, B28 | The likely impacts of the drilling equipment becoming stuck and subsequently requiring excavation needs to be considered in full in the HRA and discussed in detail in an outline contingency plan within an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied with the Applicant’s response confirming that in the event that equipment should become stuck no excavation to recover stuck equipment would be undertaken along the Kent HDD route beneath areas of saltmarsh or shallow lagoon.
5 | B2, B14, B16 | In order to provide sufficient detail to the ExA regarding potential air quality impact pathways, it should be clarified if in-combination impacts are likely. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter.
6 | B2, B14, B16 | Clarity should be provided regarding the length of time that Non-Road Mobile Machinery (NRMM) will be used and the screening distance applied. Where NRMM is below 20MW, the screening distance should be 500m. Where use of NRMM is only to be used for periods of under a year within an impact risk zone, then impacts are less likely as AQ is considered on an annual average basis. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter.
7 | B3, B38 | Percussive and disturbing works (e.g. piling) to install pylons either side of Sandwich Bay to Hacklinge Marshes SSSI should be undertaken outside of the breeding bird season to avoid a significant impact upon the SSSI. In addition, the required operational works should also be undertaken outside of the breeding bird season. These measures should be secured within the Register of Environmental Actions and Commitments (REAC). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Commitments B45 and B50 in the REAC have been updated so that any works >60dB at the SSSI boundary will take place outside of breeding bird season. In addition, percussive and disturbing works (e.g. piling) will take place outside of breeding bird season. Operational works - have queried why restriction on works can't cover the entirety of breeding bird season. |  | No Change |  | No Change
8 | B4 | The Phase 1 maps should be updated to indicate whether standing water is freshwater, saline or brackish as per the JNCC 2010 guidance. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. Please Appendix B3 [REP3-117].
9 | B6 | Geotechnical investigations should be provided to confirm whether HDD installation methods are suitable/feasible at the Pegwell Bay cable landfall location. If a trenchless technique is found not to be valid then there is a high risk of an Adverse Effect on Integrity and that a full derogations case would need to be presented including appropriate compensation measures |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
10 | B7 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
11 | B8 | The definitions for moderate adverse (negative) impact and major adverse (negative) impact should be reviewed to ensure there is a clear difference between the two effects and consideration should be given by the Applicant as to whether this changes to the conclusions of the assessments. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. Please see Appendix B3 [REP3-117].
12 | B9 | Table 2.12 should demonstrate the pathway for consideration of LSE at individual site feature level, including a column identifying the habitat/species receptors being considered in each case. This should include screening in the potential pathway for hydrological impacts of construction (HDD) upon groundwater dependent H2190 Humid Dune Slack feature of Sandwich Bay Special Area of Conservation (SAC). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Applicant directed to a table provided in Appendix A of the HRA which provides this level of detail and Natural England agree it is unnecessary to repeat this. Please see Appendix J3A [REP3A-028] to our Deadline 3a response
13 | B10 | The hoverport site should be subject to a management program to remove target invasive plant species before any work commences and comprehensive biosecurity measures during construction and O&M to reduce the risk of spread. This should be secured in the DCO/dML and/or within a named plan. The Non-native Species Management Plan (7.5.12) should be updated to include the hoverport site and route of access as a pathway for potential spread. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied that the risk of INNS introduction at the former hoverport has been considered and the appropriate controls put in place to manage this risk. Please see Appendix J3A [REP3A-028] to our Deadline 3a response
14 | B12 | Confirmation should be provided that the written scheme of decommissioning will consider impacts to ecological receptors (including designated sites) in consultation with relevant stakeholders and statutory bodies. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Recommendation that commitment GG31 is strengthened in line with the Applicant’s response to our Relevant Representations comment B12, to read: ‘A written scheme of decommissioning will be submitted for approval to the relevant planning authority at least six months prior to any decommissioning works. This would consider environmental impacts as required at that point in time, including to ecological receptors and designated sites’ |  | No Change |  | No Change
15 | B13 | Nationally designated sites should be considered a highly sensitive receptor to dust impacts, given their national importance, and ES chapters and assessments should be updated to reflect this. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change |  | No Change |  | No Change
16 | B17 | The Applicant should confirm the relevant pollutants emitted by the NRMM that could interact with ecological receptors |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England has changed its approach to giving advice on air quality impacts and will no longer be providing bespoke comment. See standard advice attached to the Covering Letter.
17 | B19 | All references to loss of functionally linked land for golden plover should be updated from an operational phase impact to a construction phase impact and assessments updated accordingly. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | While the change is not essential to the outcome of the assessment, as the impact has still been considered and satisfactorily mitigated, it should be made for completeness. |  | No Change |  | No Change
18 | B20 | The list of features of Sandwich Bay SAC in Paragraph 3.73 is incomplete and should be updated to include the missed features, with the assessment updated accordingly. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved.
19 | B22 | The Conservation Objectives listed for Thanet Coast SAC are incorrect and should be updated. The assessment should be updated to determine if these conservations objectives are likely to be hindered by the proposed works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved.
20 | B23 | The threats and pressures identified in the 2015 Natural England SIP for Thanet Coast should be added into section 3.14.4 and assessments updated to determine if these pressures will hinder the conservations objectives. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved.
21 | B24 | Natural England advises that [APP-3920] Para. 4.4.33 is updated to included consideration of operation traffic emissions. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Completed [REP1-071] 4.4.36
22 | B25 | Natural England advises that the in-combination assessment for the Kent Onshore Scheme is checked by the Applicant to ensure that all appreciable effects that are not significant alone have been taken into consideration' |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England are satisfied with the proposed avoidance/mitigation measures. While progress is noted, we question why these works cannot be restricted throughout the entire breeding season (March–September inclusive), once this addressed we should be able to agree that there will be no significant impact upon Sandwich Bay to Hacklinge Marshes SSSI as a result of the proposal. |  | No Change |  | No Change
23 | B29 | Seawater pumps used to flush saltmarsh vegetation should be operated at low pressure (<50psi) to reduce damage to vegetation/foliage and minimise potential for erosion of surface sediment. This should be confirmed in an Outline HDD Management Plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
24 | B38 | The frontal edge of the saltmarsh is exposed and vulnerable to erosion, and sensitive annuals grow from the surface of the mudflat which are easily overlooked and damaged by trampling. Natural England advise implementing a commitment to a minimum stand-off distance for vehicles and machinery at the HDD exit points. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4.
25 | B39 | Any tree height maintenance for the new Over Head Line (OHL), scrub opening for access to Sandwich Bay to Hacklinge Marshes SSSI, or other similar works should be undertaken outside of the breeding bird season to avoid disturbance, and this should be secured within the Register of Environmental Actions and Commitments (REAC). Natural England is currently unable to agree with the Applicant that there is unlikely to be a significant impact upon Sandwich Bay & Hacklinge Marshes SSSI, due to the concerns regarding timing potentially disturbing works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Query why the operational works can't take place completely outside of breeding bird season. |  | No change. |  | No change.
26 | B41 | Natural England has been made aware by the Applicant’s ecologist that no Letters of No Impediment will be required. Should this change, we recommend that the Applicant make available draft protected species licences for our wildlife licencing team to review. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 3 |  | No change. |  | No change.
27 | B45 | The final BNG assessment should incorporate separate accounting lines to ensure a 10% net gain is being achieved. |  | No change, pending review of documents submitted at Deadlines 1 and 1A. |  |  |  | No change. |  | No change.

## J - Kent Landfall
Point | Point Number(s) from Appendix B RR-3920 or Appendix J3A [REP3A-028] | Taken from Natural England’s Submission to Deadline 3A Sea Link Energy Cable Appendix J - Kent Onshore | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
RI_J1 | B1, B6 | Further assessment work is required to determine whether Horizontal Directional Drilling (HDD) is a viable mitigation method to avoid direct loss of Thanet Coast and Sandwich Bay Special Protection Area (SPA)/Ramsar site and Sandwich Bay Special Area of Conservation (SAC). Natural England strongly advises that geotechnical investigations should be provided to inform the consenting phase to give the Secretary of State the level of comfort required on the feasibility of this installation technique. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J2 | B1, B5, B11 | An outline intertidal and HDD management plan should be provided to address consenting risks and issues raised in our relevant/written reps. [RR-3920] with a comment to appropriate mitigation measures and submission of and agreement on a final HDD management plan in consultation with relevant SNCB prior to construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J3 | B1, B30-33 | Full consideration should be given to hydrological impacts of HDD, particularly upon the humid dune slacks feature of the Sandwich Bay SAC. The assessments should be updated. With groundwater investigations used to determine location of habitat mapped in relation to the two aquifers, and dewatering zones of influence to assess potential for impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J4 | B6 | Geotechnical investigations should be provided to confirm whether HDD installation methods are suitable/feasible at the Pegwell Bay cable landfall location. If a trenchless technique is found not to be valid then there is a high risk of an Adverse Effect on Integrity and that a full derogations case would need to be presented including appropriate compensation measures |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J5 | B7 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J6 | B29 | Seawater pumps used to flush saltmarsh vegetation should be operated at low pressure (<50psi) to reduce damage to vegetation/foliage and minimise potential for erosion of surface sediment. This should be confirmed in an Outline HDD Management Plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J7 | B38 | The frontal edge of the saltmarsh is exposed and vulnerable to erosion, and sensitive annuals grow from the surface of the mudflat which are easily overlooked and damaged by trampling. Natural England advise implementing a commitment to a minimum stand-off distance for vehicles and machinery at the HDD exit points. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Please see Appendix J3A [REP3A-028] provided at Deadline 3a which includes all advice relevant to Kent Landfall. Please note a new Risk and Issues Tab 'J - Kent Landfall' to be included within Deadline 4 and PADSS also updated for Deadline 4. |  | No change
RI_J8 | [REP3A-028] Table 2, point 10 - ref 7.3.68; Table 3, points 4 (ref table 3) & 5 (ref 4.3.42) | Based on the current information provided we cannot agree with the HRA conclusion on the significance of temporary disturbance. Full assessment of all protected site features and the potential impact pathways over the lifetime of the project is required and consideration given to how to reduce impacts wherever possible. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | Please see Appendix J4 to our Deadline 4 submission
RI_J9 | [REP3A-028] Table 2, point 6 - ref 5.3.8; Table 5, point 4 - ref B68 | It is the view of Natural England that AEoI on SPA/Ramsar or significant impacts to the SSSI can not currently be excluded. Further commitments are required at the consenting phase to mitigate impacts. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J10 | [REP3A-028] Table 3, point 8 - ref 7.4.13; Table 5, point 4 - ref B68; and Table 6, point 1 and point 15 | A requirement/condition should be included within the DCO/dML to ensure that the final Landfall Construction Method Statement (LCMS) and Drilling Fluid Management Plan (DFMP), is agreed with the regulators in consultation with the relevant SNCB prior to construction. Within which it must demonstrate that the potential impacts are no greater than predicted and any divergence will need a further assessment prior to construction and where necessary further permissions sought. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J11 | [REP3A-028]: Table 2, point 5 - ref 4.4.2 and Table 2, points 1 & 2 ref (3.7.1); Table 6, point 13 (table 5.1)and point 4 - ref 2.2.7 | The potential impacts from vehicles transiting the intertidal area need to be fully assessed in terms of cable installation and/or repair/ replacement of cables to assess potential changes to habitat features and protected species over the lifetime of the project. Particularly in relation to impact pathways to intertidal habitats and SPA features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No Change
RI_J12 | [REP3A-028] Table 5, point 3 - ref B67 and Table 6, point 2 - ref 2.2.5 | Further mitigation measures should be considered to reduce the impacts to intertidal habitats and compaction of sediment. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J13 | [REP3A-028] Table 5, point 6 - Ref B70 | A commitment should be made to only undertake cable repairs/replacement activities where it can be demonstrated that there will be no significant impacts to intertidal saltmarsh at the exit pit or along intertidal transit route. Where this is not possible a separate marine licence and updated assessment of impacts will be required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J14 | [REP3A-028]: Table 2, point 3 - ref 4.3.4; Table 2, point 7 - ref 7.3.10; Table 3, point 4 - ref 3.1 and Table 5, point 5 - ref B69; Table 6, point 7 (table 2.1) and point 14 (section 7) | The importance of the saltmarsh environment. It is unclear what the potential impacts to the saltmarsh would be and further consideration and evidence is required in relation to potential impacts from changes in coastal processes from the presence of infrastructure (such as the cofferdams) during installation and possibility of changes in extent of interest features over time. Further evidence should be presented to demonstrated that impacts can be avoided during installation and operation. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix E3a J3A [REP3A-028] to our Deadline 3a submission. |  | No change
RI_J15 | [REP3A-028] Table 5, point 2 - ref B66 [AS-138], [CR1-055] | A commitment should be made to avoid access on to the south-west corner of the hoverport due to the presence of fragmented saltmarsh vegetation. Further clarification is also required regarding impacts to the saltmarsh should the extent of vegetation change both temporally and spatially. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J16 | [REP3A-028]: Table 2. point 4 - ref 4.3.41 and Table 5, point 8 - ref MPE04 | It is unclear what the Maximum Design Scenario (MDS) is for cable protection (both temporary and permanent) at the exit pit locations. Information should be updated to provide justification and inform the HRA for the proposed cable protection, clarification regarding the MDS and location, and consider all impact pathways to all protected site features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J17 | [REP3A-028] Table 5, point 7 - ref MPE02 | Further evidence on coastal processes is required to support the proposed mitigation measure for seabed lowering at this location. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J18 | [REP3A-028] Table 2, point 5 - ref 4.4.2; Table 2, point 9 - ref 7.3.68 and Table 6, point 3, ref - 2.2.6 | Further consideration of disturbance impacts on SPA birds and intertidal habitats from vehicle movement from cable installation and operational activities within the intertidal area is required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J19 | [REP3A-028] Table 2, point 8 - ref 7.3.12, Table 6, point 9 - ref 3.4.3 and point 10 - ref 3.4.7 | The potential for bentonite frac-out needs to be considered and the impact pathways to SPA features need to be assessed, including the likely duration of bentonite remaining on the seabed and the implications for the wider ecosystem with particular note to the smothering of saltmarsh vegetation. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J20 | [REP3A-028] Table 5, point 1 - ref B61 | The commitment to remove bentonite where necessary within saltmarsh feature should include "by only using handheld equipment" to ensure there will be no vehicle access onto the saltmarsh. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J21 | [REP3A-028] Table 2, point 1 and table 3, point 7 - ref 4.4.2 | Further clarity is required on the potential impacts at all locations and features where HDD is proposed. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J22 | [REP3A-028] Table 2, point 11 - ref 7.4.3 | It is unclear with a likely depth of 15-18m for HDD cable installation whether the required HDD installation distance will be achieved. Further assurance is is needed to demonstrate that the depth of installation will not hinder achieving the HDD distance required. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3[REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J23 | [REP3A-028] Table 3, point 8 - ref 7.4.13 and Table 5, point 4 - ref B68 | The HRA should be informed by an outline HDD/landfall construction management plan which will need to be provided in full at the time of consent in consultation with the relevant organisations. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118]on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J24 | [REP3A-028] Table 3, point 6 - ref 3.47 and point 8 - ref 7.4.13 | Assessment of the direct and indirect impacts from the use of concrete mattresses for landfall works is required, including consideration of any scouring. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J25 | [REP3A-028] Table 6, point 5 - ref 2.3.3 | Further consideration is required of potential impacts of the proposed large cofferdams being in situ for 120 days. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix D3 [REP3-118] on marine process at Deadline 3; Appendix E3a on Benthic impacts and Appendix J3A [REP3A-028] on Kent Landfall to our Deadline 3a submission. |  | No change
RI_J26 | [REP3A-028] Table 6, point 6 - ref 2.3.3 | The proposed lighting of the cofferdams and associated working area around them needs further assessment in terms of disturbance impacts to Annex I birds (foraging, roosting and nesting) and foraging bat species is required in relation to both temporary habitat loss and impacts from lighting and installation works. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J27 | [REP3A-028] Table 6, point 8 - ref 3.3.1 | The parameters of the proposed rollers and their associated transportation and installation methods is unclear. A more detailed assessment is required and where possible these should be transported by sea to the intertidal on a barge which can bottom out with ramps so that installation equipment can access intertidal direct from there. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J28 | [REP3A-028] Table 6, point 11 (table 3.1) | Further consideration to the use of a jack up barge for the construction of the cofferdam is required and the use of the supporting vessels in order to reduce the impacts to the marine environment. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J29 | [REP3A-028] Table 6, point 12 (table 3.1) | Further information is required on the intended use of ballistic bags and impacts assessments undertaken accordingly. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 4 submission. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
RI_J30 | Appendix J4 - point 6 | Clarification as to what is meant by 'ponds' is required and how impacts will be reduced | [7 empty] | New issue identified - further to our comments provided at J4 to our Deadline 4 submission.
RI_J31 | New Issue | Contamination Risk at Kent Landfall - there is evidence relating to the potential release of contaminants and debris from further degradation of the Hover Pad. We advise that further clarification and assessment of this issue is required. | [7 empty] | New issue identified - further to our comments provided at J4 to our Deadline 4 submission.

## C - DCO
Point | Point Number(s) from Appendix C RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix C - Draft Development Consent Order | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | C1, C3 | The definition of commencement within the DCO and dML should be updated to include a separate definition of offshore commencement |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Concerns remain regarding the pre-lay grapnel run. See Deadline 3A Appendix C3a [REP3A-026]. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
2 | C2, C5 | The arbitration article should be appropriately updated |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Resolved. The arbitration Article has been appropriately updated.
3 | C4 | The definition of maintain within the DCO / dML should be amended to remove decommissioning and to link to the extent of the work assessed in the ES and consented |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
4 | C6 | Requirement 6 should be amended to require consultation with relevant SCNB. Consider moving marine only plans to the appropriate section of the dML. Consider including a requirement for an OLEM |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially Resolved. Requirements have been split between requirements and DML, however consultation with SNCB has not been secured. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
5 | C7 | Include requirement to secure protection of European Protected Species or required Biodiversity Net Gain (standard requirements in DCOs) |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
6 | C8 | Schedule 4 should be updated to consider the requirements to consult with relevant SCNBs |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
7 | C9 | The definition of commence within the DCO excludes offshore preparation works. The definition of Offshore preparation works, or/and commence should be amended to remove works significantly impactful to the marine environment |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Concerns remain regarding the pre-lay grapnel run. See Deadline 3A Appendix C3a [REP3A-026]. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
8 | C10 | The DCO should be amended to include the requirement to micro-site around any features of conservation importance, in particular those listed under Section 40 and 41 of NERC 2006. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
9 | C11 | The dML should include conditions to secure pre and post works monitoring as required and set out in an In Principle Monitoring Plan (IPMP). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change. NE is reviewing the updated DCO submitted at Deadline 3 and will update at Deadline 5.
10 | C12 | The Applicant should provide an Outline Offshore Operations and Maintenance Plan (OOMP) and the DCO should be appropriately updated to note this as a certified document, and the interpretation of maintain within the DMLs should be updated to reflect that the extent of maintain is as detailed within the Outline OOMP. Raised at Deadline 4 see Appendix G4 for details. |  | New issue |  | New issue |  | New issue |  | Raised at this Deadline.
11 | C13 | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. |  | New issue |  | New issue |  | New issue |  | Raised at this Deadline.

## D - Physical Environment
Point | Point Number(s) from Appendix D RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix D - Physical Environment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | D1, D32 | The Applicant should clarify whether cable protection measures are required adjacent to Goodwin Sands MCZ, with WCS parameters for cable protection measures provided, and potential impacts to supporting sediment transport processes assessed for the lifetime of the project. The Applicant should also consider the potential indirect effect of placing cable protection measures adjacent to the MCZ in terms of influencing sediment transport and seabed morphological change. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change.
2 | D2, D10 | A more detailed analysis of the longer-term morphological trends through the lifetime of the Project should provided to inform the cable burial and asset integrity assessment and assess potential for significant morphological change within Pegwell Bay including beach profile elevation at Pegwell Bay, progradation of Shell Ness and migration of the River Stour channel |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Issue progressed but not resolved. Adequately managing the risks and uncertainties for cable exposure and landfall infrastructure vulnerability is of vital importance. Further assurance is needed to demonstrate that landfall infrastructure and construction activities will not be affected by morphological change over the project lifetime (i.e. 40-60 years) or vice versa, by altering coastal processes and affect coastal morphology and/or sensitive benthic/supporting habitats. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission and Appendix D4 to our Deadline 4 submission.
3 | D3, D13 | The Environmental Statement (ES) should be updated to include relevant information, including: Dispersion model validation Hydrodynamic modelling and model that provided the tidal conditions (Appendix 4.1A) |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 1A, Change Request, and Deadline 2. We advise that this information should be provided to support Document 6.3.4.1.A ES Appendix 4.1.A [APP-195]. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission
4 | D4 | Sites for Trenchless cable installation crossings should be listed, rather than mentioning the trenchless installation generically as an option for cable installation anywhere. The Project Description and relevant ES chapters should be updated |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Natural England advises that the Applicant should signpost (in the Description of the Proposed Project document) to the relevant document(s) detailing the location of trenchless crossings, including at landfall. A figure should also be provided showing the location of the landfall trenchless crossings. |  | No change |  | No change. Please see our advice in Appendix D3 [REP3-118] to our Deadline 3 submission
5 | D6 | An updated assessment to include consideration of the HDD hydrodynamic impacts including (but not exclusively) from the use of any cofferdam, cable protection etc. should provided to assess whether any ground preparations may affect hydrodynamics and morphodynamics at the Suffolk landfall. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England welcome confirmation that there is no requirement for use of a cofferdam at the Suffolk landfall, can the Applicant signpost/confirm where this commitment is secured? |  | No change |  | No change.
6 | D7 | Figure 11 Offshore Seabed Surficial Geology should be updated to include distribution of bedforms at each KP to help consideration of potential environmental impacts |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | We note the updated figures in [REP1-009] which now includes KP markers and the distribution of bedforms. This resolves the issue.
7 | D8 | Sandbanks MCZ is not a recognised designated site and is not acknowledged in the Channel Coast Observatory Southeast Regional Coastal Monitoring Programme as a monitoring point. Clarity is needed on which monitoring station was used to obtain the data. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England suggest that this monitoring station is at Goodwin Sands (i.e. the Goodwin Sands waverider buoy). If the Applicant can provide confirmation then this issue will be resolved. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change, awaiting confirmation from the Applicant.
8 | D9 | The ES chapter should be updated to include all designated sites relevant to the Offshore Scheme, including figures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 2. All designated sites relevant to the Offshore Scheme should be identified on the relevant maps and figures in the ES Chapter to inform the impact assessment. Figure 6.4.4.1.12 Marine Designated Sites currently only shows designated sites at/close to landfall. |  | No change |  | The Applicant has now included Thanet Coast & Sandwich Bay SPA and Thanet Coast & Ramsar Site in the ES Chapter [REP3-021] which resolves this issue.
9 | D11 | Provide the reports and an appendix to respond to the comment: ABPmer. (2024a). Landfall Assessment at Aldeburgh. Sea Link Project – Landfalls sediment modelling. ABPmer. (2024b). Landfall Assessment at Pegwell Bay, Sea Link Project |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved.
10 | D12 | Clarity is needed on what references were used to determine the expected bedrock geology in the Offshore Scheme. It is also unclear if any sediment dispersion release from the different cable installation methods was modelled assuming sediment in each location has the same composition. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadline 2. Natural England advises that the Applicant needs to provide the relevant reference or source of evidence upon which their assumption is made regarding the nature of the sub-surface geology, its consolidation, dispersion and amount released during cable installation. We also seek clarification on whether the sediment size fractions modelled were uniform for the different release locations, or representative of the varying sediment composition along the cable route. |  | No change |  | No change.
11 | D15 | To inform the impact assessment, further consideration should be given to potential changes to the wave regime and seabed/nearshore morphology due to the presence of cofferdams during construction. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The EIA should be updated accordingly, taking into account the larger cofferdam size proposed, seabed disturbance area and volume, blockage potential, and scour potential. Duration and timing of the cofferdam installation and presence should be taken into account. The implications of the larger cofferdam dimensions to the EIA conclusions should be considered and evaluated, in terms of the scale and duration of seabed morphological impacts. This should also include the WCS predicted nearshore seabed recovery time |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
12 | D16 | Consideration should be given to potential construction and operational impacts to the sandwave-sandbank system present at the approach to Pegwell Bay. |  | Natural England highlighted this issue as 'green' during Rel Reps in error. D16 included from Deadline 3 with the corrected RAG status of 'amber' |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding their resilience and sensitivity to cable protection measures placed on/adjacent to them. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
13 | D17 | The potential impact to Aldeburgh Napes sandbank morphology due to cable installation have not been clearly stated or assessed. Given the potentially important role played by Aldeburgh Napes in protecting the adjacent coastlines, the potential impact of cable installation on its morphology should be further considered. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The scale/extent of any cable installation and cable protection impacts on the Aldeburgh Napes need to be provided to inform the impact assessment and support the EIA conclusions. Please also see our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice at Deadline 3a [REP3A-027] and Appendix D4 to this Deadline 4 submission.
14 | D18 | The results and interpretation of intertidal ground investigations appraising the risk associated with drilling activity should be submitted into examination, including consideration of the potential for impacts to intertidal habitats in the HRA and access considerations. This information should be used to inform an outline HDD management plan. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. There remain a number of key geotechnical and construction risks for the Pegwell Bay HDD that will need to be assessed and managed, including drilling fluid loss, groundwater flow into the chalk aquifer, flooding, and collapse of the Bullhead Beds. Therefore, our initial concerns remain. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
15 | D19 | APP-074 should be updated to reflect the need to avoid and where that is not possible minimise impacts to the Coralline Crag when selecting the marine exit site and onwards cable installation works (i.e., impact assessment of the HDD exit options should also be included). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | In [AS-114] it is stated that the HDD exit point will target an exit location that will be designed such that there is not a risk of exiting where the Coralline Crag is at the surface. During detailed design, the HDD contractor will microsite the exit points based on seafloor surveys and ground investigations. However, in [PDA-037] it is stated that all 3 potential points will go through the crag, and it is not stated whether drilling through this geological feature may have any impacts on the crag. This needs to be clarified. Please also see our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | Issue progressed. We welcome confirmation from the Applicant [REP3-021 & REP3-079] that there will be no cable protection placed on the surface of the Coralline Crag outcrop and the HDD exit will be located to the east of a continual section of outcrop. However, we seek clarification on other potential impacts to sub-surface or non-continual sections of Coralline Crag through the lifetime of the proposed project. This is also captured in Appendix D4 of our Deadline 4 submission
16 | D20 | Excavated material should be deposited in similar sediment habitats, adjacent to and updrift of the dredge location, this is standard best practice advice especially within designated sites and within the vicinity of sandbanks. The onus is on the Applicant to commit to best practice mitigation measures and therefore align seabed preparation works with installation to reduce the risk of infilling. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
17 | D21 | Natural England advises that further information on WCS parameters for cable protection and updated assessment of impacts at landfall is required to address consenting risks and issues raised in our relevant/written reps. [RR-3920] |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Further consideration should be given to the risk posed by Stour channel migration to the cable burial depth over the lifetime of the Project. |  | No change |  | No change. The WCS for cable protection and locations remain unclear. Further information is needed.
18 | D22 | Where cable installation activities may alter significant/important bedforms such as Goodwin Sands MCZ, Aldeburgh Napes, Cross Ledge etc., evidence of recovery to sandwave-sandbank should be provided to validate the Applicant’s predictions re: expected to recover and re-establish. Monitoring sandwave-sandbank recovery should be secured in an In Principle Monitoring Plan and dML for associated impacts. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding the resilience and sensitivity of any affected mobile sandbanks to cable protection measures placed on/adjacent to them. See also our advice in Appendix D3 [REP3-118]. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
19 | D23 | The Applicant should evaluate projected vertical elevation changes to the beach/intertidal and coastal retreat rates at both Landfalls during the lifespan of the Project. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue is resolved. |  |  |  | We no longer consider this matter resolved. We note the concerns regarding the coastal geomorphology baseline for the Suffolk landfall, and updated coastal erosion/shoreline management information provided by East Suffolk Council in [REP2-048] we consider that this remains as a key consenting and environmental risk. Concerns remain regarding coastal evolution at the Kent landfall. Need to establish a more robust baseline characterisation prior to installation to assess impacts against - Please also see our advice in Appendix D4 to our Deadline 4 submission.
20 | D25 | Further evidence is needed to support the conclusions regarding impacts to the nearshore seabed morphology due to landfall installation activities within Pegwell Bay. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Clarification of the WCS disturbance footprints for cable installation activities is needed to support and inform the HRA conclusions for the Kent landfall/Pegwell Bay. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
21 | D27 | Until further information has been provided by the Applicant as set out in [RR-3920] Appendix D, Natural England is unable to agree with conclusions in regard to marine process receptors included within the HRA |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. We seek further information or clarification on the potential impacts to marine processes which could in turn affect designated sites/protected features |  | No change |  | No change. For more detailed advice, please see Appendix D4 to our Deadline 4 submission.
22 | D30 | It remains unclear if all of the pressures/impact pathways have been fully assessed alone and cumulatively. The MCZ assessment should be updated to reflect the outcome of address points raised in Appendix D [RR-3920] |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at Deadlines 1A, Change Request and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
23 | D31 | The Applicant should evaluate migration of the Goodwin Sands sandbanks over the lifespan of the scheme to inform the MCZA and impact assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The placement of external cable protection within or adjacent to mobile sandbanks may alter sediment transport processes and, in the case of Goodwin Sands MCZ, hinder the conservation objectives of protected features. Therefore, potential impacts to Goodwin Sands MCZ and Cross Ledge Sandbanks need to be clarified and assessed. If relevant, the total area and volume of external cable protection in Cross Ledge Sandbanks should be provided. Evidence should also be provided to support the assessment conclusions and assumptions regarding their resilience and sensitivity to cable protection measures placed on/adjacent to them. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change.
24 | D33 | Cumulative/in-combination effects due to other nearby activities should be considered e.g. aggregate dredging, in particular for Goodwin Sands MCZ. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The Applicant should clarify whether there is the potential for cable protection to be placed adjacent to Goodwin Sands MCZ over the lifetime of the Project. If the Applicant considers it unlikely that cable protection will be required adjacent to the MCZ, then this should be secured as a condition. If its considered to be a requirement for cable protection adjacent to the MCZ, then its potential to interrupt or modify sediment transport should be assessed. In turn, consideration should be given to the conservation objectives of the protected features of the MCZ. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
25 | D34 | The assessment requires further information (in relation to potential changes to the physical Environment) before we can advise further on the require of mitigation measures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | This issue concerns potential risks to Goodwin Sands MCZ due to the placement of cable protection adjacent to the MCZ and also cumulative impacts to the MCZ, as detailed in the comments above. No change, pending review of documents submitted at Deadlines 1A, Change Request, and 2. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
26 | New Issue | The coastal erosion assessment refers to the National Coastal Erosion Risk Mapping (NCERM) project data, which has been superseded by NCERM2. The Applicant should consider the NCERM2 project data to inform detailed design/future assessments of coastal change. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change |  | We would welcome confirmation that the Applicant has incorporated the most recent NCERM data into their marine physical processes EIA.
27 | New Issue | In [REP1-033] it is stated that this ES chapter has been ‘updated in response to Relevant Representations from various stakeholders and to incorporate information from Application Document 9.13 Pegwell Bay Construction Method Technical Note.’ Please note, however, that it is difficult to identify where changes have been made to the ES chapter, apart from Sections 1.7.6 and Table 1.18. We do, however, note that Figures 6.4.4.1.13 and 6.4.4.1.14 have been added to [REP1-010]. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay Construction Method Statement. |  | No change.
28 | New Issue | Additional mitigation measure MPE06 - Natural England advise that a similar commitment to MPE06 should be adopted for the Kent landfall through monitoring of change in the intertidal and shallow subtidal areas, in particular where protection is planned to be placed at the HDD exit pits. Commitment MPE05 [REP1-103] ensures depth of burial monitoring surveys will be undertaken post installation. Natural England advises that the same commitment should be made for Pegwell Bay. Additionally monitoring to validate ES predictions regarding changes to nearshore seabed morphology (and associated flow dynamics), seabed recovery, and to ensure there are no unexpected changes to intertidal/shallow subtidal morphology |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change.
29 | New Issue | Figure 6.4.4.1.11 Sheet 1 (Offshore Seabed Surficial Geology Overview Sheet) identifies a number of Annex I – Reefs and Annex I – Sandbanks, including Annex I sandbanks not in a designated site. It is unclear whether these features may be affected by cable protection measures placed on or adjacent to them. The Applicant should provide an indicative map of proposed cable protection locations relative to these features to inform the impact assessment. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change.
30 | New Issue | Three different cofferdam construction options are proposed including prefabricated filled tanks, a barge with moonpool grounded after positioning, or piled sheeting. However, the Marine Physical Environment chapter [REP1-052] states that either multiple or one large moonpool or piled cofferdam will be constructed. The WCS cofferdam construction parameters should be clearly defined and made consistent across the relevant documents. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. Please see our advice in Appendix J3a [REP3A-028] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
31 | New Issue | The impact pathways and maximum design scenario (MDS) parameters for the temporary HDD working area, pulled and pushed duct installation methods have not been considered or assessed in [REP1-052], the Marine Physical Environment chapter. This should be addressed by the Applicant. |  |  |  | New issue identified following review of documents submitted at Pre-Deadline 1 and Deadline 1 and added to the R&I log for Deadline 3 submission. |  | No change. Please also see Appendix J3a [REP3A-028] to our Deadline 3a response, which includes comments on the Pegwell Bay landfall. |  | No change. We advise that all construction impacts relevant to inshore seabed morphology and designated coastal feature receptors need to be identified and MDSs quantified. Furthermore, MDS for increases in SSCs, water column turbidity, and associated deposition of disturbed sediments should include not only MDS width, length, area, but also volume and duration of activity. Please see our advice in Appendix D4 to our Deadline 4 submission.
32 | New Issue | The impact pathways and maximum design scenario (MDS) parameters in relation to the sandwave clearance works are unclear within the [REP1-052], the Marine Physical Environment chapter or within Chapter 6.11, the Marine Conservation Zone Assessment. This should be addressed by the Applicant. |  |  |  | Further information is required in relation to the proposed sandwave clearance activities due to the ambiguity around the project design MDS. The following issues need to be considered and clarified including (a) the MDS location of the sandwave clearance works; (b) the impact pathway for physical environment receptors; (c) the location and impacts in relation to protected sites. |  | No change. Please also see Benthic Appendix E3a [REP3A-027] submitted at Deadline 3a |  | No change. Please see our advice in Appendix E3a [REP3A-027] to our Deadline 3a submission and Appendix D4 to our Deadline 4 submission.
33 | New Issue | Cumulative effects have not been assessed. This is particularly important for Goodwin Sands MCZ and Pegwell Bay (and its designated features). | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission.
34 | New Issue | Potential risk of groundwater contamination discharging into coastal waters from the former Pegwell Bay hoverport site now incorporated into the Order Limits. | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission.
35 | New Issue | The EIA needs to be updated to consider impacts due to extension to the Order Limits to include the Hoverport and access across the intertidal area at Pegwell Bay. This includes updating the baseline and impact assessment. | [7 empty] | Please see our advice in Appendix D4 to our Deadline 4 submission.
36 | New Issue | Impacts to designated chalk features and subtidal chalk due to the proposed project need to be considered. Further detail is needed from the Applicant including consideration of how impacts can be avoided, mitigated etc.

## E - Benthic Ecology
Point | Point Number(s) from Appendix E RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix E - Benthic Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | E1 | The Environmental Statement should be updated to consider all potential pathways of effect on intertidal and subtidal benthic habitats |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
2 | E2, E12 | Maximum Design construction footprints should be reviewed and updated to remove any ambiguity. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
3 | E3, E14, E37 | Natural England advises that benthic mitigation measures avoid, reduce, mitigate impacts to the most sensitive Section 41 NERC Priority Habitats. The Applicant should consider all mitigation options, including bundling of the export cables for each project and micro-siting of cables to ensure permanent impacts to Section 41 Habitats are avoided/reduced wherever feasible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
4 | E4, E32 | The Applicant has not committed to removing cable protection at the Project's end of life. Natural England strongly advises that commitment is secured through DCO for the removal of all infrastructure at the time of decommissioning, both within and outside of designated sites. An Outline Decommissioning Plan should be provided at the consenting phase to detail the approach to decommissioning. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
5 | E5, E24 | The Environmental Statement should be updated with an appropriately considered and evidenced assessment of the sensitivity of all benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification required around the assessment of impacts (including Coralline Crag). |  | No change
6 | E6, E25 | All benthic receptors within the Zone of Influence should be characterised and assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
7 | E7 | Further assessment of impacts from sandwave levelling on benthic receptors is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
8 | E8, E52 | The Applicant should provide a transparent justification for the Worst-Case Scenario quantification of benthic impacts both within, and outside designated sites as a result of cable protection placement. Additional information within the Scour and Cable Protection Management Plan is also required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
9 | E9 | With regard to cable protection and the decommissioning of cable protection, we would welcome further refinement of the Rochdale envelope in order to minimise environmental impacts. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
10 | E10 | Mitigation measures should be adopted to differentiate between inside and outside of designated sites unless a precautionary approach will be taken to all installation and operation activities within the assessment. Impacts from all proposed types of external cable protection should be addressed to refine options and allow for a realistic WCS to be assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
11 | E11, E15 | There is insufficient detail on proposed O&M activities relating to the placement of scour prevention / cable protection over the lifetime of the project. Necessary detail should be provided on the parameters for O&M activities including rationale on how total figures have been determined. Further quantified detail should be provided on the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
12 | E13, E22 | Higher-level consideration of the UXO clearance activities should be included within MDS. UXO clearance activities both within and outside of designated sites should be provided to sufficiently quantify WCS to benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
13 | E16, E36, E54 | Mitigation measures should be adopted by the Applicant to mitigate for cable route preparation activities and disposal activities. Disposal options should be explored, sediment disposal should match local sediment types to avoid altering habitat character within 1.5km of the Offshore Scheme. A fall pipe should be used when dredging poses a risk of increased suspended sediment affecting sensitive sites or priority habitats. Cleared boulders adjacent to Goodwin Sands MCZ should be redistributed in similar habitats to avoid unnatural clustering and maintain baseline conditions. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
14 | E17 | Storage options for material from landfall exit pits should be explored to minimise impacts within Sandwich Bay & Hacklinge Marshes SSSI. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
15 | E21, E23 | Applicant to clarify how individual Sabellaria spinulosa count data has been considered or what thresholds have been used to determine the potential for biogenic reef. A precautionary approach to data interpretation is required to inform a WCS of the extent & distribution of S. spinulosa reef within the Offshore Scheme. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence is required to support the conclusions of the ES that no Sabellaria spinulosa reef was observed by subtidal surveys within the Offshore Scheme. |  | No change
16 | E24 | Natural England disagrees that Blue Mussel Beds and Sabellaria spinulosa reefs have 'low sensitivity' to the temporary physical disturbance impacts during construction. The Environmental Statement should be updated with an appropriately considered assessment of the sensitivity of receptors and significance of impacts on all habitats listed under Section 41 or the NERC Act |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission
17 | E25 | The EIA fails to consider potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures”. All benthic receptors within the Zone of Influence should be sufficiently characterised to enable a robust evidence-based assessment. The ecological importance and rarity of peat, clay and chalk substrates should be properly considered and efforts made to avoid physical impacts where possible. Particularly where such habitats support rare and/or irreplaceable communities such as boring piddocks. If avoidance isn't feasible, the Applicant must demonstrate how impacts have been minimised. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
18 | E26, E41, E45 | The EIA does not consider the likely deposition impacts within Thanet Coast SAC and the assessment is lacking quantification and evaluation of impacts from elevated SSC and sediment deposition within Thanet Coast SAC during construction. The Applicant should update the assessment of potential impacts from SSC and deposition on Thanet Coast SAC Annex I reefs and sea caves and ensure all benthic receptors within the red line boundary and zone of influence are transparently and comprehensively assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that the sensitivity information for reef features within the Thanet Coast SAC to ‘Medium’ sensitivity to suspended sediment concentrations and deposition is updated in line with the precautionary principle, unless further evidence is provided regarding the specific biotopes present within the site, and that impacts are mitigated accordingly. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
19 | E27 | According to MarESA, all benthic receptors are highly sensitive to habitat loss and the EIA (where relevant RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Issues remain outstanding. Natural England advises that the EIA (and where relevant, RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
20 | E28 | Clarity is required regarding the extent and distribution of Blue mussel Mytilus edulis beds throughout the Offshore Scheme so that a robust review of the assessment can be made. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence and clarification of the presence and distribution of blue mussel beds is required to support the conclusions of the ES. Natural England also advise that pre-construction surveys to identify the presence and distribution of blue mussel beds across the Offshore Scheme should be secured through the In Principle Monitoring Plan (IPMP). |  | No change
21 | E29 | A figure presenting areas within the Offshore Scheme most likely to require cable protection; their spatial relationship to benthic baseline and proximity to designated sites and Section 41 Habitats of Principal Importance should be provided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England would welcome an updated figure to reflect the areas most likely to require all forms of cable protection, including remedial areas. |  | No change
22 | E30, E58 | The Applicant has made no strong commitment to avoid / microsite around sensitive benthic receptors. The adoption of mitigation measures via a Benthic Mitigation Plan should be considered to reduce/ avoid impacts to Section 41 Habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Whilst commitments to prepare a mitigation plan are welcome, the mitigation hierarchy should be followed which sets out that impacts should first be avoided wherever possible. Securing commitments to avoid sensitive features through micro-siting of the cable wherever possible would resolve this issue. |  | No change
23 | E31 | The extent of all benthic impacts from construction access / work areas, construction of exit pits or cofferdam installation at the Kent landfall has not been assessed within the EA Benthic chapter. We advise that the EIA and RIAA are updated to consider all impacts at landfall. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. However, issues remain outstanding please see Appendix J3A [REP3A-028] of our Deadline 3a submission
24 | E33 | The Applicant has not specified the type of cable protection to be used, nor considered the limitations some methods present with successful decommissioning or likelihood of degradation over time. Due consideration should be given to cable protection engineering options that favour the greatest likelihood of successful removal at the Project's end of life. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification is required around cable protection location, type and the impact pathways, including further assessment of scour and secondary scour. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
25 | E35 | The EIA lacks transparency in how the sensitivity, value and extent of benthic features have been assessed. Not all relevant biotopes within the zone of influence have been properly considered and it is unclear if assessments are based on the worst case sensitivities described. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
26 | E38 | An Offshore IPMP should be developed and submitted into examination to include monitoring residual concerns in relation to protected habitats and those of conservation importance. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
27 | E39 | Natural England cannot agree with the conclusions of the EIA without a comprehensive assessment of all benthic impacts. We require: - A ecologically relevant understanding of the likely impacts of SSC, deposition and changes to supporting processes from cable protection on features of Goodwin Sands MCZ. - A clearer baseline and quantitative assessment of potential permanent loss of Section 41 NERC Habitats of Principal Importance, especially if avoidance measures are not committed to. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
28 | E41 | We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
29 | E43 | While we acknowledge the limited scale of habitat loss, we note that permanent loss of supporting habitat for the Outer Thames Estuary has not been assessed. We advise permanent loss of SPA features' supporting habitat should be screened into the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
30 | E44 | No mitigation has been proposed for cable protection within or adjacent to designated sites and habitats which support mobile features. Where possible cable protection should avoid benthic supporting habitat. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
31 | E46 | We acknowledge that despite the need for further transparent assessment of certain impact pathways as highlighted by comments above, it is unlikely that compensation measures will be necessary as commitments to appropriate mitigation measures are possible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
32 | E47 | The current assessment lacks appropriate quantification and evaluation of impacts from SSC and sediment deposition within nearby MPAs during construction. We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
33 | E48 | Natural England requires confirmation that no permanent loss is likely within MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change |  | No change
34 | E49, E34 | The Applicant has not considered the potential for secondary effects of cable protection adjacent to Goodwin Sands MCZ. A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Goodwin Sands MCZ, followed by secured monitoring via a deemed Marine Licence and an In-Principal Monitoring Plan to determine whether residual impacts are as predicted. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
35 | E50 | We highlight the absence of designated anchoring areas to minimise seabed disturbance and advise careful selection of anchoring zones to avoid impacts to sensitive habitats or features. We advise impact assessments of cable installation vessels (jack-up barges or cable laying barges with spud legs) and operation and maintenance activities is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
36 | E53 | Natural England advises against the use of grout bags adjacent to Goodwin Sands MCZ, unless filled with locally sourced sediment similar to that within the placement footprint (due to potential degradation of bags over time altering sediment character). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change
37 | E52, E55 | Natural England is unable to agree with the MCZ assessment conclusions without further evidence and assessment, and maintains that there is reasonable scientific doubt regarding the hinderance of Conservation Objectives (alone or in-combination) of Goodwin Sands MCZ, Kentish Knock East MCZ and Thanet Coast MCZ to be hindered both Alone and in-combination. Particular regard should be given to commitments to remove all cable protection laid directly adjacent to the Goodwin Sands MCZ boundary. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
38 | E57 | Further information is required to inform a review of the impact assessments, until then, there remains reasonable scientific doubt of the nature of impacts to the intertidal features of Sandwich Bay to Hacklinge Marshes SSSI |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change
39 | New Issue | Concrete mattresses have the potential to provide suitable substrate for colonisation by INNS. Natural England query whether use of a moonpool or prefabricated cofferdam [REP1-108] may also have the potential to introduce INNS at the Kent landfall and, in turn, present a potential impact pathway to designated site features. Clarification needed. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change
40 | New Issue | Natural England remains uncertain as to the level of recoverability and timeframes to do so where compression impacts upon mudflats occur | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change
41 | New Issue | Documents should be updated to reflect the highly sensitive nature of soft rock habitats abrasion and physical loss. Every effort should be made to avoid physical impacts to these habitats where possible. This is particularly the case where habitats support rare and/or irreplaceable communities such as boring piddocks. Where impacts cannot be avoided, we advise that evidence will need to be presented to demonstrate how impacts has been minimised as much as possible. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change
42 | New Issue | Further to our Relevant Representation advice [RR-3290], we note that all three HDD exit options appear to be located in areas where Coralline Crag is present yet there is no assessment of potential impacts on the Coralline Crag due to the HDD or cable installation at landfall. Further consideration of the locations requiring cable protection is required to inform potential impacts to sediment transport and benthic receptors. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change
43 | New Issue | Justification is required for why the required quantity of rock backfill has increased dramatically. Further information should be provided on where this rock backfill will be placed and the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. Further clarification is also required on the details of cable protection anticipated. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] our Deadline 3a submission |  | No change
44 | New Issue | Clarification is required as to why the text securing up to date INNS training, biosecurity measures and embedded mitigation measures has been removed. Removed text also includes the requirement to report suspected INNS and, if necessary, take action to control present INNS. No justification is provided for why these measures have been removed, which could increase the risk of INNS being spread or introduced by the project. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change
45 | New Issue | The standard best practice mitigation measures should be adopted where impacts from sandwave levelling could impact within MCZs and/or on NERC Habitat features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission and Appendix D3 [REP3-118] to our Deadline 3 submission. |  | No change
46 | New Issue | The commitment to the Suffolk Coast HDD should be amended so that the final HDD management plan is agreed with the regulators in consultation with the relevant SNCB, rather than it be for our information only (as per point 59 of [REP 1-103]. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change
47 | New Issue | There should not only be a commitment to agree a mitigation plan for NERC habitats in consultation with relevant SNCB prior to construction, but that unless agreed otherwise impacts to theses habitats are avoided. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
48 | New Issue | All monitoring requirements/hypotheses should be included in an Offshore IPMP at the time of consent. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change
49 | New Issue | Further interpretation of the findings of REP2-035 Geophysical and Geotechnical Report is required to demonstrate where cable protection is mostly likely to be needed and once this is known undertake an assessment of the potential direct/indirect impacts from cable protection on designated sites features, irreplaceable geological features, and NERC habitats. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change

## F - Marine Mammals
Point | Point Number(s) from Appendix F RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix F - Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | F1, F6 | Worst Case Scenario. It remains unclear if precautionary estimates have been considered. Clarity is needed in the wording to demonstrate how a precautionary approach has been adopted in addition to use of updated survey data. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, it is stated in paragraph 4.4.17 that "The criteria for assessing effects and residual significance are presented in Application Document 6.2.1.5 Part 1 Introduction Chapter 5 EIA Approach and Methodology." [APP-046] Natural England currently do not have access to this document so it is unclear if this issue has been properly addressed. |  | No change |  | No Change
2 | F2 | The assessment should be updated to consider peak abundances for each species as representative of the WCS. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The seasonality of the peak abundance and density estimates for each marine mammal species used in the assessment is not clearly stated. Natural England are therefore unable to determine if this issue has been addressed throughout the assessment. Further information from the Applicant regarding the seasonality of the peak abundance and density estimates for all species used to represent the WCS would clarify this. Uncertain if issue has been properly addressed. |  | No change |  | No Change
3 | F3 | Natural England cannot currently agree with the conclusions of the EIA for the reasons outlined below see comments F12-F21 |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England notes that only minimal changes have been made in the EIA following our advice, thus we maintain our original advice. |  | No change |  | No change
4 | F4, F33 | Natural England cannot currently agree with the conclusions of the HRA for the reasons outlined below. The HRA should be revisited once outstanding issues with assessment methodologies have been addressed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England do not see any evidence of the changes in the assessment. In-combination assessment is particularly poor and has not been improved at all. Specifically, to assess whether there will be significant noise disturbance within a harbour porpoise SAC, the applicant needs to calculate the total area from which the harbour porpoise would be displaced using the latest EDRs (2025). Noise disturbance within an SAC from a plan/project, individually or in combination, is considered to be significant if it excludes harbour porpoises from more than: 20% of the relevant area of the site in any given day; or an average of 10% of the relevant area of the site over a season. Please consulate the Guidance for assessing the significance of noise disturbance against Conservation Objectives of harbour porpoise SACs (England, Wales & Northern Ireland). |  | No change |  | No change
5 | F5 | The Environmental Statement (ES) states that the Berwickshire and North Northumberland Coast SAC is designated for harbour seal. This is incorrect, this SAC is designated for grey seal. Wording should be updated |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The issue is resolved.
6 | F8 | The assessment should be updated to consider abundances of species within the study area in the winter months and the highest abundances taken forward to assessment as representing the WCS |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | It is now acknowledged that the peak abundance of harbour porpoise within the order limits is likely to be in the winter months, rather than summer. However, it is unclear as to if this has been reflected within the marine mammal abundance and density tables. Further information from the applicant regarding the seasonality of these peak abundance and density estimates for all species would clarify this. Uncertain if issue has been properly addressed. |  | No change |  | No change
7 | F9 | Both SCANS III and SCANS-IV are referenced as the source used for abundance and density estimates. Clarity is needed on the data used to estimate abundance in table 4.14. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
8 | F12 | Heinanen & Skov (2015) should also be included in the data used in the assessment, particularly for harbour porpoise and HRA. Include Heinanen & Skov (2015) in the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
9 | F13 | A range of harbour porpoise abundance estimates and densities are provided here for various management units and SCANS blocks, but it is not clear from the table or accompanying text which figures have been taken through to inform the assessment. This is also the case for all other species of cetacean and pinniped. Please provide clarification as to which figures have informed the assessment |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
10 | F14 | Table 4.18 presents the hearing groups presented in Southall et al, but the assessment uses the metrics found in NMFS (2018), so it is not clear why the hearing groups in NMFS (2018) haven’t been used. Please provide clarification of the functional hearing groups used in the assessment and ensure one set of criteria is used consistently throughout. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
11 | F15 | There is no information presented regarding the modelling that was presumably undertaken to generate the figures presented in Table 4.20. Therefore, Natural England cannot be sure the appropriate model type or parameters have been used in the assessment. Please provide further details regarding any underwater noise modelling that was undertaken during the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | Natural England expects the project to have undertaken underwater noise modelling to accurately predict the impacts of underwater noise. The outputs of this modelling will inform the impact ranges for the noisy activities planned for this project and therefore are essential for assessing the impacts from the project on marine mammals. No information has been provided to show evidence of this modelling. Natural England expects to see an underwater noise modelling report with details of the methodology and outputs from the modelling to be incorporated into the impact assessments.
12 | F16, F28, F29, F30 | It is not appropriate to use harbour porpoise as a proxy for all other species, including pinnipeds, when separate injury criteria are presented in the NMFS (2018) guidelines. Impacts to seal species and their respective designated sites should be carried out separately from the assessment of impacts to harbour porpoise. Account should be taken of the different hearing ranges and sensitivities of different species within the assessment. As stated above, the SELcum metric from the modelling should be used to inform impacts to designated sites, not just the SEL. Impacts to species, particularly from PTS, should be assessed using the SELcum metric. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | Natural England agrees with the Applicant's response to our comments on REP2-014 and this is now resolved
13 | F17 | It is not appropriate to use A-weighted sound levels (used for human hearing) in an assessment of the impacts of airborne noise on seals, especially when an M-weighted sound levels for phocids in air is presented in Southall et al 2019. The M-weighted sound levels for phocids in air should be used to assess the impacts of airborne noise on seals. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Correction made in Document 9.49 Seals and Airborne Sound Disturbance Technical Note. [REP1-122] The issue is resolved. |  | No change |  | M-weighted sound levels modelling has now been under taken and presented in document 9.49 [REP1-122] with updated noise information provided in 9.13 [REP2-012]. (Please note this is only in relation to airborne noise disturbance to seals and the above issue regarding underwater noise modelling is still unresolved). The planned HRA update at Deadline 5 should fully resolve this issue. NOTE: This was incorrectly marked as resolved at Deadline 3
14 | F18 | Natural England advises that the predicted zone of PTS as described by the SELcum metric in Table 4.20 should inform the mitigation zone, not the outdated standard 500m described in the 2017 JNCC guidelines. The JNCC guidelines for minimising the risk of injury to marine mammals from geophysical surveys have been updated as of February 2025 and are available in draft form on the JNCC website. These guidelines state that the mitigation zone should be a minimum of 500m. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | The updated 2025 JNCC guidance has been referenced, however it should still be clarified in the wider text that a 500m mitigation zone should be used as a minimum. Issue partially addressed, though further clarification is needed before issue is downgraded. |  | No change |  | Natural England agrees with the Applicant's response to our comments on REP2-014 and this is now resolved
15 | F19 | The pre-shooting search should be 30 minutes in duration, not 20 minutes as stated here. Please refer to the updated JNCC February 2025 guidelines for minimising the risk of injury to marine mammals from geophysical surveys. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
16 | F20 | A Marine Mammal Mitigation Protocol (MMMP) should be produced that outlines the procedures to be followed to correctly implement the appropriate mitigation as outlined in the JNCC 2025 guidelines for minimising the risk of injury to marine mammals from geophysical surveys. An outline MMMP should be provided to support the application and a MMMP secured through condition in the DCO/dML. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | Natural England reviewed Document 7.5.11 Outline Marine Mammal Mitigation Plan [REP1-025] As acknowledged by the Applicant, this is an early stage version and will be updated and refined throughout the course of the project, following advice from Natural England. Some issue addressed, though further advice will be needed. In general, The purpose of the MMMP is to serve as a concise, user-friendly manual outlining the specific mitigation measures that must be implemented in the field for activities that may impact marine mammals. To maintain clarity and focus, sections on legislation, project details unrelated to the MMMP, and general marine mammal descriptions should not be included in this document, as they are more appropriately placed in the Marine Mammal EIA chapter or other supporting materials. Instead, the MMMP should concentrate on clearly presenting mitigation measures, operational procedures, observer responsibilities, and reporting requirements. The MMMP represents the practical outcome of the assessments conducted during the EIA process. |  | No change |  | No change
17 | F21 | There is no quantification of the potential impacts to marine mammal species, i.e. how many animals could potentially be impacted, despite abundance and density data being provided. Therefore, Natural England are not currently able to agree with the assessment conclusions. Issues outlined here regarding the methodology for assessment should be resolved and the assessment updated accordingly. After further review of relevant representations the risk rating has been upgraded to red. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change
18 | F23 | Natural England are content that the listed projects can be scoped out of the cumulative impact assessment based on the justification provided.
19 | F31, F32 | It is not sufficient to state that delivery of projects in-combination can be managed without an adverse in-combination effect without providing any information as to what the scale of the impact from all these projects in-combination is predicted to be or how these impacts will be managed. There is no consideration of in-combinations impacts to marine mammals in this section. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. |  | No change |  | No change

## G - Marine Ornithology
Point | Point Number(s) from Appendix G RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix G - Marine Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | G1, G7 | Natural England advises a timing restriction is needed on construction activities from 1st November to 31st March inclusive, irrespective of whether other developments occur, to mitigate impacts on red-throated diver within the Outer Thames Estuary (OTE) SPA . |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Partial commitment to the seasonal restriction has been made but Natural England emphasise the importance of avoiding impacts throughout the over-wintering period. See Appendix G4 to our Deadline 4 response for full details (pending review of documents submitted at Deadline 3).
2 | G2, G4 | Based on the information submitted Natural England cannot rule out AEOI on the OTE SPA. We recommend that the November to March timing restriction on cable construction activities is widened to include pre-lay grapnel run, O&M activities (including surveying) and decommissioning phases. As a minimum, adherence to Natural England’s best practice protocol will be required for these phases but depending on the proposed level of activity in each phase, that may not be sufficient. To progress this matter we recommend the Applicant provides additional detail on anticipated frequency , duration and extent of such works. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Partial commitment to the seasonal restriction has been made but Natural England emphasise the importance of avoiding impacts throughout the over wintering period. We continue to advise that the proposed mitigation may not be a sufficient commitment to avoid disturbance/displacement effects during the sensitive winter period and the project may still contribute to in-combination effects.
3 | G3, G10 | We note the applicant's intention to consult NE before pre-lay grapnel run during January-March. Should some O&M works be considered necessary during the November-March period (e.g. in emergency situations), a report detailing the nature of the event, and the specific location, duration and extent of any works undertaken, including associated vessel transits, may be requested to quantify potential impacts and for assessment of future cumulative/in-combination effects from similar projects. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
4 | G5 | The Applicant states that RTD numbers in the OTE SPA are declining by February. Evidence from both the January and February 2013 (APEM, 2013) and the early and late February 2018 surveys (Irwin et al, 2019) of the OTE SPA suggest that RTD numbers appear to build in the late winter period rather than decline. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
5 | G8 | In order that a meaningful assessment or WCS impacts can be made, a higher-level consideration of the UXO clearance activities included within MDS is needed. Information from neighbouring projects can be used as a proxy and commitments to mitigation measures secured. To provide a sufficiently broad WCS quantification of benthic impacts we also advise that UXO clearance activities both within, and outside, designated sites should be provided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | Natural England welcomes the Applicant’s commitment to continue engagement with both Natural England and the MMO to ensure that the consenting approach for UXO activities is appropriate and that the assessments supporting the marine licence applications fully capture the potential effects of the Proposed Project. |  | QA note: Trimmed.
6 | G9 | Based on the information and mitigation submitted within the application we cannot rule out an AEOI on the OTE SPA. To determine the required level of mitigation, the Applicant is recommended to provide a detailed spatial & temporal analyses of anticipated works for pre-lay grapnel run, O&M activities and decommissioning, and to quantify and assess the implications for using of the SPA by RTD. The required elements are set out in detail within our Relevant Representations. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
7 | G11 | The Applicant should update their cumulative impacts assessment to account for smaller impacts that have, at present, been scoped out. Also to consider the ongoing impacts of London Array offshore wind farm. Further, a more detailed consideration of the potential interactions between Five Estuaries, North Falls and Sea Link through the project stages is needed to inform mitigation measures. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
8 | G12 | Natural England are unable to agree with the conclusions of the EIA until a comprehensive assessment of all impacts are considered, including a demonstration that sufficient mitigation is proposed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
9 | G16 | Natural England are unable to agree with the conclusions of the HRA until a transparent and comprehensive assessment of all impacts are considered, including a demonstration that sufficient mitigation is proposed |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. |  | No change.
10 | G17 | The seasonal restriction for cable installation should be updated to include a 2km buffer around the Outer Thames Estuary SPA. See Deadline 4 response Appendix G4. |  | New issue |  | New issue |  | New Issue |  | Issue raised at Deadline 4.

## H - Suffolk LVIA
Point | Point Number(s) from Appendix H RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix H - Suffolk & Essex Coast and Heaths Designated Landscape - Landscape Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3A | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | H1 | Without further information, Natural England is concerned that the project may have a significant impact (in EIA terms) on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. Seem at H2 so greyed out
2 | H2 | Natural England is concerned about the significant (in EIA terms) cumulative impact that the project’s construction phase will have on the statutory purposes of the Suffolk & Essex Coast & Heaths National Landscape and its setting, and the Suffolk Heritage Coast. We note that no compensation is proposed, and it is not clear how the project has sought to further the purposes of the Suffolk & Essex Coast & Heaths National Landscape. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change. See Appendix H4 of Natural England's Deadline 4 submission for detailed advice.
3 | H3 | The assessment in Table 2.1 should be expanded to ensure that it can be understood with respect to impacts on the specific Suffolk and Essex Coast & Heaths National Landscape Indicators. Natural England are expecting significance of effects to be reported at this special quality scale so it is clear which part of the baseline may change. Natural England are unclear which special qualities of the Suffolk & Essex Coast & Heaths National Landscape will be affected by this proposal, and we advise that this information is essential to the assessment. For example The “intactness of the landscape” SQ specifically refers to the important of acid grassland and heath. Natural England advise that impacts to this SQ are clearly assessed. |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
4 | H4 | Further baseline information is required to clarify the extent and habitat type which are impacted by the cable route within the Suffolk & Essex Coast & Heaths National Landscape and its setting. This information is required to understand the scale of impact on very highly susceptible features of the landscape, such as acid grassland. Table 2.1, Document: 6.3.2.1.C highlights that acid grassland is an important defining element of natural beauty for the Suffolk & Essex Coast & Heaths National Landscape. There is also insufficient evidence used to justify that the impacts to acid grassland are small scale Natural England does not agree that impacts in relation to small geographical extents can moderate impact to statutory purposes. Information should indicate the exact locations for trenched and trenchless cable construction. This information should be used to inform a clear justification on the use of open cut techniques within the Suffolk & Essex Coast & Heaths National Landscape. In addition it is not clear if the 4.05 ha of land within the extended golf club will be able to be reinstated. Will this area remain in operation as a golf course following reinstatement? It is not clear how the golf course proposals have been considered in combination with the proposal. Natural England advise that the Applicant provides detail on how the location of the enhancement area for acid grassland within the Suffolk & Essex Coast & Heaths National Landscape was chosen (also see H12). We note that there are two types of acid grassland defined in the management plan, this is lowland dry and also lowland dry + heathland. It is not clear which habitat type is impacted, and Natural England advise that this is clarified (this information cannot be worked out from the Phase I mapping). |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
5 | H5 | Clarity is needed on: (1) the methodology used to assess impacts on the setting of the Suffolk & Essex Coast & Heaths National Landscape (2) the conclusions made in terms of impacts to the setting of the Suffolk & Essex Coast & Heaths National Landscape (3) Clarification is required on what the impact on users of the Suffolk Coast Path is assessed to be. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
6 | H6 | Natural England remains unclear on the realistic anticipated overall timeframe for construction and reinstatement (of soils, habitats and hedgerows) in relation to works within the NL and its setting, and we advise that these details are clearly set out and evidenced. The Applicant should set out how much habitat will be affected by the cable route, where habitat will be reinstated, and the timescales involved for the works (for construction and reinstatement). It remains unclear which areas will be impacted and reinstated. For example, will the area of the golf course disturbed and reprofiled (4.05 ha) impact any reinstatement potential in this area? The magnitude of landscape effects (as assessed) is dependent on the short duration and reversibility of works, which should be evidenced. We advise that the complexity of this habitat some of which is priority habitat and added risks of reinstatement, including time to reach functionality should be evidenced in the LVIA. NE advises that the Applicant needs to set out information on the recoverability of habitats post-construction, highlighting any risks to this. This information should include the justification used to assume full reinstatement by year 15, and in line with the mitigation hierarchy, clear justification for why open cut trenching methods within the Suffolk & Essex Coast & Heaths National Landscape and its setting cannot be avoided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
7 | H7 | Multiple major projects will combine to cause significant adverse impacts on the statutory purpose of the Suffolk & Essex Coast & Heaths National Landscape. This conclusion of adverse and significant effects on the Suffolk & Essex Coast & Heaths National Landscape and Suffolk Heritage Coast requires further consideration. We advise that further assessment (in alignment with GLVIA) is required (used) to underpin this conclusion (is provided), and that impacts are reported in terms of impacts on the Special Qualities of the Suffolk & Essex Coast & Heaths National Landscape, and in relation to information on anticipated construction schedules. Natural England advises the Applicant engages with all parties on how compensation can be achieved, in consultation with the Suffolk & Essex Coast & Heaths National Landscape partnership and Natural England. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change
8 | H8 | The Applicant should provide further information to support the assessment of impacts to Suffolk Heritage Coast, and the conclusion of minor adverse construction effects. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at 1A, change request and 2. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
9 | H9 | Any replacement planting should reflect the Landscape Character of the area. This should be specifically clarified within the outline vegetation reinstatement plans. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change, pending review of documents submitted at 1A, change request and 2. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
10 | H10 | The commitments register should include contingency measures should reinstatement plans fail, or should reinstatement not be achievable within the timeframes stated. This is particularly important for acid grassland, and for this habitat, the commitments register should reflect the contingency measures described in 6.7.3 of the oLEMP. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change. Further evidence is required. See Appendix H3 [REP3-120] for detailed comments |  | No change |  | No change
11 | H11 | Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023. It is not clear how the project proposes to further the purposes of the national landscape. Natural England refer the developer to Guidance for relevant authorities on seeking to further the purposes of Protected Landscapes - GOV.UK for further advice. The developer may also wish to speak to the National Landscape team for further advice on possible opportunities. The guidance refers to avoiding harm, and contributing to conservation and enhancement. We would expect the duty to be applied (where reasonably practical) to each stage of the mitigation hierarchy to achieve the conservation aim of the duty. The guidance also refers to enhancement and therefore we would advise that this aspect also needs to be considered to 'further the purpose' of the designation. We have advised that the mitigation hierarchy applies to each stage of the assessment of impact. We advise that a clear justification is required detailing why avoidance of impact through employing trenchless crossings in the Protected Landscape, has not been pursued. Natural England understand that 6ha of acid grassland enhancement and creation are being put forward to satisfy the new duty, in relation to the direct temporary construction impacts on acid grassland within the protected landscape. Natural England advise that the Applicant provides clarity and justification as to whether the proposals are to conserve and enhance, and how the duty has been applied at each stage of the mitigation hierarchy. |  | No change, pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. Text has been expanded upon to improve clarity. |  | No change. See Appendix H3 [REP3-120] for detailed advice. |  | No change |  | No change
| H12 | From the information provided it is not clear how the 6Ha proposals seek to further the purposes of the Protected Landscape. The current baseline of the 6Ha enhancement area appears to include priority deciduous woodland habitat and biodiversity interest, it is not clear how the enhancement proposals may themselves impact on an area of existing value for biodiversity. It remains unclear what the existing baseline pH is for this area and how the applicant has considered impact pathways from the adjacent pig farm and cultivated land on any potential for reinstatement of acid grassland in this location. It is not clear which Special Qualities and Indicators will be targeted by the acid grassland enhancement. We advise that an explanation of how 10 years is a sufficient length of time in which to manage this area to a sufficient standard to compensate for direct impacts to acid grassland in the Protected Landscape. We continue to advise that in accordance with the mitigation hierarchy and the importance of this habitat landscape in both landscape, and ecological terms, the project should avoid sensitive habitats and employ trenchless techniques in this area.
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removing refs amending furthering the purpose ref the purpose