## Version History
Version History
Date | Issue | Status | Description / Changes
March 2025 | A | Final | For DCO submission
October 2025 | B | Final | As requested for Deadline A
November 2025 | C | Final | As requested for Deadline 1
November 2025 | C Ver. 2 | Final | Changes and additions are only in reference to the Change Request
January 2026 | D | Final | As requested for Deadline 3
February 2026 | E | Final | Updates to an Excel spreadsheet. As requested for Deadline 4
March 2026 | F | Final | As requested for Deadline 5
April 2026 | G | Final | As requested for Deadline 6
April 2026 | H | Final | As requested for Deadline 7

## Appendix B- Schd. Negotiations
Appendix B: Schedule of Negotiations with Land Interests
1.1 Progress of negotiations with affected persons
The table below shows the progress of negotiations with affected persons within the Order land. Please note that the table is correct at the date of the 29th April 2026.
Table 1.1 Schedule of Negotiations with Land Interests
AP ref no. | Land Interest | County | Representation Submitted | Relevant Representation Number | Link to Submitted Relevant Representation on the PINS website | Written Representation Number | Link to Submitted Written Representation on the PINS website | Interest | Sheet Number & Land Plot Number | Description of rights sought | Highways Subsoil Interest | Agreement Needed | Agent | Summary of Negotiation Status - Submission - 25.03.2025 | Summary of Negotiation Status Deadline A and Deadline 1- 08.10.2025 & 18.11.2025 | Summary of Negotiation Status Deadline 2 - 9.12.2025 | Summary of Negotiation Status Deadline 3 - 09.01.2026 | Summary of Negotiation Status Deadline 4 - 10.02.2026 | Summary of Negotiation Status Deadline 5 - 10.03.2026 | Summary of Negotiation Status Deadline 6 - 13.04.2026 | Summary of Negotiation Status Deadline 7 - 29.04.2026 | Occupier Consent | Completed | Refused
39 & 60 | Jean Veronica Spanton & Christopher John Spanton | Kent | Yes | RR-5840 | RR-5840 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006506 |  |  | Freehold | Kent - 4/26 4/27 | Class 9. Temporary Use for Access | No | Yes | BTF Partnership | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. | 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. |  | 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | 10.02.2026 – The Applicant's Agent has been engaging with the landowner’s agent regarding the Heads of Terms and has provided additional clarity on the use of the rights being sought on both the 8th January 2026 and the 22nd January 2026. The landowner’s agent hasn’t yet provided any detailed response on any of the other points in the Heads of Terms which remain outstanding. Their focus has been on the proposed use and commercials. The Applicant’s Agent continues to seek this feedback on the remainder of the terms. The Applicant's Agent responded on 9th February 2026 by email providing comparable evidence for the consideration offered. It is believed an agreement can be reached before the end of Examination. | 10.03.2026 - On the 2nd March 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation that the Heads of Terms, commercial elements aside, are agreed. The Applicant's Agent issued further revised Heads of Terms to the landowner's agent on 9th March 2026. No response has been received to date. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On the 9th March 2026, the Applicant's Agent emailed the landowner's agent with a revision of the Heads of Terms which further refined the rights sought to reflect the temporary nature of the access provisions. Additionally, the Applicant's Agent sought confirmation that the terms are in agreed form and requested further evidence regarding the commercial terms. On the 31st March 2026, the Applicant's Agent emailed the landowner's agent to confirm that no response has been received to any communications concerning the landowner since the 6th February 2026. It was confirmed by the Applicant's Agent that in order to address any queries or concerns their client may have, it is essential that the Applicant's Agent is provided with information regarding perceived issues with other aspects of the Heads of Terms including an evidenced position relating to commercial terms. On the 8th April 2026, the Applicant's Agent left a voicemail with the landowner's son requesting a call back to discuss the Heads of Terms. It is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On the 14th April 2026, the Applicant's Agent emailed the landowner's agent confirming that they would be contacting the landowner to discuss the Heads of Terms in the absence of a response. The landowner's agent responded on the 14th April 2026 providing a summary of the landowner's position and requesting a response on three points. The Applicant's Agent is working internally to provide responses to these and make adjustments to the Heads of Terms where possible to reflect their concerns. These points are as follows: 1. The duration of the agreement and the timescales for the required works themselves. 2. The nature of the rights granted versus the actual project requirements 3. The basis for the commercial payment The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
49 & 219 | Ian Stewart Chandler & Paul Stewart Dunn | Kent | No |  |  |  |  | Freehold | Kent - 2/47 2/50 2/51 2/52 2/53 2/54 2/55 2/59 2/60 2/63 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email on 20th January 2026. The Applicant's Agent has responded to those comments and sought confirmation from the landowner’s agent that the updated Heads of Terms can be issued in their final form for signature. On the 27th January 2026 the landowner’s agent sought an amendment to the plan to limit the extent of the rights being sought - this point remains in discussion but it is believed all other terms are agreed and an agreement will be reached by Deadline 5. | 10.03.2026 - Heads of Terms have been agreed in principle and the agreed form has been sent to the Landowner's agent for signature on the 26th February 2026. The Applicant's Agent have received the signed Heads of Terms from the landowner's agent on the 9th March 2026. | 13.04.2026 - Signed Heads of Terms were received from the landowner's agent on 9 March 2026. Legal drafting of the Option Agreement is ongoing | 29.04.2026 - Legal drafting of the Option Agreement is ongoing.
97 | Kent County Council | Kent | Yes | RR-2980 | RR-2980 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001249 | REP1A-059 | REP1A-059 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001578-F76E1F05E%20-%20Sea%20Link%20Joint%20Submission%20-%20ISH%20locations.pdf | Freehold | Kent - 1/1 2/83 3/3 3/4 3/5 3/10 3/12 3/13 3/14 3/15 3/16 3/19 3/23 3/24 3/25 3/26 3/27 3/29 3/30 3/33 3/34 3/35 3/36 3/37 3/40 3/81 3/84 3/85 3/87 3/93 3/96 3/97 3/97a 3/98a 3/100 3/101 3/102 3/104 3/107 4/2 4/3 4/4 4/11 4/12 4/13 4/19 4/20 4/21 4/22 4/23 4/24 4/26 4/28 6/6 | Class 1. Compulsory Acquisition of land Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Carter Jonas | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - The Applicant's Agent contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | 10.02.2026 - The landowner’s agent responded with queries relating to the number of cables proposed and other matters within the Heads of Terms on 21st January 2026. Revised Heads of Terms were issued to the landowner’s agent on 22nd January 2026. The landowner’s agent has provided a further mark up of the Heads of Terms on 26th January 2026, a response was provided on 29th January 2026. It is understood all points in the Heads of Terms are now agreed with the exception of the duration of the cable rights sought for the easement and commercial consideration. These points remain in discussion and it is believed an agreement can be reached before the end of Examination. | 10.03.2026 - Since Deadline 4 there has been engagement between the Applicant's Agent and the landowner's agent including emails and telephone calls on 5th February, 17th February and 3rd March 2026. The rights sought in the draft DCO and voluntary land agreements are in perpetuity. The landowner's agent is seeking a 30 year term which is not compatible with National Policy for Energy or National Grid Land Rights Strategy. Discussions continue in relation to the duration of the rights sought and commercial terms. It is understood that the remaining provisions within the Heads of Terms are agreed. Provided that the landowner's agent accepts the rights required are in perpetuity, a voluntary agreement could be reached by the close of Examination. | 13.04.2026 - The Applicant's Agent emailed the landowner's agent on 24th March and 31st March 2026 requesting an update on whether they have had further discussions with their client on the outstanding points in the Heads of Terms. The outstanding terms pertain to the duration of rights and the commercial terms. The Applicant's Agent has confirmed to the landowner that the voluntary rights being sought are in perpetuity which is in line with the rights being sought in the DCO. The Applicant's Agent called the landowner's agent on 8th April 2026 and left a voicemail which the landowner's agent responded to via email on the 9th April 2026. The email from the landowner's agent confirmed that they were still seeking further instruction from their client. The Applicant's Agent continues to engage and negotiate with the landowner's agent. It is anticipated that an agreement can be reached, however, it is unlikely to be before the end of Examination. | 29.04.2026 - The landowner's agent has not responded to the Applicant's agent with any further feedback on the Heads of Terms. On 24th April 2026, the Applicant' Agent left a voicemail message and sent a chaser email to the landowner's agent. The outstanding matters in relation to the Heads of Terms are the commercial elements. The landowner's agent confirmed on 27th April 2026 that they are still waiting for further feedback and instruction from their client in relation to the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
154 | Edward Martin Spanton | Kent | No |  |  |  |  | Freehold | Kent - 3/44 3/45 3/49 3/50 3/51 3/53 3/54 3/55 3/56 3/57 3/63 3/77 3/78 3/79 3/80 3/82 3/83 3/87 4/7 4/8 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 10.02.2026 - A Teams meeting was held on 14th January 2026, the landowner’s agent followed up the points discussed in an email to The Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026, this response also included clarification of the easement consideration. An email was received from the landowner’s agent on 27th January 2026, it is understood the principle outstanding point is in relation to restrictions on development within the cable easement. Further information is awaited from the landowner’s agent to enable this to be progressed and it is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - On the 18th February 2026, the landowner's agent provided the Applicant's Agent with further detail of the golf course expansion proposals. The Applicant and the Applicant's Agent are reviewing this information and are in the process of organising a meeting with the landowner's agent. At this stage, based on the information recently received, it is not possible to confirm if agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent had a Teams meeting with the landowner's agent on 18th March 2026, where the landowner's proposals for developing the land were discussed in detail to see how the two proposals can co-exist. The landowner's development proposals involve raising the ground levels up to 4m above the existing ground level. This proposed change to the ground levels could impact the Applicant's proposal, however, the Applicant confirmed their willingness to work with the landowner to provide more detailed design information at the meeting on the 18th March 2026. A revised drawing of the Transition Joint Bay will be provided to the landowner to allow adjustments to be made to the landowner's proposals, enabling both proposals to co-exist. A further meeting will be arranged once the drawing of the Transition Joint Bay has been provided to the landowner's agent. The landowner's agent and Applicant's Agent continue to progress matters constructively, however, due to the complexities of their development plans, Heads of Terms will not be signed before the end of Examination. The Applicant is working with the landowner's agent to draft a Statement of Common Ground to help resolve outstanding issues regarding the development proposals, it is expected that this will be submitted at Deadline 7. | 29.04.2026 - The Applicant's Agent followed up with the landowner's agent in relation to the draft Statement of Common Ground on 31st March 2026 to provide assurances that the Applicant is willing to work with the landowner to determine if their golf club extension development proposals and the Project proposals can co-exist. On 24th April 2026, the Applicant's agent has provided the landowner's agent with the revised drawing of the Transition Joint Bay and is setting up a meeting with the landowner's agent to progress their development proposals alongside the Project proposals. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
159 | Natalie Anne Brundenell | Kent | No |  |  |  |  | Freehold | Kent - 4/26 | Class 9. Temporary Use for Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
167 | Thanet District Council | Kent | Yes | RR-5372 | RR-5372 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005472 | REP1-141 REP3A-034 | REP1-141 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001215-Thanet-District-Council-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S2CA355BB.pdf REP3A-034 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002232-Thanet%20District%20Council%20-%20Written%20Representation%20to%20Change%20Request%20Application.pdf | Freehold | Kent - 3/90 3/97 3/97a 3/108 3/111 3/112 5/6 5/8 5/17 5/25 5/30 5/30a 5/31 5/32 5/33 5/35 5/36 5/39 5/45 5/46 5/47 5/48 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Hobbs Parker | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. | 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | 10.02.2026 - Thanet District Council (TDC) informed the Applicant's Agent on 12th January 2026 that they have appointed an agent to negotiate Heads of Terms on their behalf. On 16th January 2026 the landowner’s agent provided initial comments on the Heads of Terms. On 19th January 2026 the Applicant's Agent responded to the TDC's agent’s comments and issued revised Heads of Terms with clarification provided on the easement consideration . A meeting was held on 5th February 2026 which was productive and allowed Heads of Terms discussions to progress positively. The Applicant’s Agent understands the points under discussion relate to the bespoke nature of the land use in this foreshore area. It is anticipated that a revised version of the Heads of Terms will be issued imminently which will resolve these points. Additionally, discussions are ongoing in relation to the commercial terms. A further meeting has been arranged for 5th March 2026 where it is anticipated further progress will be made. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - On the 5th February 2026, the Applicant's Agent and landowner's agent held a meeting to discuss revisions to the Heads of Terms regarding the bespoke nature of the land. Revised Heads of Terms were sent to the landowner's agent on the 26th of February 2026, which referred to the bespoke nature of the land. On the 5th of March 2026, the Applicant's Agent and the landowner's agent held a meeting that discussed the wording of the clauses which are now with legal to review and update. Most of the provisions of the Heads of Terms are agreed in principle, however, the outstanding element to be agreed is the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent has not received a detailed update from the landowner's agent following the meeting on 5th March 2026 where it was raised that a number of matters were being checked with the landowner's legal advisors. The Applicant's Agent has contacted the landowner's agent for updates on 24th March and 31st March 2026. Following a phone call on 8th April 2026, it is now understood that the landowner's agent has changed to another member in their firm. The landowner's new agent confirmed on 8th April 2026 that the Heads of Terms are still with the landowner for review and legal consideration of a number of points including the drafting around use of compulsory powers and contamination. The commercial terms are still under discussion and the Applicant's Agent awaits more comparable evidence from the landowner's agent. A further meeting has been requested by the Applicant's Agent and should that be arranged it is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - A change of personnel has unfortunately caused a delay in progression of the negotiation of the Heads of Terms. The Applicant's Agent is still awaiting feedback from the landowner's legal team in respect of the drafting around a restriction on the use of compulsory purchase powers and contamination. A further meeting has been arranged with the landowner's agent on Wednesday, 6th May 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
184 & 637 | James Bedford Pace & Alexandra Ruth Pace | Kent | No |  |  |  |  | Freehold | Kent - 2/132 2/144 2/145 2/147 2/150 2/153 2/154 4/14 4/15 4/18 4/22 4/23 4/26 | Class 1. Compulsory Acquisition of land. Compulsory Acquisition of land Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. |  | 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 10.02.2026 – On 14th January 2026 the Applicant's Agent met with the landowners' agent who confirmed they are now able to share comparables to inform the commercial terms. On 22nd January 2026 the Applicant's Agent followed up to request the comparable data and confirmation that the remainder of the terms are agreed. A response has not yet been received, It is understood that the commercial terms are the only points outstanding and that an agreement will be reached by the end of Examination. | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the Landowner's Agent requesting both comparable evidence supporting their commercial position, and commentary on the Heads of Terms. On the 2nd March 2026 the Applicant's Agent phoned and emailed the Landowner's Agent to request the aforementioned comparable evidence and feedback on the Heads of Terms. The Landowner's Agent confirmed that they would look to provide this information by 6th March 2026. To date, no response has been received but the Applicant's agent remains positive Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
189 | Ian David Mather | Kent | Yes | RR-0291 | RR-0291 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006193 |  |  | Freehold | Kent - 2/148 2/149 2/152 4/16 4/17 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 7. Compulsory Acquisition of Rights – Mitigation | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. |  | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 10.02.2026 – On 14th January 2026 the Applicant's Agent met with the landowners' agent who confirmed they are now able to share comparables to inform the commercial terms. On 22nd January 2026 the Applicant's Agent followed up to request the comparable data and confirmation that the remainder of the terms are agreed. A response has not yet been received. It is understood that the commercial terms are the only points outstanding and that an agreement will be reached by the end of Examination. | 10.03.2026 - On 29th January 2026, the landowner's agent raised two issues with the Heads of Terms - these were, the rights sought for utility diversions and also the commercial terms. At this point no evidence was provided to justify a revised commercial approach. On 24th February 2026 the landowner's agent provided the Applicant Agent's with some commercial information for consideration. The Applicant's agent is in the process of further understanding how this may impact on the commercial terms. It is still expected that an agreement will be reached by the end of Examination. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion.
237 | The National Trust for Places of Historic Interest or Natural Beauty | Kent | Yes | RR-5384 | RR-5384 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005599 |  |  | Freehold | Kent - 3/109 3/110 5/1 5/9 5/26 5/27 5/28 5/29 5/34 5/37 5/40 5/41 5/42 5/43 5/44 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Ardent | 25.03.2025 - National Grid's Agent issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 a number of dates for a meeting was proposed to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | 10.02.2026 - The Applicant's Agent has sought updates from the landowner's agent in respect of comments on the Heads of Terms, as well as seeking to arrange a meeting to discuss the landowner’s objection. On 22nd January 2026 the Applicant's Agent re-issued the Heads of Terms with clarification on the easement consideration. The landowner’s agent has submitted some comments on the Heads of Terms in an email dated 27th January 2026. The Applicant’s Agent has reviewed the comments and will discuss the matters of objection including construction methodology, mitigations and proposed easement width in detail during a meeting set for 11th February 2026. | 10.03.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent held a Teams meeting to discuss a number of topics including construction methodology and mitigations on 11 February 2026. A further meeting was held with the Applicant's Agent and the landowner's agent on 2 March 2026 to discuss the Heads of Terms. The meeting was productive and it is understood that an agreement has been reached on a number of terms. The points still under negotiation include the extent of the working area, insurance provisions, commercial terms and the links to documentation within the draft DCO. A further meeting is planned for week commencing the 16th March 2026. At this stage, the Applicant's Agent remains positive that Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - The Applicant, the Applicant's Agent, the landowner and the landowner's agent have been progressing matters constructively since Deadline 5. Teams meetings took place on 19th March, 26th March and 7th April 2026. A number of points have been resolved, the outstanding points under discussion are insurance provisions and commercials. The next meeting is arranged for 21st April 2026. The Applicant's Agent believes that Heads of Terms will be signed by the end of the Examination. The Applicant continues to work with the landowner to agree the Statement of Common Grounds by Deadline 7. | 29.04.2026 - The Applicant has had Teams meeting with the landowner and their agent on 21st, 27th and 28th April 2026 in order to progress both the Statement of Common Ground and Heads of Terms. After the meeting on 28th April 2026 it is understood that the outstanding points in relation to insurance provisions and commercials are agreed between both parties. The Applicant’s Agent issued revised Heads of Terms to the landowner and their agent on 28th April 2026 to include minor amendments to wording as discussed at the meeting. The Applicant is awaiting final confirmation from the landowner that the Heads of Terms are in an agreed form, which is expected to be received before the close of Examination. | Kent Wildlife Trust
341 | Ebbsfleet Minster (Kent) Limited | Kent | No |  |  |  |  | Freehold/ Occupation | Kent - 3/10 3/24 3/26 3/28 3/29 3/31 3/32 3/35 3/38 3/39 3/41 3/46 3/47 3/74 3/75 3/76 4/5 | Class 1. Compulsory Acquisition of land Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Finn's (1865) Ltd | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. |  | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14 January 2026 | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026. The Applicant’s Agent has been informed by the landowner’s agent that there is an Option agreement on the land with Statkraft, and that consent will be required from Statkraft in order for the landowner to be able to sign the Heads of Terms. The Applicant’s Agent has requested a meeting with the landowner’s agent and a relevant representative from Statkraft to discuss this further and awaits a response from the landowner’s agent. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - Template Heads of Terms are agreed with this agent, however due to the presence of an Option Agreement with Statkraft over the land, these Heads of Terms have not yet progressed to signature. On 28th January 2026 and 5th February 2026, the Applicant's Agent requested a joint meeting with Stratkraft to seek their consent to the Option Agreement for this Proposed Project. On the 19th February 2026 on a phone call between the Applicant's Agent and the landowner's agent, the landowner's agent confirmed they do not yet have a date from Stratkraft for a meeting. There is a meeting with the landowner's agent on 16th March 2026 but due to the interaction with Stratkraft and their restrictions over the land, it is not envisaged that agreement will be reached before the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement. | 13.04.2026 - The Applicant's Agent had a Teams meeting with the landowner's agent on 18th March 2026, where the landowner's proposals for developing the land were discussed in detail to see how the two proposals can co-exist. The landowner's development proposals involve raising the ground levels up to 4m above the existing ground level. This proposed change to the ground levels could impact the Applicant's proposal, however, the Applicant confirmed their willingness to work with the landowner to provide more detailed design information at the meeting on the 18th March 2026. A revised drawing of the Transition Joint Bay will be provided to the landowner to allow adjustments to be made to the landowner's proposals, enabling both proposals to co-exist. A further meeting will be arranged once the drawing of the Transition Joint Bay has been provided to the landowner's agent. Additionally, as stated at Deadline 5 and the Compulsory Acquisition Hearing on 25th March 2026, the Applicant is still trying to contact the third party developer, Statkraft UK Ltd, who holds an Option Agreement over part of this land to discuss how the developments can coexist. The landowner's agent and Applicant's Agent continues to progress matters constructively, however, due to the complexities of their development plans, Heads of Terms will likely not be signed before the end of Examination. | 29.04.2026 - The Applicant followed up with the landowner's agent in relation to the draft Statement of Common Ground on 31st March 2026 to provide assurances that the Applicant is willing to work with the landowner to determine if their golf club extension development proposals and the Project proposals can co-exist. On 23rd April 2026, the landowner's agent provided the Applicant's agent with a contact for Stratkraft UK Ltd. The Applicant's agent will now liaise with Stratkraft in relation to their development proposals On 24th April 2026, the Applicant's agent has provided the landowner's agent with the revised drawing of the Transition Joint Bay and is setting up a meeting with the landowner's agent to progress their development proposals alongside the Project proposals. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
378 | Church Commissioners for England | Kent | No |  |  |  |  | Freehold | Kent - 2/65 2/69 2/70 2/71 2/72 2/73 2/74 2/75 2/76 2/78 2/79 2/83 2/84 2/107 2/108 2/109 2/111 2/112 2/113 2/187 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Savills | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. |  | 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 10.02.2026 – On 15th January 2026 the Applicant's Agent met with the landowner’s agent to discuss soil management and hydrology related concerns held by the farming tenant. On 21st January 2026 the Applicant's Agent emailed the landowner’s agent following up regarding feedback on the Heads of Terms. On the 21st January 2026 the landowner’s agent responded confirming that they have additional information to review before they can provide further comments on the Heads of Terms. At this stage it is understood an agreement should be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the landowner's agent requesting feedback on the Heads of Terms. The landowner's agent responded with a query surrounding compensation which has now been resolved. On the 4th March 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent for review. On the 6th March 2026, the Applicant's Agent proposed a meeting with the Landowner's Agent for the 25th March 2026. This landowner is an absentee landlord and as such there are additional complexities with the occupation of the land. To date no substantive feedback has been provided by the landowner's agent. It is therefore unlikely that Heads of Terms will be signed by the end of Examination but it is believed further meaningful discussions can be had to progress matters between the landowner's agent and the Applicant's Agent. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | Pippa Southorn / D H Clifton
411 | Southern Water Services Limited | Kent | Yes |  |  | REP1-263 | REP1-263 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001398-Southern%20Water%20Services%20Limited%20(SWS).pdf | Freehold/ Occupation | Kent - 1/1 1/7 1/8 1/10 2/81 2/82 2/83 3/41 3/44 3/46 3/47 3/49 3/52 3/53 3/54 3/74 3/75 3/77 3/79 3/80 3/81 3/85 3/86 3/87 3/91 3/92 3/95 3/96 3/97 3/97a 3/99 3/100 3/101 3/102 4/5 4/6 4/7 4/10 4/11 4/12 4/13 4/19 4/19a 4/22 4/23 4/25 4/26 4/27 6/1 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access Class 10. Land that is not subject to powers of acquisition nor temporary | No | No | [5 empty] | 10.02.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted. | 10.03.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 13.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted | 29.04.2026 - The land rights required from Southern Water's Category 1 land interest has been removed from the Application at Deadline 4. Protective Provisions will provide the security to Southern Water that their operations will not be interrupted
458 | The King's Most Excellent Majesty in Right of His Crown | Kent | Yes | RR-5378 | RR-5378 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004393 |  |  | Freehold | Kent - 2/58 2/62 2/85 2/91 2/98 2/105 5/11 5/12 5/14 5/15 5/16 Suffolk - 6/7 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | In House | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage. In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. |  | 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | 10.02.2026 - The Applicant's Agent has reviewed the points raised by The Crown Estate’s agent and responded with a marked up set of Heads of Terms on 6th February 2026 and has offered a meeting to discuss the outstanding points. The Applicant is confident that a voluntary agreement will be reach with the Crown. | 10.03.2026 - On 25th February 2026, the Applicant and the Applicant's Agent met with the landowner's agent to discuss the principles within the Heads of Terms. Positive progress was made including clarity on the next steps for S135 consent. On 6th March 2026, the Applicant's Agent emailed the landowner's agent with a revised position on the outstanding points. In addition to commercial matters, the main outstanding point relates to insurance provisions. The Applicant remains confident that a voluntary agreement will be reached with the landowner. | 13.04.2026 - The Applicant's Agent and the landowner's agent have had proactive negotiations and have agreed the commercial terms and the level of indemnity for the crossing of the River Stour agreement. Heads of Terms for the River Stour Crossing are being redrafted in their final form with these updates to be signed by both parties. Terms for the temporary crossing right are provisionally agreed with final comments made by the Applicant agent on 10th March 2026. The Applicant expects that agreement can be reached before the end of examination. | 29.04.2026 - Heads of Terms have been agreed for both the River Stour crossing and the temporary bridge crossing on 22nd April 2026. Legal drafting of the Option agreements and s135 consent is ongoing.
494 | Struan Gordon Robertson | Kent | Yes | Oral Representation at OFH and request to speak at CAH |  |  |  | Freehold/ Occupation | Kent - 2/118 2/119 2/120 2/121 2/122 2/123 2/124 2/127 2/128 2/129 2/130 2/133 2/134 2/137 2/138 2/139 2/140 2/141 2/142 2/143 2/146 2/151 2/155 2/156 2/157 2/158 2/159 2/160 2/161 2/162 2/163 2/164 2/165 2/166 2/167 2/168 2/169 2/170 2/171 2/172 2/173 2/174 2/175 2/176 2/177 2/178 2/179 2/180 2/182 2/183 3/2 3/3 3/6 3/7 3/8 3/9 3/10 3/11 3/17 3/20 3/20a 3/21 3/22 3/23 3/24 3/25 3/26 3/29 3/35 3/98 3/98a 4/1 4/4 4/29 | Class 1. Compulsory Acquisition of land Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Hobbs Parker | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. |  | 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025. A follow up meeting proposed for 16th January 2026. | 10.02.2026 – On 5th February 2026 the Applicant’s Agent attended a meeting with the landowner’s agent to discuss outstanding comments in relation to the Heads of Terms. Outstanding areas for agreement include the option period, pre-entry and survey works, ancillary rights for utilities, rights to be granted to the Grantee, and the commercial terms. A follow up meeting has been arranged between the Applicant’s Agent and the landowner’s agent on 5th March 2026. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - There has been ongoing dialogue between the Applicant's Agent and the landowner's agent following the meeting on 5th February 2026. An email was sent by the Applicant's Agent on 26th February 2026 seeking comparables for the commercial terms offered. On 25th February and 3rd March 2026 the Applicant's Agent had various phone calls with the landowner's agent in preparation for their meeting on 5th March 2026. On 5th March 2026 the Applicant's Agent attended a meeting with the landowner's agent where a number of the points raised at the previous meeting were discussed. On 6th March 2026, the Applicant's Agent issued revised Heads of Terms to the Landowner's Agent, it is understood that the revised terms will be discussed with the landowner at an in-person meeting on 10th March 2026. The outstanding points relate to rights sought for utility diversions and commercial terms. It is understood that an agreement can be reached before the end of Examination. | 13.04.2026 - On the 25th March 2026, the Applicant's Agent called the landowner's agent to discuss the outcomes of their meeting with the landowner proposed for the 10th of March 2026. The landowner's agent confirmed that this had not occurred yet and will be rescheduled. On the 25th March 2026, the Applicant's Agent sent an email to the landowner's agent requesting comparable evidence supporting their commercial position. On 30th March 2026, the Applicant's Agent called the landowner's agent to discuss the proposed landowner meeting, it was confirmed that this was to proceed on the 31st March 2026. The landowner's agent requested further information to support their discussion with the landowner and this was provided via email on the 31st March 2026 ahead of the meeting. The Applicant's Agent tried to call the landowner's agent on the 2nd April 2026, the landowner's agent returned the call on 8th April 2026. The landowner and landowner's agent are happy that the documentation and principles are progressing in the right direction towards voluntary agreement, however, a number of matters are subject to ongoing discussion. These matters subject to further discussion include ancillary rights sought across the wider holding, accommodation works and value of the retained land. On 9th April 2026, the Applicant's Agent issued an editable version of the latest Heads of Terms to allow further comments from the landowner's agents. Progress has been made on the proposed structure of the transaction, but given the complex nature of the acquisition it is not believed Heads of Terms will be signed by the end of Examination. Confirmation was received on 9th April 2026 stating that for the Class 1 land areas the landowner is content to go straight to acquisition on a voluntary basis, and the terms for this are under active negotiation. | 29.04.2026 - On the 22nd April 2026, the Applicant's Agent called the landowner's agent requesting feedback on their progress with providing further feedback on the Heads of Terms. A meeting was arranged for the 6th May 2026 with the landowner's agent committing to provide written feedback ahead of this meeting. The Applicant's agent discussed and sent a follow up email requesting comprehensive comparable evidence to inform the commercial position and allow progress in that regard. The landowner's agent confirmed that they would provide this evidence by close of play on the 24th April 2026. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
498 | Kent Wildlife Trust | Kent | Yes | RR-2980 | RR-2980 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100002909 | REP1-151 REP1-152 REP3A-023 | REP1-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001167-Deadline%201_Sea%20Link%20Written%20Reps%20Summary_KWT_F0B50218B_Nov25.pdf REP1-152 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001166-Deadline%201_Sea%20Link%20Written%20Reps_KWT_F0B50218B_Nov25.pdf REP3A-023 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002223-Deadline%203a%20Sea%20Link%20DCO%20Application%20Change%20Consultation_Kent%20Wildlife%20Trust%20_Jan26.pdf | Freehold / Leasehold / Occupation | Kent - 3/109 3/110 5/1 5/9 5/10 5/13 5/18 5/26 5/27 5/28 5/29 5/34 5/37 5/38 5/40 5/41 5/42 5/43 5/44 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | BTF Partnership | 25.03.2025 - National Grid's Agent issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the Examination process. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. | 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | 10.02.2026 – The Applicant's Agent issued Heads of Terms directly to the landowner by letter on 13th January 2026 and emailed the Heads of Terms to the landowner’s agent on 15th January 2026. Following the Compulsory Acquisition Hearing 1, the Applicant’s Agent emailed the landowner’s agent on 2nd February 2026 requesting to enter into discussions on the Heads of Terms. The Applicant’s Agent followed this up with an email to the landowner on 9th February 2026. The Applicant’s Agent will continue engage with the landowner to seek to secure a voluntary agreement. | 10.03.2026 - The Applicant has made further attempts to engage directly with the landowner and their agent on 16th February 2026, but has received no response from either the landowner or the landowner's agent. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. Noting the ExA's request to Kent Wildlife Trust to meaningfully engage, the Applicant is prepared to move these negotiations forward once communications are returned | 13.04.2026 - The landowner submissions at Deadline 5 and their representations at the Compulsory Acquisition Hearings on 25th March 2026 made the landowner's position clear in relation to the voluntary negotiations. Whilst the Applicant remains willing to engage and reach a voluntary agreement, it is not believed an agreement will be reached by the end of Examination. | 29.04.2026 - The landowner has not changed their position, and they remain unwilling to enter into negotiations for a voluntary agreement. The Applicant remains willing to engage with this landowner after Examination has closed, should their position change.
524 | Gavin Johnson |  | Yes | RR-1696 | RR-1696 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003566 |  |  | Freehold/ Occupation | Kent - 4/26 | Class 9. Temporary Use for Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
538 | Trapoc Ltd | Kent | No |  |  |  |  | Freehold/ Occupation | Kent - 6/3 6/4 6/5 | Class 5. Compulsory Acquisition of Rights – Access | No | Yes |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). | 03.10.2025 – Ongoing engagement with the PIL to secure voluntary agreement. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. |  | 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | 10.02.2026 – On the 9th January 2026, the landowner confirmed that they would provide feedback on the Heads of Terms during the week commencing 19th January 2026. The Applicant's Agent emailed the landowner on 22nd January 2026 to confirm if feedback was still expected. On 5th February 2026, the Applicant’s Agent called the landowner who confirmed that they require further internal reviews before feedback on the Heads of Terms can be provided. The Applicant’s Agent will continue to engage with the landowner and it is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 23rd February 2026, the Applicant's Agent emailed the landowner requesting feedback on the Heads of Terms and inquired as to whether any further information could be provided to facilitate a response. On the 6th March 2026 the Applicant's Agent emailed the landowner with revised Heads of Terms for review and proposed a meeting for the week commencing 23rd March 2026. It is understood that there are no in principle concerns from the landowner and the Applicant's Agent expects that an agreement can be reached by the end of Examination once the landowner has had time to consider the proposed terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent called the landowner to discuss Heads of Terms and project timescales. The landowner confirmed that they would provide written feedback on the documentation ahead of the Easter break. To date written feedback has not been received, and Applicant's Agent sent a follow up email on the 9th April 2026. Given the delays from the landowner it is not expected that an agreement will be reached by the end of Examination. | 29.04.2026 - On the 20th April 2026, the Applicant's Agent emailed the landowner requesting written feedback on the Heads of Terms and offering a meeting. The Applicant's Agent attended a Teams meeting with the landowner on the 22nd April 2026 to discuss the Heads of Terms and the landowner sent a follow up email with the marked up documentation. The main points that they have provided feedback on are in relation to restrictions within the option area, ancillary rights for utilities and third party interests. The Applicant is currently reviewing the landowner's feedback on the Heads of Terms and the Applicant will respond with their position as soon as practicable. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
553 | St. Augustine's Golf Club (Ramsgate) Limited | Kent | No |  |  |  |  | Freehold/ Occupation | Kent - 3/54 3/65 3/66 3/88 3/89 3/99 3/100 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 11th November 2025 to progress matters. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 10.02.2026 – A Teams meeting took place with the Applicant’s Agent and landowner’s agent on 14th January 2026. The Applicant's Agent issued a follow-up email to the landowner’s agent on 22nd January 2026 enquiring whether there any outstanding issues preventing the Heads of Terms being issued in final form for the landowner’s signature. A response has not been received but based on previous positive engagement it is anticipated that an agreement will be reached by the end of Examination. | 10.03.2026 - On 18th February 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation of any outstanding issues in the Heads of Terms. On 20th February 2026, the landowner's agent emailed to confirm the Heads of Terms should mirror the bespoke amends made for other golf course terms. These amends will be incorporated and the Heads of Terms reissued by the Applicant's Agent. Further discussion is ongoing in relation to an alternative access route with the most recent contact being a phone call on 6 March 2026. It is believed that an agreement will be reached by the end of Examination. | 13.04.2026 - The landowner's agent provided a list of comparable evidence in relation to the commercial terms on 30th March 2026. Discussions continue in relation to the proposed operational access route. In a meeting with the landowner's agent on 1st April 2026, the access route was discussed in more detail and a proposal is with the landowner for further consideration. On 9th April 2026, the Applicant's Agent called the landowner's agent to provide clarity on the access route and confirmed that a plan will be provided the landowner's agent for their consideration. With the exception of the access route and commercial terms, the Heads of Terms are in an agreed form. It is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the previous outstanding points concerning the commercials and the operational access route. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently.
576 | HMS Two Incorporated Limited |  | No |  |  |  |  | Freehold/ Occupation | Kent - 3/3 3/10 | Class 5. Compulsory Acquisition of Rights – Access Class 9. Temporary Use for Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
654 | Robert John Chapman | Kent | No |  |  |  |  | Freehold | Kent - 3/59 3/60 3/61 3/65 4/10 4/22 4/23 4/24 4/25 4/26 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. |  | 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 10.02.2026 - Following a Teams meeting on 14th January 2026, the landowner’s agent followed up the points discussed in an email to the Applicant's Agent on 20th January 2026. The Applicant's Agent responded to those comments on 22nd January 2026 and re-issued the Heads of Terms to clarify the easement consideration and requesting that the landowner’s alternative access route be provided to the Applicant's Agent for further review. The landowner’s agent provided an alternative access route on 27th January 2026, which is now being reviewed by the Applicant. It is understood that an agreement can be reached before the end of Examination. | 10.03.2026 - On the 27th of January 2026, the Applicant's Agent received an alternate access route proposal from the landowner's agent. On the 3rd February 2026, the Applicant's Agent and landowner's agent discussed access arrangements, commercial terms and activities permitted in the easement. In a meeting on 19th February 2026, the landowner's agent confirmed that only the outstanding matter was in relation to the commercials. The landowner's agent confirmed that comparable valuation evidence would be provided for the Applicant's Agent's consideration. The Applicant anticipates reaching a voluntary agreement prior to the end of the Examination. | 13.04.2026 - On 23rd March 2026, the Applicant's Agent issued a final version of the Heads of Terms to the landowner's agent for signature, at the request of the landowner's agent. On the 24th March 2026, the landowner's agent sought higher consideration and provided some comparable evidence. Despite further correspondence with the landowner's agent and a revised offer, commercial terms are not yet agreed but it is expected that a voluntary agreement can be reached by the close of the Examination. | 29.04.2026 - An agreement has been reached between the Applicant's Agent and the landowner's agent in relation to the outstanding points concerning the commercials. On 23rd April 2026, finalised Heads of Terms and accompanying plan were issued to the landowner's agent for signature. The Applicant is confident that agreement will be reached with this landowner imminently.
698 | John Robert Collins | Kent | Yes | RR-1465 | RR-1465 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005394 |  |  | Freehold | Kent - 2/23 2/24 2/27 2/28 2/29 2/30 2/32 2/36 2/39 2/40 2/41 2/42 2/88 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Elgars | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. | 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the Examination process. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. |  | 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | 10.02.2026 - The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 19th January 2026, the Applicant's Agent left a voicemail with the landowner requesting a meeting for the 21st January 2026. On 21st January 2026 the Applicant's Agent visited and spoke with the landowner to confirm that their agent is still appointed to negotiate with the Applicant's Agent on their behalf. The landowner was due to speak to the agent and encourage a response with regards to the Heads of Terms. The Applicant's Agent followed this meeting up with an email to the landowner’s agent on 22nd January 2026. The landowner’s agent has only provided feedback on the objection clause. Despite this clause being amended to address their concerns, the Applicant’s Agent hasn’t received any further feedback on the latest version of the Heads of Terms issued – this is still awaited. | 10.03.2026 - On the 23rd February 2026 the Applicant's Agent called the landowner regarding the Heads of Terms where the landowner confirmed that he has not spoken with his agent since the Applicant's Agent visited his property on the 21st January 2026, but that he would do so in the near future. Whilst feedback has not been provided on the Heads of Terms, on the 4th March 2026, the Applicant's Agent issued revised Head of Terms to the landowner's agent and proposed a meeting to discuss further on the 24th March 2026. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination, but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On the 31st March 2026, the Applicant's Agent spoke with the landowner's agent on the phone. Their primary concern is around the prohibition of objection clause in the Heads of Terms. The Applicant's Agent confirmed that this particular clause has been extensively updated and the Heads of Terms re-issued. Despite this, the landowner's agent has stated they are not willing to provide any feedback to the Applicant's Agent regarding additional changes required until after the Examination has closed. On the 9th April 2026, the Applicant's Agent sent a letter to the landowner setting out the position adopted by their agent and encouraging the landowner to engage with the Applicant to resolve any other outstanding issues. | 29.04.2026 - No response has been received to the letter issued to the landowner on the 9th April 2026. In line with previous confirmation that the landowner's agent would not be willing to provide feedback on the Heads of Terms until Examination closes, the Applicant's Agent will continue to engage with the landowner's agent after the close of Examination.
718 | Richborough Estates Limited | Kent | Yes | RR-1466 | RR-1466 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005470 |  |  | Freehold | Kent - 2/125 2/126 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Elgars | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. | 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the Examination process. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. |  | 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm continued appointment of their agent in relation to the Heads of Terms. No response has been received. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. The landowner’s agent has only provided feedback on the objection clause. Despite this clause being amended to address their concerns, the Applicant’s Agent hasn’t received any further feedback on the latest version of the Heads of Terms issued – this is still awaited. On 22nd January 2026 the Applicant's Agent sent further email correspondence to the landowner’s agent requesting feedback on the Heads of Terms and any concerns held by the landowner. A request has been made to meet with the landowner’s agent and the landowner to discuss the Heads of Terms in more detail. | 10.03.2026 - On the 4th March 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent and on the 24th of March 2026, the Applicant's Agent proposed to hold a meeting with the landowner and their agent to discuss the revised Heads of Terms. At this point it is not envisaged that the landowner's agent will engage sufficiently to agree the Heads of Terms by the end of Examination but, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with the landowner. | 13.04.2026 - On the 31st March 2026, the Applicant's Agent spoke with the landowner's agent on the phone. Their primary concern is around the prohibition of objection clause in the Heads of Terms. The Applicant's Agent confirmed that this particular clause has been extensively updated and the Heads of Terms re-issued. Despite this, the landowner's agent has stated they are not willing to provide any feedback to the Applicant's Agent regarding additional changes required until after the Examination has closed. On the 9th April 2026, the Applicant's Agent sent a letter to the landowner setting out the position adopted by their agent and encouraging the landowner to engage with the Applicant to resolve any other outstanding issues. | 29.04.2026 - No response has been received to the letter issued to the landowner on the 9th April 2026. In line with previous confirmation that the landowner's agent would not be willing to provide feedback on the Heads of Terms until Examination closes, the Applicant's Agent will continue to engage with the landowner's agent after the close of Examination.
1015 & 2370 | Nigel Stewart Daw & Dorcas Muriel Daw |  | No |  |  |  |  | Freehold | Kent - 1/1 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
1271 | Network Rail Infrastructure Limited | Kent | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf | Freehold/ Occupation | Kent - 2/110 2/113 2/114 2/115 2/116 2/117 2/123 2/186 2/187 2/188 3/3 3/80 3/86 3/87 Suffolk - 7/21 7/22 7/26 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | In House | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. | 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. | 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. |  | 10.2.2026 - Meeting with the Network Rail Agent on the 20 January confirmed that the Heads of Terms are broadly agreed for the Kent section of the project, with the outstanding matter being the OHL Clearance over the active railway crossing. The NR agent confirmed that there was an engineering assessment being undertaken on the Benhall Bridge section of the project, in Suffolk. The NR agent has confirmed that the Framework Agreement between NR and NGET is still in place and that template documents will follow that format. | 10.03.2026- The Applicant will continue to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 29.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this is being taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. In relation to Protective Provisions, the Applicant is continuing to pursue engagement with the statutory undertaker. It has now received Network Rail’s comments on the Applicant’s proposed protective provisions . Based on those comments, it has made further amendments to the protective provisions which can be seen in the dDCO submitted at Deadline 7. The Applicant has now also received the draft framework agreement which is under review. The Applicant hopes to set up a meeting to discuss the outstanding points with Network Rail soon after Deadline 7. The Applicant believe that Heads of Term will be signed after Deadline 7. The Applicant will provide an update to the Examining Authority in due course.
1335 | David John Fuller |  | No |  |  |  |  | Freehold | Kent - 2/83 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
1336 | Denton & Co Trustees Limited (as trustee to The Dentons Self Invested Personal Pension) |  | No |  |  |  |  | Freehold | Kent - 2/83 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
2386 & 2387 | Samuel David Price & Amy Elizabeth Price |  | Yes | RR-4767 | RR-4767 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004980 |  |  | Freehold | Kent- 1/1 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3589 | Personal Representative to the Estate of Andrew William Johnson | Kent | Yes | RR-3805 | RR-3805 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004353 |  |  | Freehold | Kent - 1/2 1/3 1/4 1/5 1/6 1/7 1/8 1/9 1/10 1/11 1/12 1/13 1/14 1/15 1/16 1/17 1/18 1/19 1/20 1/21 1/22 2/1 2/2 2/3 2/4 2/5 2/6 2/7 2/8 2/9 2/10 2/11 2/12 2/13 2/14 2/21 2/90 2/93 2/94 2/95 2/96 2/99 2/104 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | BTF Partnership | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. |  | 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | 10.02.2026 – The Applicant's Agent emailed the landowner’s agent on 09th January 2026 to provide additional clarity regarding the proposed use of Whitehouse Drove Road which has been a point of concern for the landowner. Clarity was provided regarding the timescales for use, the number of vehicle movements, construction phasing for the use of Whitehouse Drove facilities and subsequent repair. The Applicant’s Agent sent a further email to the landowner’s agent on 6th February 2026 requesting confirmation that the information has been shared with the landowner and feedback on the Heads of Terms in light of the update provided. The Applicant’s Agent understands agreement should be possible by the end of Examination. | 10.03.2026 - The Administrator for the Estate of the landowner has passed away. The Applicant's Agent remains in regular dialogue with the landowner's agent. On 3rd March 2026, the Applicant's Agent emailed the landowner's agent to seek confirmation regarding current administratorship to the Estate of the landowner. On the 6th March 2026 the Applicant's Agent issued revised Heads of Terms to the landowner's agent. Although there is regular communication with the landowner's agent, it is expected that the Heads of Terms won't be signed before the end of Examination due to recent passing of the Administrator and difficulties pursuant to it. | 13.04.2026 - On the 9th April 2026, the Applicant's Agent emailed the landowner's agent requesting confirmation as to whether the landowner's agent has had contact with the Executors of the Estate of the landowner and their position with regards the Heads of Terms. The Applicant's Agent has not received any response to this email or the previous correspondence set out at Deadline 5. Agreement is unlikely to be reached by close of Examination but the Applicant's Agent will continue attempts to progress matters. | 29.04.2026 - On the 24th April 2026, the Applicant's Agent sent a further email to the landowner's agent requesting information on whether they have been able to make contact with the Executors for the Estate of Andrew Johnson, and if so, what their instructions are in relation to the Proposed Project and Heads of Terms. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination in order to reach a voluntary agreement.
2591 | The Marquess Conyngham | Kent | Yes | RR-5383 | RR-5383 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001574 |  |  | Freehold | Kent - 2/57 2/61 2/64 2/66 2/67 2/68 2/86 2/92 2/100 2/103 2/106 | Class 2. Compulsory Acquisition of Rights – Overhead Line Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | CW Gooch Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. |  | 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | 10.02.2026 The Applicant's Agent spoke with the landowner's agent on 19th January 2026. The agent confirmed that the Heads of Terms are agreed in principle; however, they are unable to sign any documents before the grant of probate for the estate due to the nature of the probate claim. | 10.03.2026 - On 11th February 2026, the Applicant's Agent emailed the landowner's agent to confirm whether a signature can be obtained on the Heads of Terms subject to documentation being issued for legal progression upon grant of probate. On 23rd February 2026 and the 2nd March 2026, the Applicant's Agent left a voicemail for the Landowner's Agent requesting a call back to discuss the same. The landowner's agent confirmed that they would take instruction from solicitors regarding the issue of the signature and update the Applicant's Agent. On 2nd March 2026 the Applicant's Agent issued a follow up email confirming this discussion. On the 5th March 2026 the Applicant's Agent requested an update via email from the landowner's agent. The Heads of Terms are agreed in principle. Due to complications with probate it is unlikely they will be signed before the end of Examination. | 13.04.2026 - The Heads of Terms are in agreed form, however, due to probate it is unlikely they will be signed before the end of Examination. | 29.04.2026 - The Heads of Terms are in agreed form, however, due to complications with Probate it is unlikely they will be signed before the end of Examination. The Applicant's Agent will continue to engage with the landowner's agent after the close of Examination to ensure that they are signed as soon as Probate is settled.
2669 | Ian Peter Alan Smith | Kent | Yes | RR-4206 | RR-4206 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100002807 | REP5-162 | https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002793-Peter%20Smith.pdf | Freehold/ Occupation | Kent - 3/92 3/94 3/96 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | George Webb Finn | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. |  | 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms. The Applicant is aware that the landowner has an Option Agreement in place with a developer over this land and the developer intends to submit a planning application to develop this land for commercial use. Engagement is ongoing with the landowner, their agent and the developer to clarify timescales of related development proposals and determine if the two developments can co-exist. The landowner’s agent emailed on 12th January 2026 setting out their position in relation to the development proposals. The Applicant’s Agent emailed the landowner’s agent on 6th February 2026 to state that the Applicant believes that the developments can co-exist and are looking to set up a meeting in February to understand any further developments to their proposals. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent emailed the landowner's agent on 18th February 2026 requesting a meeting to discuss overlapping development timescales. On the 6th of March, the Applicant's Agent issued revised Heads of Terms to the landowner and their agent and requested a further meeting to discuss the overlapping development timescales. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - A meeting is arranged with the landowner's agent for 21st April 2026 to discuss timescales for both developments. As there is a 3rd party Option Agreement in place over the land associated with the development proposals, it is anticipated that the landowner will not be able to sign Heads of Terms until they have the third party developer consent to do so. Heads of Terms are unlikely to be signed by the end of Examination but discussion will continue to progress them with the landowner and the site developer. | 29.04.2026 - The Applicant's Agent had a Teams meeting with the landowner's agent and representatives from their developer on 21st April 2026. The meeting allowed all parties to provide an update on their development proposals and timescales, the developer is concerned that the Project proposals for temporary use of this land might interfere with their ability to get planning permission and develop the land. The Applicant has offered assurances that their need for the site is only temporary and the Landowner should still be able to progress their proposals with the local authority. The Applicant will continue to engage with the Landowner after the close of Examination.
3258 | Wallace John Wilson-Haffenden | Kent | No |  |  |  |  | Freehold/ Occupation | Kent - 6/1 6/2 | Class 1. Compulsory Acquisition of land Class 5. Compulsory Acquisition of Rights – Access | No | Yes | Finn's (1865) Ltd | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting on the 14th November 2025 with the landowner's agent to discuss the proposed terms in more detail. |  | 09.01.2026 – On 3rd December 2025, Dalcour Maclaren re-issued the Heads of Terms to the landowner’s agent to seek their feedback. A follow up email was sent on the 18th December 2025. Engagement continues in relation to the commercial terms. | 10.02.2026 – On 14th January 2026 the Applicant's Agent met with the landowner’s agent’s who confirmed that they are now able to share comparables to inform the commercial terms. On 22nd January 2026 the Applicant's Agent followed up to request that the comparable data and request confirmation that the remainder of the terms are agreed. A response has not yet been received, it is understood by the Applicant’s Agent that the commercial terms are the only points left to agree and that an agreement will be reached by the end of Examination. | 10.03.2026 - On the 11th February 2026, the Applicant's Agent emailed the Landowner's Agent requesting both comparable evidence supporting their commercial position, and commentary on the Heads of Terms. On the 2nd March 2026, the Applicant's Agent phoned and emailed the Landowner's Agent to request the aforementioned comparable evidence and feedback on the Heads of Terms. The Landowner's Agent confirmed that they would look to provide this information by 6th March 2026. To date, no response has been received but the Applicant's agent remains positive Heads of Terms can be agreed by the end of Examination. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. Further discussion is ongoing in relation to the impact on the retained holding. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - On 14th April 2026, The Applicant's Agent emailed the landowner's agent to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is currently engaging with the landowner's agent to reach an agreement in relation to the commercial elements of the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made
30 & 135 | Caroline Nichol & Gerlinde Edmunds | Suffolk | Yes | RR-4545 | Please see RR response for AP Ref No. 439 (Robert Nichol) RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 |  |  | Freehold/ Occupation | Suffolk - 1/14 1/16 1/17 1/18 1/20 1/21 1/22 1/28 1/30 1/74 1/75 1/76 1/77 1/78 1/79 | Class 1. Compulsory Acquisition of land Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Dalcour Maclaren had a phone call with the landowner’s agent on 11th November 2025 to discuss the previously issued terms and await further substantive feedback from the landowner. |  | 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is believed an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026, however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landowner's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
32 & 587 | Nicolas Jon Stuchfield & Jill Stuchfield | Suffolk | Yes | RR-4009 RR-2471 | RR-4009 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003679 RR-2471 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100002847 | REP1-230 | REP1-230 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001031-Submission%20to%20Planning%20Inspectorate%20F2BF7676B.docx.pdf | Freehold | Suffolk- 5/33 | Class 3. Compulsory Acquisition of Rights – Underground Cable System | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to confirm the already agreed terms within the Heads of Terms. A meeting is scheduled with the landowner and their agent on 23rd February 2026 to discuss landowner specific matters for inclusion in the Heads of Terms. It is understood by the Applicant’s Agent that an agreement should be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. The landowners primary concerns are in relation to construction impacts on their adjoining residential property. Whilst it is expected that the Heads of Terms will be agreed in principle by the end of Examination, further detail is required on the programme of the works in proximity to their residential property before Heads of Terms will be signed. | 3.04.2026 - The landowner's agent is part of the Suffolk agents group with whom we are negotiating template Heads of Term, however most of the outstanding points raised in the template are not specifically relevant to this land interest. Whilst the Applicant believes the template Heads of Terms points raised have now been adequately addressed, a number of amends requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is now awaiting comparable evidence for the land values from the landowner's agent. Whilst it is expected that the Heads of Terms will be agreed in principle by the end of Examination, further detail is required on the works programme in this area before Heads of Terms will be signed by this landowner. The rights being sought from this landowner are over a very small plot, they are underground cable rights only and no works are proposed at surface level, however, the landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant acknowledges the concerns and has sought to provide assurances in our response to the relevant reps submitted. REP2-018 4.1.3.3 of Document 9.34.3 : Applicants Response to Relevant Representations from Affected Landowners. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent to mitigate any potential disruption.
44 | Graham David Page |  | No |  |  |  |  | Freehold | Suffolk - 7/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
67 | James Henry Rogers | Suffolk | Yes | RR-6000 | RR-6000 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100008017 |  |  | Freehold/ Occupation | Suffolk - 2/19 | Class 3. Compulsory Acquisition of Rights – Underground Cable System | No | Yes | Brown & Co | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. |  | 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 10.02.2026 – The Applicant's Agent followed up on previous correspondence and emailed the landowner’s agent on 17th January 2026 to confirm if the landowner is willing to engage in relation to the Heads of Terms. The principal concerns are how the Sea Link cable will interact with a proposed Battery Energy Storage System (BESS) development on their land and construction phase impacts on their residential property due to the close proximity to Kiln Lane substation . The Applicant's Agent met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms and The Applicant is addressing comments in the Heads of Terms in relation to pre-entry soil surveys, access and drainage rights and commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination, whilst awaiting confirmation of the overlap in the development proposals before signing the Heads of Terms. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms that addressed feedback received from the landowner's agent. The Applicant's Agent met with the landowner's agent on the 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. Whilst it is expected that the Terms will be agreed in principle by the end of Examination, further clarity is sought by the landowner on the exact location of permanent infrastructure to determine the impact on the overlapping development proposals before the Heads of Terms will be signed. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner.
81 | Anthony Beverley Totton |  | No |  |  |  |  | Freehold | Suffolk- 7/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
109 & 766 | Michael Guy Hilliard Heald & Lucinda Jane Fullerton Heald | Suffolk | No |  |  |  |  | Freehold/ Occupation | Suffolk - 2/66 2/84 2/85 2/100 2/101 2/105 2/106 2/107 2/108 2/109 2/110 2/111 2/112 3/23 3/43 3/44 3/48 3/50 3/52 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Landbridge | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. | 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the Examination process. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. | 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 10.02.2026 – The Applicant's Agent held a Teams meeting with the landowner’s agent on 14th January 2026 to discuss the Heads of Terms. Heads of Terms were reissued to the landowner’s agent on 3rd February 2026 to address comments in relation to the proposed ancillary apparatus, occupiers consent and commercial matters. It is understood the updated Heads of Terms addressed all points save for the commercial terms. The Applicant’s Agent will continue to engage with the landowner’s agent and it is expected an agreement can be reached before the end of Examination. | 10.03.2026 – The Applicant’s Agent has had regular correspondence with the landowner’s agent including emails and phone calls on 18th February 2026, 20th February 2026, and 26th February 2026. A further phone call was made on 4th March 2026, and an email was sent on 6th March 2026, issuing revised Heads of Terms to the landowner's agent. The Applicant’s Agent has not received any substantial feedback on the Heads of Terms and any comments previously made have been addressed in the most recent iteration of the Heads of Terms. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026 after which the Applicant's Agent is expecting confirmation on whether the Heads of Terms are agreed. A meeting is currently being arranged between the Applicant's Agent and the landowner's agent for w/c 9th March. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
132 | William Notcutt Estates Limited | Suffolk | Yes |  |  | REP1-291 | REP1-291 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001137-William-Notcutt-Estates-Limited-The-applicant%E2%80%99s-updates-%E2%80%93-refer-to-annex-E-of-the-Rule-6-Letter-S8E67390E.pdf | Freehold/ Occupation | Suffolk - 1/1 1/2 1/3 1/4 1/5 1/7 1/8 1/9 1/10 1/11 | Class 1. Compulsory Acquisition of land Class 4. Compulsory Acquisition of Rights – Construction Compound Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Wilson Wraight | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. |  | 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | 10.02.2026 – The Applicant's Agent continues to negotiate the Heads of Terms with the landowner. Revised Heads of Terms were issued to the landowner and their agent on 2nd February 2026. The principle of the rights being sought is agreed with the landowner. However, there are terms still under discussion including future access and drainage rights, the future management of the proposed mitigation land along with the termination provisions should the project be decommissioned. A meeting is being arranged for February 2026 with the landowner and their agent and it is understood by the Applicant’s Agent that terms should be agreed by the end of Examination. | 10.03.2026 - The Applicant's Agent had a Teams meeting with the landowner and their agent on 6th March 2026 to discuss the revised Heads of Terms issued in February. Outstanding points to be agreed including termination clauses in the long-leasehold for mitigation land, pre-entry soil condition surveys and commercial matters. A further meeting has been arranged with the landowner and their agent for the 30th March 2026 and it is expected an agreement will be reached before the close of Examination. | 13.04.2026 - On 27th March 2026, revised Heads of Terms were issued to the landowner and their agent which included updates to the outstanding provisions on termination and soil condition surveys. The Applicant's Agent had a Teams meeting with the landowner and their agent on 30th March 2026 to discuss the revisions to Heads of Terms. The outstanding matters now are in relation to the commercial elements of the terms, access and drainage rights, future restrictions on the land and the soil survey matter is still outstanding. Revised Heads of Terms will be issued to the land owner week commencing 13th April 2026 and a further meeting has been scheduled for 21st April 2026 to discuss the revisions. Whilst it is anticipated that an agreement will be reached, due to the complexity of the agreements it is likely that this will be after the end of Examination. | 29.04.2026 - On 21st April 2026, the Applicant's Agent had a Teams meeting with the landowner and their agent to discuss the revised Heads of Terms. The final points for agreement in the Heads of Terms are the commercial matters, a further meeting is booked with the landowner and their agent for 13th May 2026, where it is hoped that the Heads of Terms will be finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
166 & 518 | Jeannie Ethel May Wright & Anne Elizabeth Wright | Suffolk | No |  |  |  |  | Freehold/ Occupation | Suffolk - 2/60 2/61 2/62 2/63 2/64 2/65 2/67 2/68 2/69 2/72 2/72a 2/72b 2/72c 2/73 2/75 2/76 | Class 1. Compulsory Acquisition of land Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Strutt & Parker | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. |  | 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since revised Terms were issued on 12th December 2025. The principle discussions with the landowner’s agent have been in relation to the Option agreement that the landowner has with Scottish Power Renewables and how this overlaps with the rights that National Grid are seeking. The Applicant’s Agent remains in regular dialogue with the landowner’s agent, with the most recent contact on 10th February 2026, to progress the acquisition of the rights required for the Sea Link project. | 10.03.2026 - The Applicant's Agent emailed the landowner's agent on 25th February 2026 and 2nd March 2026 to request a further meeting in order to receive more substantial feedback on the Heads of Terms. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On 7th April 2026, the Applicant's Agent emailed the landowner's agent to request a meeting to discuss any feedback on the Heads of Terms, however, no response has been received to this or previous attempts to arrange a meeting. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, the Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination however, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On 24th April 2026, the Applicant's Agent had email correspondence with the landowner's agent in relation to additional purchases of land being made by SPR and how these overlap with the Project proposals. Once these purchases are confirmed to have completed, the Applicant will issue revised plans for the areas of land the Applicant is negotiating to purchase from this landowner. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
174 | Michael Neil Copinger Mahony | Suffolk | Yes | RR-3700 | RR-3700 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005629 | REP1-226 | REP1-226 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001307-Michael-Mahony-Written-representations-(WR)-and-summaries-for-any-that-exceed-1500-words.-S224B872C.pdf |  | Suffolk - 2/3 2/26 2/27 2/28 2/29 2/29a 2/32 2/32a 2/33 | Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | No |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. |  |  |  | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - The Applicant's agent met with the landowner and their agent on 23rd February 2026 to discuss the updated class of rights in the land plans at Deadline 4 and the Applicant's proposed activities on this plot. Heads of Terms are not being issued given the existing rights. | 13.04.2026 - The Applicant confirms that its position is that the existing deed of easement dated 2002, already provides the necessary rights to access and carry out the works. The landowner does not agree with this interpretation and has indicated that they may instruct solicitors to challenge the Applicant’s reliance on the deed. A meeting will be arranged with this landowner to further discuss entry under the Deed and agree an appropriate route of access to undertake the works. The Applicant proposes to rely on the existing easement rights and does not intend to enter into a separate licence arrangement, as doing so would undermine the Applicant’s legal position by implying that the existing deed is insufficient. The Applicant has included the land within the Order limits for completeness and, should the landowner object to the exercise of the existing rights, the matter can be addressed through the Temporary Possession powers sought in the Development Consent Order. | 29.04.2026 - On 21st April 2026, the Applicant's Agent emailed the landowner to confirm their position as set out at Deadline 6. The Applicant's Agent has subsequently discussed the position with the landowner's agent and awaits a response in writing. Whilst the Applicant will maintain its position in relation to the existing Deed of Easement, the Applicant will continue to engage with the landowner in relation to the proposed works.
224 | Hazlewood Hall Management Company Limited |  | Yes | RR-1953 | RR-1953 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004809 |  |  | Freehold | Suffolk - 4/13 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
268 & 719 | Janet Francis Howard & Peter Edward Howard |  | No |  |  |  |  | Freehold | Suffolk - 2/2 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
335 & 491 | Lindsay Peter Tomlinson & Sarah Tomlinson | Suffolk | Yes | RR-3196 | RR-3196 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000354 |  |  | Freehold | Suffolk - 5/14 5/15 5/17 5/18 5/19 5/20 5/21 5/22 5/23 5/24 5/25 5/30 5/31 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plan to the landowner's agent on 20th March 2026 and are awaiting feedback. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impact of the proposed works on their residential property. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made
342 | Ernest Alexander Tait Wright | Suffolk | No |  |  |  |  | Freehold/ Occupation | Suffolk - 2/78a 2/78b 2/79 | Class 1. Compulsory Acquisition of land Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Strutt & Parker | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. The Applicant's Agent have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. |  | 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since revised Terms were issued on 10th December 2025. The principle discussions with the landowner’s agent have been in relation to the Option Agreement that the landowner has with Scottish Power Renewables and how this overlaps with the rights that National Grid are seeking. The Applicant’s Agent remains in regular dialogue with the landowner’s agent, with the most recent contact on 10th February 2026 in relation to progressing the acquisition of the rights required for the Sea Link project. | 10.03.2026 - The Applicant's agent emailed the landowner's agent on 25th February 2026 and 2nd March 2026 to request a further meeting in order to receive more feedback on the Heads of Terms. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On 7th April 2026, the Applicant's Agent emailed the landowner's agent to request a meeting to discuss any feedback on the Heads of Terms however no response has been received to this or previous attempts to arrange a meeting. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, the Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all points raised have now been adequately addressed, amendments requested by the landowner's agent in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. As stated at Deadline 5, it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination however, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On 24th April 2026, the Applicant's Agent had email correspondence with the landowner's agent in relation to additional purchases of land being made by SPR and how these overlap with the Project proposals. Once these purchases are confirmed to have completed, the Applicant will issue revised plans for the areas of land the Applicant is negotiating to purchase from this landowner. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
352 & 545 | Andrew Michael Hilliard Heald & Emma May Alexandra Heald | Suffolk | Yes | RR-0274 | RR-0274 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100002978 |  |  | Freehold | Suffolk 2/81 2/83 | Class 1. Compulsory Acquisition of land Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Landbridge | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. | 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowner’s agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. |  | 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 10.02.2026 – The Applicant's Agent held a Teams meeting with the landowner’s agent on 14th January 2026 to discuss the Heads of Terms. Heads of Terms were reissued to the landowners' agent on 21st January 2026. The Applicant's agent had further phone call with the landowner’s agent on 3rd February 2026 to discuss the commercial terms which are still in negotiation. The Applicant’s Agent will continue to engage with the landowner’s agent and it is understood by the Applicant’s Agent that an agreement can be reached before the end of Examination. | 10.03.2026 – The Applicant’s Agent has had regular correspondence with the landowner’s agent including emails and phone calls on 18th February 2026, 20th February 2026, and 26th February 2026. A further phone call was made on 4th March 2026, and an email was sent on 6th March 2026, issuing updated Heads of Terms including revised commercials to the landowner's agent. The Applicant’s Agent has not received any substantial feedback on the Heads of Terms and any comments previously made have been addressed in the most recent iteration of the Heads of Terms. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026 after which the Applicant's Agent is expecting confirmation on whether the Heads of Terms are agreed. A meeting is currently being arranged between the Applicant's Agent and the landowner's agent for w/c 9th March. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
374 | National Highways Limited |  | Yes | RR-3919 | RR-3919 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000388 | REP2-131 | REP2-131 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001734-Sea%20Link%20Deadline%202%20Submission%2028%20November%202025%20FINAL.pdf | Freehold | Suffolk: 7/1 7/16 7/23 7/27 7/28 7/29 7/30 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  |  | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
383 | Jane Ruth Van Lennep |  | No |  |  |  |  | Freehold | Suffolk- 1/98 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
406 & 488 | Simon Nicholas Fulford & Nicola Suzanne Fulford | Suffolk | Yes | RR-5020 RR-3978 | RR-5020 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001141 RR-3978 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005065 | REP1A-151 | REP1A-151 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001478-Nicola-(Ning)-Suzanne-Fulford-Written-summaries-of-oral-submissions-made-at-hearings-held-during-w/c-3-and-w/c-10-November-2025.-S55829990.pdf | Freehold/ Occupation | Suffolk - 2/30 2/31 | Class 9. Temporary Use for Access | No | No |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. |  |  |  | 10.02.2026 - National Grid proposes to rely on existing land rights under the existing Deed. A legal review has been undertaken of the existing Deed and has been found to be appropriate for the Project's needs. As explained in the CAH1, this area of land was included in the Order Limits to ensure all works for the project can be completed within the project's boundary. The Class of Rights have therefore been reduced to Class 8, temporary powers only and as a result voluntary terms for additional rights are not required. | 10.03.2026 - Heads of Terms are not being issued given the existing rights. | 13.04.2026 - Heads of Terms are not being issued given the existing rights. | 29.04.2026 - Heads of Terms are not being issued given the existing Deed of Easement held over this land.
425 | Blackheath Farms Limited | Suffolk | Yes | RR-0641 | RR-0641 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001328 |  |  | Freehold/ Occupation | Suffolk - 2/21 2/22 2/22a 2/22b 2/23 2/23a 2/24 2/25 2/27 2/30 3/35 3/37 3/38 3/39 3/40 3/45 3/46 3/47 3/49 3/51 3/53 3/55 3/56 3/57 3/58 3/59 3/60 3/61 3/62 3/63 3/64 4/1 4/2 4/3 4/4 4/5 4/6 4/7 4/8 4/9 4/10 4/11 4/12 4/13 4/14 4/15 4/16 4/17 4/18 4/19 4/20 4/21 4/22 4/23 4/24 4/25 4/26 4/27 4/28 5/1 5/2 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access Class 10. Land that is not subject to powers of acquisition nor temporary | No | Yes | Brooks Leney | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 10.02.2026 – The Applicant's Agent met with the landowner’s agent on 4th February 2026 to discuss the Heads of Terms. The final points under discussion relate to the extent of restrictions over the land and rights sought for access and drainage rights, pre-entry soil surveys, the depth of agricultural operations permitted over the cable easement and commercial terms. It is believed that all other points in the Heads of Terms are agreed in principle. It is anticipated that agreement will be reached by Deadline 5. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms to the landowner's agent on 3rd March 2026 following a meeting in February. The majority of the clauses in the Heads of Terms are now agreed however there are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights and the commercials are yet to be agreed. It is understood that the landowner's agent is attending an agents group meeting on 23rd March 2026. A follow up meeting has been arranged with the landowner's agent on 31st March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed. It is expected that agreement will be reached by the end of Examination. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
439 | Robert Roy Jonas Nichol | Suffolk | Yes | RR-4545 | RR-4545 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003909 |  |  | Freehold/ Occupation | Suffolk - 1/12 1/13 1/14 1/16 1/18 1/19 1/23 1/26 1/27 1/29 1/31 1/32 1/33 1/34 1/39 1/40 1/44 1/50 1/51 1/74 1/75 1/80 1/81 1/82 1/83 1/84 1/97 1/98 | Class 1. Compulsory Acquisition of land Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 10. Compulsory Acquisition of land | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | 10.02.2026 – Commercial negotiations are well advanced in relation to the freehold acquisition of this land. The Applicant's Agent remains in regular dialogue with the landowner’s agent. Written feedback is awaited and anticipated prior to the meeting scheduled with the landowner’s agent on 12th February 2026. It is understood by the Applicant’s Agent that an agreement will be reached before the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner's agent on 12th February 2026 and 4th March 2026 and good progress has been made in relation to the freehold acquisition. The principles of the Heads of Terms are accepted and the commercials are being finalised. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 6. It is expected that an agreement will be reached before the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised terms to the landowner's agent on 9th March 2026 and it is understood that the landowner and their agent met on 10th March 2026 to discuss the Applicant's revised terms. The Applicant's Agent is awaiting written feedback on the revised terms issued on 9th March 2026 however the Applicant's Agent continues to discuss the purchase offer with the landowner's agent to finalise the commercial elements of the terms. The Applicant's Agent is looking to arrange a further meeting with the landowner's agent before Deadline 7. The Applicant's Agent understands that the landowner is seeking additional specialist advice before agreement can be reached. Whilst it is anticipated that agreement will be reached, due the additional advice required, it is possible that the final terms will be agreed after Examination has closed. | 29.04.2026 - The Applicant's Agent continues to progress discussions with the landowner's agent in relation to the freehold acquisition. On 21st April 2026, the landowner's agent provided written feedback on the terms issued on 9th March 2026. The ongoing discussions are in relation to the commercial elements of the terms and the Applicant's Agent had arranged a meeting with the landowner's agent for 14th May 2026 to finalise matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
461 | Linda June Serpell |  | Yes | RR-3186 | RR-3186 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006071 |  |  | Freehold | Suffolk- 3/18 | Class 9. Temporary Use for Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
476 & 3146 | James John Skellorn & Personal Representative to the Estate of Margaret Anne Bacon | Suffolk | No |  |  |  |  | Freehold/ Occupation | Suffolk - 1/24 1/25 1/35 1/36 1/37 1/38 1/41 1/42 1/43 1/45 1/46 1/47 1/48 1/50 1/52 1/53 1/56 1/57 1/60 1/85 1/86 1/87 1/88 1/90 1/91 2/1 2/2 | Class 1. Compulsory Acquisition of land Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | 10.02.2026 - The Applicant's Agent met with the landowner and their agent on 20th January 2026 to discuss the Heads of Terms. The landowner is engaging proactively with the Applicant’s Agent and the legal mechanism for securing the rights is being explored further to see if a long-leasehold arrangement is suitable. The Applicant's Agent is drafting revised terms which will be re-issued to the landowner and their agent shortly. Additionally, the commercial terms are still under negotiation. It is understood that an agreement will be reached before the end of Examination. | 10.03.2026 - The Applicant's Agent met with the landowners' agent on 12th February 2026 and 4th March 2026. The landowners' agent provided feedback on the Heads of Terms on 12th February 2026 and revised Heads of Terms were issued to the landowners' agent on 27th February 2026 which incorporated the long-leasehold in line with the landowners' request. It is understood that the landowners' agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowners' agent. It is understood that an agreement will be reached before the end of Examination. | 13.04.2026 - There is ongoing discussion between the Applicant's Agent and the landowner's agent in relation to the structure of the transaction based on the rights being sought. The options being explored are freehold acquisition as per the Land Plans, or a long-leasehold interest. The Applicant's Agent has arranged a meeting with the landowner and their agent on 22nd April 2026. Once the specific rights are agreed the outstanding matters to be agreed will be the commercial elements. Although the landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst the Applicant's Agent anticipates that agreement will be reached, it is possible that this will be after the end of Examination. | 29.04.2026 - On 17th April 2026, the Applicant's Agent issued revised Heads of Terms to the landowner's agent. On 22nd April, the Applicant's Agent met with the landowner and their agent to discuss the possible options for the transaction, these being freehold acquisition or a long-leasehold interest. The Applicant is continuing to discuss these options with the landowner and their agent in addition to the commercial terms. The Applicant's Agent is arranging a further meeting with the landowner's agent in May 2026 to progress these discussions. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
485 | Jean Frances Flick |  | No |  |  |  |  | Freehold | Suffolk- 3/18 | Class 9. Temporary Use for Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
508 | Peter Murray Mann | Suffolk | No |  |  |  |  | Freehold / Leasehold / Occupation | Suffolk - 2/20a 2/22 2/22a 2/22b 2/23 2/23a 2/24 2/25 2/40 2/41 2/43 2/44 2/49 2/50 2/51 2/52 2/53 2/54 2/55 2/90 2/102 2/103 2/104 3/1 3/2 3/3 3/4 3/5 3/6 3/7 3/8 3/9 3/10 3/11 3/12 3/13 3/14 3/15 3/16 3/17 3/18 3/19 3/20 3/20a 3/20b 3/21 3/21a 3/21b 3/22 3/22a 3/38 3/39 3/40 3/41 3/42 3/45 3/46 3/47 3/49 3/51 3/53 3/55 3/56 3/57 3/59 3/63 4/2 4/4 4/5 4/6 4/8 4/9 4/10 4/11 4/14 4/15 4/16 4/17 4/19 4/24 4/25 4/26 5/1 5/2 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | Brown & Co | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | 10.02.2026 – The Applicant's Agent is continuing to engage with the landowner and their agent in relation to the Heads of Terms. The landowner has an Option Agreement with Scottish Power Renewables (SPR) and they are seeking consent from SPR to enter into an agreement with National Grid as the developments overlap. The Applicant's Agent had a phone call with the landowner and their agent on 29th January 2026 and met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. Terms which remain under discussion are practical matters such as pre-entry soil surveys and access and drainage rights and as well as commercial matters. Due to the requirement for consent from a third party it is not possible to say if agreement can be reached before the end of Examination but the Applicant’s Agent remains committed to engaging with the landowner’s agent to agree the Heads of Terms in principle subject to consent from third parties. | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent and the third party consent requirements. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, whilst we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle by the end of the Examination, the third party consents required are likely to take longer to agree. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. On 21st April 2026, The Applicant's Agent had a phone call with the landowner and their agent to discuss the proposals to mitigate any impact to the irrigation infrastructure, which has been agreed by both parties. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
533 & 2746 & 2747 | Lady Patricia Ann Hopkins & Joel Hopkins & Abigail Hopkins |  | Yes | RR-0010 | RR-0010 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005521 |  |  | Freehold | Suffolk - 4/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
548 | East Suffolk Council | Suffolk | Yes | RR-1240 | RR-1240 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004405 | REP3A-016 | REP3A-016 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002216-ESC%20Relevant%20Representation%20on%20proposed%20changes%20(CR1)%20to%20the%20Sea%20Link%20project%20-%20DL3A%20-%2019.1.26.pdf | Freehold | Suffolk - 6/3 6/5 6/6 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access | No | Yes |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. A further version of the Heads of Terms was re-issued in August 2025. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. |  | 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | 10.02.2026, The Applicant’s Agent emailed the landowner’s agent on 13th and 21st January 2026 to clarify their queries on the Heads of Terms in relation to the cable easement width, the extent of restrictions over the land and rights sought for access and drainage and issue revised Heads of Terms. The Applicant’s Agent is awaiting further written feedback from the landowner’s agent. A meeting is scheduled for 9th February 2026 to discuss the revised Heads of Terms. The commercial terms remain in negotiation. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 – The Applicant's Agent held a Teams meeting with the Landowner's Agent on 9th February 2026 where they discussed ongoing queries, in particular in relation to restrictions over the Easement width at surface level. The Applicant's Agent issued confirmation of outstanding points and emailed the Landowner's Agent on the 18th February 2026 to arrange a further meeting. It is anticipated that the remaining outstanding matters will be addressed in the next revision of the Heads of Terms which are due to be issued imminently. It is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The Applicant's Agent issued revised Heads of Terms to the landowner's agent on 17th March 2026 to address the landowner's concerns in relation to restrictions over the easement at surface level and request comparable land value data. On 26th March 2026, the Applicant's Agent had a Teams meeting with the landowner's agent to discuss the amendments to the Heads of Terms, at this meeting it was agreed further amendments were required. Following this meeting, further revisions to the Heads of Terms were made in relation to restrictions over the easement at surface level and issued to the landowner's agent on the same day. The interest here is Aldeburgh beach and as such The Applicant does not perceive the restrictions imposed by the easement to be limiting in the Council's use and control of the land as beach. The Applicant believes that the terms are agreed in principle with the landowner's agent, subject to feedback from the landowner's agent in relation to the commercial proposals. The Applicant's Agent followed up with the landowner's agent for feedback on the commercial proposals on 9th April 2026. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent has not yet received any feedback in relation to the revised Heads of Terms issued to the landowner's agent on 26th March 2026. The Applicant's Agent sent a follow up email on 17th and 24th April 2026 however it is understood that the landowner's agent is out of office until 30th April 2026. The Applicant believes that the revised Heads of Terms issued on 26th March 2026 addressed the landowners outstanding concerns and the Applicant is awaiting feedback on the commercial proposal from the landowner. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
579 | Elisabeth Lesley Lindores | Suffolk | No |  |  |  |  | Freehold | Suffolk - 5/27 5/29 5/32 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Heads of Terms have been agreed, discussions are ongoing between legal advisors to draft and agree the Option Agreement. 18.11.2025 - National Grid's solicitors have been engaging with the landowner’s solicitors to progress the Option Agreement. |  | 09.01.2026 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | 10.02.2026 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | 10.02.2026 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | 13.04.2026 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | 29.04.2026 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. |  | Yes
588 | Timothy Peter Singleton |  | No |  |  |  |  | Freehold | Suffolk - 7/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
598 & 730 | David John Beatton & Sarah Ann Beeton | Suffolk | No |  |  |  |  | Freehold | Suffolk - 5/13 5/14 5/16 5/17 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in August 2025. On 12th February 2026 a meeting is arranged with the landowners' agent to obtain detailed feedback on the Heads of Terms. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. A meeting has been arranged with the landowner and their agent on 14th April, after which the Applicant expects that agreement will be reached. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is meeting with the landowner and their agent on 14th April 2026 to discuss the most recent Heads of Terms and construction impacts to their property. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Whilst it is anticipated that an agreement will be reached with this landowner, it is likely that this will be after the end of Examination. | 29.03.2026 - On 14th April 2026, the Applicant's Agent met with the landowner and their agent to discuss Heads of Terms and the impacts of the future restrictions of the easement on their property. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
618 | Royal Society for the Protection of Birds | Suffolk | Yes | RR-4651 | RR-4651 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100003786 | REP1-157 REP1-158 REP1-159 REP1-160 REP1-165 | REP1-157 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001402-RSPB%20Summary.pdf REP1-158 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001399-RSPB.pdf REP1-159 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001400-RSPB%20Appendix.pdf REP1-160 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001401-RSPB%20References.pdf REP1-165 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001414-RSPB%20submission%20in%20advance%20of%20ISH1.pdf | Freehold/ Occupation | Suffolk - 5/26 5/28 5/34 6/1 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access | No | Yes | Bidwells | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. |  | 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | 10.02.2026 – The Applicant's Agent received further comments on the Heads of Terms from the landowner’s agent on 21st and 28th January 2026. The final points under discussion are practical points around ongoing management of the RSPB reserve and records of condition ahead of works starting. It is expected that these matters can be resolved swiftly and ahead of Deadline 5. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent issued revised Heads of Terms on 26th February 2026 that addressed the outstanding points raised at previous meetings and correspondence with the landowner and their agent. It is believed that the Heads of Terms are agreed between the Applicant's Agent and the landowner's agent subject to final approval from the landowner. The landowner is working with the Applicant to agree a Statement of Common Ground which addresses their wider concerns around the Proposed Project. A meeting is being arranged with the landowner's agent ahead of Deadline 6 and it is anticipated that an agreement can be reached prior to the close of Examination. | 13.04.2026 - The landowner's agent provided comments on the Heads of Terms and feedback from the Suffolk Agents meeting by email on 25th March 2026 and the Applicant's Agent responded to this on 26th March 2026 to set out the Applicant's position. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss Heads of Terms and the feedback from the Suffolk agents meeting on 23rd March 2026. The Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from this meeting on 9th April 2026, which included updates on the soil condition surveys, reinstatement provisions and commercial matters. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026.Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Whilst it is anticipated that an agreement will be reached, the landowner has made the Applicant aware of their internal review and sign off process once Heads of Terms are finalised and this is likely to extend beyond the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms and the Statement of Common Ground. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made
679 | June Bloomfield | Suffolk | No |  |  |  |  | Freehold | Suffolk - 3/54 3/62 3/64 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access | No | Yes | Brown & Co | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  | 26.11.2025 – The Applicant’s land agent, Dalcour Maclaren have engaged with the landowner about the additional plots. Heads of Terms will be issued if appropriate. | 09.01.2026 – Dalcour Maclaren issued template Heads of Terms to the landowner’s agent on 4th December 2025 ahead of the Change Request being accepted. Dalcour Maclaren issued populated Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 10.02.2026 –. The Applicant's Agent met with the landowner’s agent on 3rd February 2026 to discuss the Heads of Terms. The points still under negotiation are practical matters including pre-entry soil surveys, and access and drainage rights in addition to the commercial terms. It is believed an agreement will be reached before the end of Examination | 10.03.2026 - The landowner’s agent provided feedback on the Heads of Terms on 3rd February 2026. On 26th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. The Applicant's Agent met with the landowner's agent on 4th March 2026 to discuss the revisions. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. A follow up meeting is arranged with the landowner's agent for 30th March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. It is believed an agreement will be reached before the end of Examination. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026, following the agents group meeting on 23rd March 2026, to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. It is expected that agreement will be reached before the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and will be agreed with the landowner's agent soon after issuing. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made
692 | Ian Charles Rix | Suffolk | Yes | RR-5010 | RR-5010 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005367 | REP1-203 REP4-171 REP4-172 | REP1-203 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001416-Ian%20Rix.pdf REP4-171 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002495-David%20Rix.pdf REP4-172 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002356-The-Rix-Family-All-parties-who-made-oral-representations-at-the-hearings.pdf | Freehold Occupation | Suffolk - 1/12 1/49 1/49a 1/50 1/58 1/64 1/67 1/69 1/70 1/71 1/72 1/73 1/89 1/91 1/92 1/93 1/94 1/95 1/96 1/98 1/99 1/100 2/2 2/3 2/5 2/6 2/7a 2/7b 2/10 2/10a 2/11 2/11b 2/14 2/15 2/15b 2/16 2/17 2/18 2/20b 2/20c 2/20d 2/20e 2/20f 2/36 2/37 2/38 2/40 2/42 2/43 2/46 2/47 2/48 2/49 2/53 2/62 2/99 7/1 7/13 7/15 7/17 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 7. Compulsory Acquisition of Rights – Mitigation Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Brown & Co | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. | 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. | 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 10.02.2026 - The Applicant's Agent discussed the revised Heads of Terms with the Landowner’s agent on 13th January 2026. The Applicant's Agent met with the landowner’s agent on 3rd February 2026 to discuss outstanding comments in relation to the Heads of Terms and a further meeting was held on 4th February with the landowner and their agent to discuss their outstanding points of objection. In relation to the Heads of Terms, outstanding areas to reach agreement on include to pre-entry soil surveys, access and drainage rights, the form of consent required from Scottish Power Renewables (SPR) and commercial matters. In relation to the landowner’s outstanding points of objection: The Applicant is reviewing plot 2/20 and committed to providing an inset plan in the OLEMP to show what is happening in more detail. There will also be further discussion in relation to maintaining an access between plots 2/37 and 2/20. Hedge (plots 1/93, 1/94, 1/99, 1/100) – the Applicant’s requirement and justification for the proposed hedge was discussed at the meeting on 4th February 2026. Whilst the rights for this hedge are being negotiated with the landowner’s agent, there is a fundamental difference in opinion on this particular issue. Width of substation access track - the Applicant confirmed that the existing 33kv line needs to be diverted alongside the access road, also allowing space for mitigation for the access road and avoiding mature trees. Responding to comments about the are of land take compared to SPR - the Applicant has confirmed that there is a wider area is to route the cables through the SPR landscape mitigation. Being aware of outline landscape mitigation plan for SPR, the DC cable route has been designed to limit impacts on SPR proposals. It is hoped that an agreement in principle on the specific clauses in the Heads of Terms can be reached whilst the Applicant works to provide further information in relation to the outstanding objection points | 10.03.2026 -The Applicant's Agent continues to engage with both the landowner and their agent. A meeting with the landowner’s agent was held on 4th March 2026 to discuss revisions made to the template Heads of Terms since the meeting on 3rd February 2026. Revised Heads of Terms were issued to the landowner’s agent on 9th March 2026 to address a number of outstanding points. Matters previously raised by the landowner including: the requirement for hedge planting (plots 1/93, 1/94, 1/99, 1/100); a right of access for agricultural machinery between plots 2/37 and 2/20d; extent of the land sought for the access road (plots 2/7b, 2/7a, 2/20b); mitigation planting (plot 2/20c) are still points of contention. Voluntary agreement discussions are still progressing with the landowner and the landowner’s agent. As a result of the number of points under discussion and the interaction with Scottish Power Renewables (SPR), it is not anticipated that agreement will be reached before the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner and the beneficiary of the Option Agreement (SPR) covering the majority of the land at the earliest opportunity. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues.
755 | Suffolk County Council |  | Yes | RR-5209 | RR-5209 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100001774 | REP3-122 REP3A-031 REP4-149 | REP3-122 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002081-Suffolk%20County%20Council%20-%20Comments%20on%20submissions%20received%20by%20Deadline%202.pdf REP3A-031 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002324-Suffolk%20County%20Council%20Relevant%20Representation%20on%20Changes%20to%20Sea%20Link%20Proposals.pdf REP4-149 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002617-Sea%20Link%20CAH1%20Post%20Hearing%20Submission.pdf | Freehold/ Occupation | Suffolk - 1/1 1/3 1/12 1/14 1/16 1/50 1/51 1/53 1/74 1/75 1/88 1/89 1/91 1/96 1/97 1/98 2/2 2/3 2/20 2/21 2/22 2/27 2/30 2/34 2/40 2/43 2/49 2/52 2/53 2/62 2/67 2/73 2/75 2/77 2/100 3/18 3/35 3/37 3/58 3/60 3/61 3/62 3/64 4/1 4/3 4/13 4/15 5/5 5/6 5/14 5/17 5/19 5/34 6/3 6/5 7/1 7/4 7/13 7/15 7/16 7/17 7/22 7/23 7/24 7/25 7/27 7/28 7/29 7/30 7/31 | Class 1. Compulsory Acquisition of land Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access Class 10. Land that is not subject to powers of acquisition nor temporary use | Yes | No |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. |  |  |  |  | 10.3.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC.
791 | Carlyon Estates Limited | Suffolk | [5 empty] | Freehold | Suffolk: 6/4 | Class 3. Compulsory Acquisition of Rights - Underground Cable System | No | [7 empty] | 10.03.2026 - This landowner has been identified as the owner of Suffolk plot 6/4 which is unregistered. The Applicant's Agent issued Heads of Terms to the landowner on 9th March 2026. | 13.04.2026 - The Applicant's Agent has spoken to the landowner's representative, as confirmed by the Companies House address. The Landowner's representative confirmed that they have forwarded all correspondence to their client. Due to the time scales, it is unlikely that agreement can be reached before the end of Examination. The Applicant's Agent is committed to progressing voluntary agreement. | 29.04.2026 - The Applicant's Agent has arranged a Teams meeting with the landowner on 29th April 2026 to discuss the Project proposals and receive their feedback on the Heads of Terms. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
831 | Personal Representative to the Estate of Terence James Martin Haworth | Suffolk | Yes | RR-5322 | RR-5322 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004967 | REP1-290 REP1A-199 REP3-127 REP4-174 | REP1-290 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001421-TJ%20Haworth-Culf.pdf REP1A-199 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002028-Cllr%20Haworth-Culf%20SCC%20Cllr%20%209th%20January%202026.pdf REP3-127 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001449-T-J%20Haworth-Culf.pdf REP4-174 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002492-T-J%20Haworth.pdf | Freehold | Suffolk - 5/3 | Class 3. Compulsory Acquisition of Rights – Underground Cable System | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. |  | 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since significant amendments were made to the terms and reissued to the landowner’s agent in August 2025. A meeting is scheduled with the landowner and their agent on 11th February 2026 to discuss landowner/holding specific terms . On 12th February 2026 a meeting is arranged with the landowner’s agent to obtain detailed feedback on the overall Heads of Terms as it relates to all of their landowners. At this stage it is understood that an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5 following receipt of the feedback on the Heads of Terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 11th February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. The landowners primary concerns are in relation to construction impacts on their adjoining residential property. Whilst it is expected that the Heads of Terms will be agreed in principle by Deadline 6, further detail is required on the programme of works in proximity to their residential property before Heads of Terms will be signed. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent beyond the close of Examination to mitigate any potential disruption.
1205 | Pamela Tile |  | No |  |  |  |  | Freehold | Suffolk - 5/19 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
1270 | Georgeta Catargiu (As Personal Representative to the Estate of Martin Peter Handscombe) | Suffolk | No |  |  |  |  | Freehold | Suffolk - 2/3 2/4 2/8 2/8a 2/9 | Class 1. Compulsory Acquisition of land Class 5. Compulsory Acquisition of Rights – Access Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Strutt & Parker | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. |  | 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, which included a further revision of the Heads of Terms. Further feedback is anticipated. | 10.02.2026 – The Applicant's Agent has not received substantive feedback on the Heads of Terms since revised Terms were issued on 12th December 2025. The principle discussions with the landowner’s agent have been in relation to the Option Agreement that the landowner has with Scottish Power Renewables and how this overlaps with the rights that National Grid are seeking. The Applicant’s Agent remains in regular dialogue with the landowner’s agent, with the most recent contact on 10th February 2026, to progress the acquisition of the rights required for the Sea Link project. | 10.03.2026 - The Applicant's agent emailed the landowner's agent on 25th February 2026 and on 2nd March 2026 to request a further meeting in order to received more substantial feedback on the Heads of Terms. At this point it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 13.04.2026 - On 7th April 2026, The Applicant's Agent emailed the landowner's agent to request a meeting to discuss any feedback on the Heads of Terms however no response has been received to this or previous attempts to arrange a meeting. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5, it is not envisaged that the landowner's agent will meaningfully engage sufficiently to agree the Heads of Terms by the end of Examination but, as has been demonstrated to date, the Applicant's Agent will continue to attempt to progress matters to reach a voluntary agreement with this landowner. | 29.04.2026 - On 24th April 2026, the Applicant's Agent had email correspondence with the landowner's agent in relation to additional purchases of land being made by SPR and how these overlap with the Project proposals. Once these purchases are confirmed to have completed, the Applicant will issue revised plans for the areas of land the Applicant is negotiating to purchase from this landowner. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made.
1365 & 1366 & 2336 | Kevin Russell Armstrong & Jennifer Louise Armstrong & Lily Armstrong |  | Yes | RR-2996 | RR-2996 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100000852 | REP1-205 | REP1-205 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001408-Jennifer%20Armstrong.pdf | Freehold | Suffolk - 1/12 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
1367 & 1368 &1369 | Laurence Justin Dowley & Emma Louise Dowley & Cripps Trust Corporation Limited (as trustee to The Dowley Family Discretionary Settlement 2018) |  | No |  |  |  |  | Freehold | Suffolk - 1/12 1/74 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
1668 | Aldeburgh Golf Club Limited | Suffolk | Yes | RR-0093 | RR-0093 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100004387 |  |  | Freehold | Suffolk - 5/4 5/5 5/6 5/7 5/8 5/9 5/10 5/11 5/12 5/17 5/19 | Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 5. Compulsory Acquisition of Rights – Access Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | Clarke & Simpson | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. | 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. |  | 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | 10.02.2026 - The Applicant's Agent has not received substantive feedback on the Heads of Terms since amendments were made to the terms and reissued to the landowner’s agent in December 2025. The Applicant's Agent met with representatives of Aldeburgh Golf Club and their agent on 29th January 2026. Discussions were primarily around agreeing accommodation works, ensuring that the Golf Club is not impacted significantly during construction. Discussions are ongoing around the golf club extension and reservoir development. Looking likely to reach agreement in principle, notwithstanding views expressed more widely by the membership of the golf club. The Applicant has changed the route of the cable around the golf course and has worked very closely with them in the last three or four years. The Applicant's Agent has a meeting arranged with the landowner’s agent on 12th February 2026 to obtain further detailed feedback on the overall Heads of Terms. It is thought an agreement can be reached before the end of Examination but a further update will be provided at Deadline 5. | 10.03.2026 - The Applicant's Agent met with the landowner and their agent on 23rd February 2026 and also met with the landowner’s agent on 12th February 2026 and 4th March 2026. The landowner’s agent provided feedback on the Heads of Terms on 12th February 2026. On 27th February 2026 the Applicant’s Agent shared a revised version of the Heads of Terms to address feedback received. There are some minor outstanding practical matters still under discussion, namely soil condition surveys and reinstatement and access and drainage rights. It is understood that the landowner’s agent is attending an agents group meeting on 23rd March 2026. Following this meeting we expect to be able to confirm that all matters in relation to the voluntary terms are agreed in principle save for commercial terms as the Applicant’s Agent awaits comparables from the landowner’s agent. The landowner is working with the Applicant to agree a Statement of Common Ground (SoCG) which addresses their wider concerns around the project including construction accommodation works, it is anticipated that agreement on the Heads of Terms will not be reached until the SoCG is agreed by both parties. | 13.04.2026 - On 20th March 2026, The Applicant's Agent issued a revised access and drainage plans to the landowner's agent and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, the Applicant's Agent provided feedback on the requested amendments to the Heads of Terms from the agents meeting to the landowner's agent on 9th April 2026, which included updates on the soil condition surveys and reinstatement provisions. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The Applicant's Agent is awaiting comparable evidence for the land values from the landowner's agent. Document Number 9.142 Draft Statement of Common Ground with Aldeburgh Golf Club is in active discussion. The draft Statement of Common Grounds has been issued to the Golf Club ahead of Deadline 6 and this document includes comments on the impact on the attractiveness of the course as raised by the golf club. It is anticipated that agreement on the Heads of Terms will not be reached until these accommodation measures and the Statement of Common Grounds are agreed by both parties. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with this landowner and their agent to mitigate any potential disruption. Document Number 9.142 Draft Statement of Common Ground with Aldeburgh Golf Club has been signed by both parties. This sets out the matters that will continue to be discussed and agreed ahead of construction, once these discussions points have progressed further it is expected that Heads of Terms will be agreed.
2286 | Sophie Clare Langmead |  | No |  |  |  |  | Freehold | Suffolk - 4/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
2298 | ScottishPower (UK) Renewables Limited | Suffolk | Yes | RR-4903 | RR-4903 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005920 | REP1-139 REP3A-014 | REP1-139 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001105-Scottish-Power-Renewables-Requests-by-affected-persons-(defined-in-section-59(4)-of-the-Planning-Act-2008-(PA2008))-to-be-heard-at-a-compulsory-acquisition-hearing-(CAH).-S5AA6A0E0.pdf REP3A-014 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002217-Deadline%203A%20Submission.pdf | Freehold/ Occupation | Suffolk: 2/78 2/79a | Class 1. Compulsory Acquisition of land Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | No | Yes | In House |  |  |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | 10.02.2026 - Negotiations are positively ongoing with SPR in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. | 10.03.2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and SPR's representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that SPR intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge SPR's interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with SPR to understand their land interests. The Applicant proposes to issue Heads of Term to SPR following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with SPR/EA1N/EA2 and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site.
2460 | J T Pegg & Sons Limited | Suffolk | No |  |  |  |  | Freehold | Suffolk- 1/5a | Class 10. Land that is not subject to powers of acquisition nor temporary | Yes | No |  |  | 18.11.2025 – The applicant will engage with the affected party to negotiate the land rights required |  |  | 30.1.2026- Further to a review with the Applicant's engineering, cabling and consents team. This plot class of right is able to change to Class 10 where no powers of acquisition or temporary use is required. | 30.1.2026- Further to a review with the Applicant's engineering, cabling and consents team. This plot class of right is able to change to Class 10 where no powers of acquisition or temporary use is required. | 13.04.2026- Further to a review with the Applicant's engineering, cabling and consents team. This plot class of right is able to change to Class 10 where no powers of acquisition or temporary use is required. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
2748 | Sarah Younger |  | No |  |  |  |  | Freehold | Suffolk- 4/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3202 | Henry John Rix |  | No |  |  |  |  | Freehold | Suffolk - 2/3 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3446 & 3447 | Andrew Charles Clayton-Payne & Ghalia Clayton- Payne |  | Yes | RR-5687 RR-5794 | RR-5687 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006967 RR-5794 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100006969 |  |  | Freehold | Suffolk- 7/1 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3448 | Benhall Developments Limited |  | No |  |  |  |  | Freehold | Suffolk- 7/1 7/4 | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Yes | No |  |  |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3519 | George William Barrington-Phillips |  | No |  |  |  |  | Freehold | Suffolk- 3/58 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
3520 | Connie Amber Peck |  | No |  |  |  |  | Freehold | Suffolk- 3/58 | Class 5. Compulsory Acquisition of Rights – Access | Yes | No |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 18.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.12.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 09.01.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.02.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 10.03.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network.
2569 | East Anglia One North Limited | Suffolk | Yes | RR-1415 | RR-1415 Relevant Representations ¦ Representation by East Anglia ONE North Limited | REP2-046 REP3-084 REP3A-014 REP4-113 | REP2-046 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001798-Deadline%202%20Submission.pdf REP3-084 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002060-Response%20to%20ExQ1%20for%20SPR_%20EA1NL%20and%20EA2L.pdf REP3A-014 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002217-Deadline%203A%20Submission.pdf REP4-113 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002542-Appendix%201%20-%20EA1NL_EA2L_SPR(UK)%20Ltd%20-%20DL4%20submission%20-%20Written%20Summary%20of%20Oral%20Case%20-%20CAH1.pdf | Freehold | Suffolk - 2/5a 2/6a 2/7 2/11b 2/12 2/13 2/15a 2/20 2/20a 2/32 2/35 2/36a 2/42a 2/46a 2/47a 2/55 2/57 2/58 2/59 2/60 2/61 2/63 2/64 2/65 2/68 2/69 2/70 2/71 2/72 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | In House |  |  |  |  | 10.02.2026 - Negotiations are positively ongoing with SPR in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. | 10.03.2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA1N representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA1N intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA1N interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA1N to understand their land interests. The Applicant proposes to issue Heads of Term to SPR following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site.
3586 | East Anglia Two Limited | Suffolk | Yes | RR-1416 | RR-1416 Relevant Representations ¦ Representation by East Anglia TWO Limited | REP2-046 REP3-084 REP3A-014 REP4-113 | REP2-046 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001798-Deadline%202%20Submission.pdf REP3-084 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002060-Response%20to%20ExQ1%20for%20SPR_%20EA1NL%20and%20EA2L.pdf REP3A-014 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002217-Deadline%203A%20Submission.pdf REP4-113 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002542-Appendix%201%20-%20EA1NL_EA2L_SPR(UK)%20Ltd%20-%20DL4%20submission%20-%20Written%20Summary%20of%20Oral%20Case%20-%20CAH1.pdf | Freehold | Suffolk - 2/5a 2/6a 2/7 2/11b 2/12 2/13 2/15a 2/20 2/20a 2/32 2/35 2/36a 2/42a 2/46a 2/47a 2/55 2/57 2/58 2/59 2/60 2/61 2/63 2/64 2/65 2/68 2/69 2/70 2/71 2/72 | Class 1. Compulsory Acquisition of land Class 2. Compulsory Acquisition of Rights – Overhead Line Class 3. Compulsory Acquisition of Rights – Underground Cable System Class 6. Compulsory Acquisition of Rights – Drainage Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure Class 9. Temporary Use for Access | No | Yes | In House |  |  |  |  | 10.02.2026 - Negotiations are positively ongoing with SPR in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. | 10.03.2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA2 and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site.