## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 7 Submission version 2 - Tab E Benthic Ecology only.
For:
The construction and operation of Sea Link Energy Cable.
Planning Inspectorate Reference ENO20026
18th September 2026

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Sea Link examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - Suffolk Onshore B - Kent Onshore C- Development Consents Order D - Physical Environment E - Benthic Ecology F - Marine Mammals G - Marine Ornithology H - Sufolk and Essex Coast & Heaths DL The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## E - Benthic Ecology
Point | Point Number(s) from Appendix E RR-3920 | Taken from Natural England’s Relevant and Written Representations Sea Link Energy Cable Appendix E - Benthic Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 3a | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved | Applicant's Comments at Deadline 7 (inresposne to NE D6 R&I Log submission) [REP7-258] | Consultation, actions, progression at SoS RFI 1 | RAG
1 | E1 | The Environmental Statement should be updated to consider all potential pathways of effect on intertidal and subtidal benthic habitats |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Part Progressed. Please see Appendix E7. |  | No | The specifics for this general comment have been addressed and responded to in the specific rows below and in previous specific response to the specific queries. The Applicant believes it has updated all habitats and pathways identified as missing or incomplete including updates to peat and clay exposures, subtidal chalk, reefs and seacaves as per Thanet Coast SAC, updates to Sabelleria and mussel beds sensitivity and as per their distribution in the corridor near Goodwin Sands MCZ, quantification of ciralittoral soft rock habitats etc. The latest updates relating peat and clay exposures and quantification of ciralittoral soft rock habitats were provided at Deadline 6 Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. Additional information on areas of sandwave levelling and cable protection have also been provided in Application Documet 6.2.4.2 (G) submitted at Deadline 7. If there are specific pathways or habitats still missing the Applicant requests NE to please provide specifics to ensure they are addressed as the Applicant has been unable to identify anything outstanding. | Partially resolved. However, unresolved issues remain. See R&I Log points: 2, 5, 6, 8, 12, 17, 25 & 41.
2 | E2, E12 | Maximum Design construction footprints should be reviewed and updated to remove any ambiguity. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Part Progressed. Please see Appendix D7 and E7. |  | No | A number of updates have been made to the Project Description chapter during the examination and additional technical notes provided, particularly in relation to construction activities at Pegwell Bay (Application Document 9.13 (D) Pegwell Bay Construction Method Technical Note [REP6-104]). These updates have been incorporated into various iterations of benthic ecology ES chapter with updates to relevant sections of the impact assessment also provided where required. Further updates have been included in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology submitted at Deadline 7 following a call with NE on 16/04/2026 to provide further clarification in relation to the use of cable rollers at the Kent Landfall. Further information has also been provided in relation to cable protection in protected sites. | Unresolved. Natural England highlights that landfall methods at Pegwell Bay remain uncertain and that it is unclear if the MDS and WCS have been presented or assessed.
3 | E3, E14, E37 | Natural England advises that benthic mitigation measures avoid, reduce, mitigate impacts to the most sensitive Section 41 NERC Priority Habitats. The Applicant should consider all mitigation options, including bundling of the export cables for each project and micro-siting of cables to ensure permanent impacts to Section 41 Habitats are avoided/reduced wherever feasible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. Please see responses to ExQ2 BE 9 and 10 in Appendix K5 in our deadline 5 submissions |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. |  | No | The Applicant has updated Commitment BE05 in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) to provide further detail on mitigation measures for benthic habitats of principal importance. The updated wording is provided below for reference: BE05: As secured under the dML, in accordance with the Environmental Principles set out in the Outline Cable Specification and Installation Plan, where benthic habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species) are identified during pre-construction surveys, and additional mitigation is required to avoid or reduce impacts impact on these habitats, the Undertaker must prepare a Benthic Mitigation Plan. Any necessary Benthic Mitigation Plan(s) must be submitted to and approved in writing by the MMO prior to Work 6 in the dML commencing and should include a timetable for implementation of the mitigation and details of any necessary monitoring. Any agreed mitigation and/or monitoring must be implemented in accordance with the agreed timetable. A monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan will be submitted to the MMO (unless otherwise agreed in writing by the MMO) within three months of the 'as-built survey'. The Applicant has also included a new commitment BE06: All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. An outline IPMP (Application Document 9.140 Outline In-Principle Monitoring Plan) was submitted at Deadline 6. | Partially resolved. Natural England welcomes the adoption of BE05 and BE06. However, the wording requires further revision to strengthen the commitments to ensure permanent impacts to NERC Section 41 Habitats are avoided/reduced wherever feasible. BE05 - It is not immediately clear what Work Plan 6 includes and therefore, needs to be more explicit. But we would expect that the benthic mitigation plan to be agreed prior to any seabed preparation works being undertaken. Furthermore, the benthic mitigation plan must be informed by the findings of a completed and agreed pre-construction baseline survey. The use of the 'as-built' survey is confusing and therefore we request clarity and alignment with standard conditon working.
4 | E4, E32 | The Applicant has not committed to removing cable protection at the Project's end of life. Natural England strongly advises that commitment is secured through DCO for the removal of all infrastructure at the time of decommissioning, both within and outside of designated sites. An Outline Decommissioning Plan should be provided at the consenting phase to detail the approach to decommissioning. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. We welcome the submission of [REP4-091] 9.93 (A) Offshore Decommissioning Technical Note . However, it hasn't addressed our concerns. Please see Appendix E Point E.20 to our Deadline 5 submissions |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | No | The Applicant has responded previously to this point (Application Document 9.34.1 Applicant's Detailed Responses to Relevant Representations identified by the ExA [REP1-111] noting that given the operational life of the marine cables is between 40 and 60 years, taking account of potential future changes to regulatory requirements and industry best practice, the approach to decommisioning may also be subject to change depending on requirements at end of asset life and therefore cannot be confirmed at this stage in the process. However, Application Document 9.92 (C) Outline Cable Specification and Installation Plan (Tracked) [REP6-137], does state that "The Applicant will factor in the removability of cable protection when identifying the external cable protection for the Proposed Project dependent on its use. The Applicant will ensure it uses all available best practice guidance for cable decommissioning in its decision making prior to construction and at the time of decommissioning". This is also included as commitment GM08 in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) Application Document 9.93 (A) Offshore Decommissioning Technical Note [REP4-091] also set outs the overarching principles for decommissioning which will be adhered to in the preparation of a Decommissioning Plan. | Unresolved. No change in Natural England's position.
5 | E5, E24 | The Environmental Statement should be updated with an appropriately considered and evidenced assessment of the sensitivity of all benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification required around the assessment of impacts (including Coralline Crag). |  | No change |  | Part Resolved. While we welome updates to the Benthic Chapter on the sensitivity of some receptors. Please see Apendix E5 to our Deadline 5 submission where we advise that assessments are updated. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Partly Resolved Natural England advises that the document should be updated to include a ‘high’ sensitivity rating for subtidal chalk to physical disturbance impacts. |  | No | The sensitivity of benthic habitats identified by NE have been updated in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. Specifically this included changes to the sensitivity for sea caves, reefs, peat and clay exposures and sublittoral chalk. | Partially resolved. Issue resolved for reef, sea caves and peat and clay exposures due to updated sensitivity information. As previous advised at Deadline 7, Natural England highlights that no sensitivity information is provided for subtidal chalk. Whilst the sensitivity score for peat and clay exposures may be intended to also apply to subtidal chalk, this is unclear as written.
6 | E6, E25 | All benthic receptors within the Zone of Influence should be characterised and assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on indirect impacts to designated sites |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | No | All benthic habitats within the zone of influence have now been assessed. For example, habitats such as sea caves and reefs were updated in relation to SSC and depositon effects in particular at Deadline 6 in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. | Partially resolved. Natural England does not consider subtidal chalk and peat and clay exposures to have been adequately characterised and assessed. NE refers to our advice provided at Deadline 7 which describes how chalk and clay is likely to be periodically covered and uncovered by a thin veneer of sediment, but has the potential to be damaged or destroyed by physical disturbance. Therefore, NE advised that areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, should be fully characterised and considered the same as outcropping chalk and clay within assessments.
7 | E7 | Further assessment of impacts from sandwave levelling on benthic receptors is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Natural England advises in Appendix E5 of our D5 submission that to resolve this issue a Sandwave Levelling management plan is required. |  | No Change. Please see Apendices D6, E6 and K6 to our Deadline 6 submission in relation to further advice in relation to sandwave levelling |  | Part Resolved. Please see Appendix D7 where we set out the further commitments that are required |  | No | The Applicant has committed to "avoiding relocating any sediment to with 50m of any Annex II Sabellaria spinulosa reef identified during pre-construction surveys and/or adjacent to and updrift of sandwaves". This commitment (BE07) is included in Application Document Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC). Further updates on sandwave levelling have been included in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology submitted at Deadline 7. | Requires revision - new issue. Natural England advises that the wording of BE07 requires revision. Sediment should not be relocated within 50 m of Annex I Sabellaria spinulosa reef or any NERC Act Section 41 Habitat of Principal Importance (e.g. blue mussel beds). Separately, Natural England supports the relocation of sediment within similar sediment habitats, adjacent too, and updrift of sandwaves removed to ensure sediment re-enters the sandwave system, and that levelling works does not distript sediment supply or natural processes. The current wording suggests that sediment should not be relocated updrift of sandwaves, which is incorrect. In addition, note that Sabellaria spinulosa reef is an Annex I habitat, not Annex II species. Text requires revision wherever BE07 is referenced.
8 | E8, E52 | The Applicant should provide a transparent justification for the Worst-Case Scenario quantification of benthic impacts both within, and outside designated sites as a result of cable protection placement. Additional information within the Scour and Cable Protection Management Plan is also required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on direct and indirect impacts to designated sites from the placement of cable protection. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change. No further evidence has been presented to support negligible assessment conclusions. Please see Appendix E7 |  | No | The Applicant can confirm that further information on impacts to designated sites from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection. Furthermore, in the MCZA [REP7-088] it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope.
9 | E9 | With regard to cable protection and the decommissioning of cable protection, we would welcome further refinement of the Rochdale envelope in order to minimise environmental impacts. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. No change. Please see Appendix E5 to our Deadline 5 submission in relation to use of more readily removable cable protection |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | The Applicant can confirm that several measures have already been taken to refine the Rochdale envelope and minimise environmental impacts. These measures include a commitment to bundling the two cables into one cable trench and re-routing of the cable route to avoid passing through the Goodwin Sands MCZ. The Applicant has also include several additional commitments relating to cable protection in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) including: BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. GM08 - The Applicant will factor in the removability of cable protection when identifying the external cable protection for the Proposed Project. The Applicant will ensure it uses all available best practice guidance for cable decommissioning in its decision making. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Unresolved. No change in Natural England's position. Please see previous comments
10 | E10 | Mitigation measures should be adopted to differentiate between inside and outside of designated sites unless a precautionary approach will be taken to all installation and operation activities within the assessment. Impacts from all proposed types of external cable protection should be addressed to refine options and allow for a realistic WCS to be assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. In relation to assessment of operation and maintenance activites and in particular cable protection over the lifetime of the project. We advise this should be considered at the time of consent. If not then there should be a commitment to apply for a separate Operation and Maintenance licence will be applied for prior to the commence of the O&M phase of the project |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No Change to Deadline 5. Please also see Appendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | The Applicant can confirm that further information on impacts to designated sites from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Unresolved. No change in Natural England's position.
11 | E11, E15 | There is insufficient detail on proposed O&M activities relating to the placement of scour prevention / cable protection over the lifetime of the project. Necessary detail should be provided on the parameters for O&M activities including rationale on how total figures have been determined. Further quantified detail should be provided on the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | As for Point 10 |  | No Change. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to O&M activities. Without further consideration we advise that O&M activities are not permitted as part of this licence and a separate marine licence will be required. |  | No Change to Deadline 5. Please also see Apendices D6 and E6 to our Deadline 6 submission in relation to impacts to designated sites from cable protection. |  | No | The Applicant can confirm that further information on impacts to designated sites from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Unresolved. No change in Natural England's position.
12 | E13, E22 | Higher-level consideration of the UXO clearance activities should be included within MDS. UXO clearance activities both within and outside of designated sites should be provided to sufficiently quantify WCS to benthic receptors. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Please see advice provided in Appendix F5 and EXQ 2 ECOL5 in Appendix K5 to our Deadline 5 submission |  | No Change to our Deadline 5 advice |  | No Change to our Deadline 5 advice |  | No | As the location of any potential UXO clearance cannot be determined at this stage any UXO clearance will require a separate marine licence application and accompanying impact assessment. Any potential impacts to benthic features will be assessed post-consent when the information necessary for the assessment is available. | Unresolved. No change in Natural England's position. Please see main RFI 1 response letter.
13 | E16, E36, E54 | Mitigation measures should be adopted by the Applicant to mitigate for cable route preparation activities and disposal activities. Disposal options should be explored, sediment disposal should match local sediment types to avoid altering habitat character within 1.5km of the Offshore Scheme. A fall pipe should be used when dredging poses a risk of increased suspended sediment affecting sensitive sites or priority habitats. Cleared boulders adjacent to Goodwin Sands MCZ should be redistributed in similar habitats to avoid unnatural clustering and maintain baseline conditions. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | In progress. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission and Tab J of the R&I log where further detail on our outstanding issues can be found. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Part Resolved. Natural England advises on further commitments in relation to sandwave sweeping is included in Appendix D7. Natural England advises in Appendix E7 that boulder clearance desposition is now resolved |  | No | The Applicant can confirm that the further information on sediment disposal including mitigation identifed by Natural England in Sea Link Energy Cable Appendix E5 - Natural England's Advice on Benthic Ecology [REP5-218] has been incorporated in the Application Document 9.92 (C) Outline Cable Specification and Installation Plan [REP6-136] at Deadline 6 under Section 8 Sediment Disposal Management. The Applicant has also included the following commitments in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE07 - The Applicant will avoid relocating any sediment to with 50m of any Annex II Sabellaria spinulosa reef identified during pre-construction surveys and/or adjacent to and updrift of sandwaves. MPE12 - Boulders would be relocated locally to similar habitats and placed to be reflective of the surrounding habitats and not in a linear berms which have the potential to disrupt sediment transport. BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. | Unresolved. Only limited inclusion of sediment disposal mitigaton has been incorporated into the outline CSIP [REP6-136 or REP7-160]. No commitment has been made to match disposal areas with local sediment types to avoid altering habitat character within 1.5km of the Offshore Scheme, or to use a fall pipe when disposal of sediment poses a risk of increased suspended sediment affecting sensitive sites or priority habitats. In addition, as stated for Row 8 above, the commitment BE07 requires revision due to incorrect wording - refer to Point 7. This requires across all documents where BE07 is recorded.
14 | E17 | Storage options for material from landfall exit pits should be explored to minimise impacts within Sandwich Bay & Hacklinge Marshes SSSI. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Partially resolved. While we welcome the submission of a CSIP concerns still remain. Please see Appendix E5 point E.5 of our Deadline 5 submission for further advice on this matter |  | No Change to our Deadline 5 advice |  | No Change to our Deadline 5 advice |  | No | The Applicant confirms that, based on the nature and scale of the works, any material from the HDD exit pits will be temporarily stored within the cofferdam so that it can be used to backfill the HDD exit once HDD installation is complete. The volume of material will be quantified post-consent, as part of the detailed engineering of the HDD installation. | Resolved.
15 | E21, E23 | Applicant to clarify how individual Sabellaria spinulosa count data has been considered or what thresholds have been used to determine the potential for biogenic reef. A precautionary approach to data interpretation is required to inform a WCS of the extent & distribution of S. spinulosa reef within the Offshore Scheme. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence is required to support the conclusions of the ES that no Sabellaria spinulosa reef was observed by subtidal surveys within the Offshore Scheme. |  | No change |  | No Change. To resolve this issue please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Please see Appendix E6 to our deadline 6 submisson and also comments in Appendix E7 to our deadline 7 submission in relation to determining extent of NERC habitats and requirement for drop Down Video as well as geophysical data. |  | No | The Applicant has included the following commitment in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) specifically relating to Annex II Sabellaria spinulosa reef: BE07 - The Applicant will avoid relocating any sediment to with 50m of any Annex II Sabellaria spinulosa reef identified during pre-construction surveys and/or adjacent to and updrift of sandwaves. | Unresolved. Natural England continues to have concerns regarding the methodology and approach used to identify Sabellaria spinulosa reef. In addition, refer to advice above (e.g. row 8) regarding BE07 wording.
16 | E24 | Natural England disagrees that Blue Mussel Beds and Sabellaria spinulosa reefs have 'low sensitivity' to the temporary physical disturbance impacts during construction. The Environmental Statement should be updated with an appropriately considered assessment of the sensitivity of receptors and significance of impacts on all habitats listed under Section 41 or the NERC Act |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission | [9 empty] | Yes
17 | E25 | The EIA fails to consider potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures”. All benthic receptors within the Zone of Influence should be sufficiently characterised to enable a robust evidence-based assessment. The ecological importance and rarity of peat, clay and chalk substrates should be properly considered and efforts made to avoid physical impacts where possible. Particularly where such habitats support rare and/or irreplaceable communities such as boring piddocks. If avoidance isn't feasible, the Applicant must demonstrate how impacts have been minimised. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission. Natural England advises that commitments to avoid impacts to Section 41 habitats by micro-siting should be secured in the DCO. Please see Tab C in this R&I log (C10) and Appendix E5 submitted at Deadline 5. Please also see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | Natural England advises areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, which have the potential to be impacted by construction works (temporary disturbance) or placement of infrastructure (permanent habitat loss) should be considered the same as outcropping subtidal chalk and clay exposures. The extent of each habitat should be fully quantified and included within the assessment. Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Natural England advises that clarification is provided regarding the extent and distribution of subtidal chalk across the whole of Offshore Scheme. Please see Appendix E7 of our Deadline 7 submission for more detail. |  | No | Further information on potential impacts to “outcropping clay and soft chalk” and “peat and clay exposures” was provided in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. | Partially resolved. Whilst further information has been provided for surficial chalk and peat/clay, we refer to advice provided at Deadline 7 regarding subtidal chalk and peat and clay which are covered by a thin veneer of sediment. Due to the high mobility of sediments and the potential for damage to irreplaceable habitats of principal importance, these habitats should be considered the same as surficial chalk and clay. In addition, whilst NE welcomes BE06, we believe that the wording could be strengthened to ensure secured effective protection for NERC S41 habitats.
18 | E26, E41, E45 | The EIA does not consider the likely deposition impacts within Thanet Coast SAC and the assessment is lacking quantification and evaluation of impacts from elevated SSC and sediment deposition within Thanet Coast SAC during construction. The Applicant should update the assessment of potential impacts from SSC and deposition on Thanet Coast SAC Annex I reefs and sea caves and ensure all benthic receptors within the red line boundary and zone of influence are transparently and comprehensively assessed. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that the sensitivity information for reef features within the Thanet Coast SAC to ‘Medium’ sensitivity to suspended sediment concentrations and deposition is updated in line with the precautionary principle, unless further evidence is provided regarding the specific biotopes present within the site, and that impacts are mitigated accordingly. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Partially resolved. Please see Appendix E5 Point 2 to our Deadline 5 submission where we confirm that the sensitivity of reef features of Thanet SAC have been updated, but we note there has been no update to the assessment therefore this remains unresolved. |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to limited updates to assessments of SSC |  | Natural England advises in Appendix E7 and K7 of our Deadline 7 submission that this issue is now resolved. |  | Yes | Further information on likely deposition impacts within Thanet Coast SAC and quantification and evaluation of impacts from elevated SSC and sediment deposition within Thanet Coast SAC during construction was provided in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. Thiis was informed by additional sediment modelling that was undertaken for Pegwell Bay (Application Document 9.144 Additional Sediment Dispersion Modelling - Technical Note [REP6-120]). | Resolved
19 | E27 | According to MarESA, all benthic receptors are highly sensitive to habitat loss and the EIA (where relevant RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Issues remain outstanding. Natural England advises that the EIA (and where relevant, RIAA) should be updated with a more appropriate evidenced evaluation and assessment of the permanent loss of benthic habitats. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No change. Please see Appendix E5 , D5 and K5 to our Deadline 5 submission where we provide further advice on direct and indirect impacts to designated sites from the placement of cable protection. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No change. Please see advice proivded at Appendix E7 on the need to assess impacts on subcropping chalk |  | No | The Applicant can confirm that further information on impacts to designated sites from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Unresolved. Natural England continues to advise that all benthic receptors are highly sensitive to direct habitat loss. No change in position.
20 | E28 | Clarity is required regarding the extent and distribution of Blue mussel Mytilus edulis beds throughout the Offshore Scheme so that a robust review of the assessment can be made. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England advises that further evidence and clarification of the presence and distribution of blue mussel beds is required to support the conclusions of the ES. Natural England also advise that pre-construction surveys to identify the presence and distribution of blue mussel beds across the Offshore Scheme should be secured through the In Principle Monitoring Plan (IPMP). |  | No change |  | No Change - Blue Mussel (Mytilus edulis) are a NERC Section 41 Habitat and therefore we refer to advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 on NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No Change. Please see Appendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  | No | The baseline and impact assessments for blue mussel beds were significanlty updated in Application Document 6.2.4.2 (C) Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP1-054]. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. | Unresolved. Updates do not resolve NE concerns regarding the blue mussel bed assessments. No change in Natural England's position.
21 | E29 | A figure presenting areas within the Offshore Scheme most likely to require cable protection; their spatial relationship to benthic baseline and proximity to designated sites and Section 41 Habitats of Principal Importance should be provided. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England would welcome an updated figure to reflect the areas most likely to require all forms of cable protection, including remedial areas. |  | No change |  | Natural England notes that this has been provided within the CSIP which shows location in relation to designated sites. But doesn't consider the location of NERC Section 1 Habitats. Please also see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | In Progress: Please see Appendices D6 and E6 to our Deadline 6 submission where further information is quested of the Applicant to resolve this issue. |  | Part Progressed. Please see Appendix D7 in relation impacts to Goodwin Sands, and Appendix E7 in relation to Nerc Habitats |  | No | The Applicant can confirm that further information on impacts to designated sites from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Unresolved. No change in Natural England's position.
22 | E30, E58 | The Applicant has made no strong commitment to avoid / microsite around sensitive benthic receptors. The adoption of mitigation measures via a Benthic Mitigation Plan should be considered to reduce/ avoid impacts to Section 41 Habitats. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially addressed. Natural England requests clarification as to why the commitment to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance have been removed. Whilst commitments to prepare a mitigation plan are welcome, the mitigation hierarchy should be followed which sets out that impacts should first be avoided wherever possible. Securing commitments to avoid sensitive features through micro-siting of the cable wherever possible would resolve this issue. |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 submission noting that these habitats are also NERC Section 41 habitats |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  | Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. Please see Appendix E7 of our deadline 7 submission for more detail. |  | No | The oIPMP [Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116] commits to monitoring any area within the Offshore Scheme where protected habitats (Annex 1, NERC S41), that have the potential to be impacted by the Offshore Scheme, are identified during pre-construction surveys. | Unresolved. Commitment BE06 should be reworded to secure stronger commitments to avoid Annex I and NERC Section 41 Habitats of Principal Importance.
23 | E31 | The extent of all benthic impacts from construction access / work areas, construction of exit pits or cofferdam installation at the Kent landfall has not been assessed within the EA Benthic chapter. We advise that the EIA and RIAA are updated to consider all impacts at landfall. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | This issue is resolved. However, issues remain outstanding please see Appendix J3A [REP3A-028] of our Deadline 3a submission | [9 empty] | Yes | As many benthic habitats are dynamic and highly variable over time identifying specific areas for survey requirements, on the basis of survey data that is now a few years old, is not possible at the pre-consent stage. This is particularly the case since the exact location of any required cable protection is also not known until the detailed pre-construction surveys have been undertaken. It is a standard process for monitoring of benthic habitats, in relation to a project such as the Offshore Scheme, to assess on a WCS and finalise micrositing, cable protection locations and the determination of sensitive habitats, at the post-consent, pre-construction stage.
24 | E33 | The Applicant has not specified the type of cable protection to be used, nor considered the limitations some methods present with successful decommissioning or likelihood of degradation over time. Due consideration should be given to cable protection engineering options that favour the greatest likelihood of successful removal at the Project's end of life. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. Further clarification is required around cable protection location, type and the impact pathways, including further assessment of scour and secondary scour. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. We welcome the submission of [REP4-091] 9.93 (A) Offshore Decommissioning Technical Note . However, it hasn't addressed our concerns. Please see Appendix E Point E.19 to our Deadline 5 submissions |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to mitigation commitments |  |  |  |  | The Applicant can confirm that the followowing commitments relevant to cable protection have been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): GM08 - The Applicant will factor in the removability of cable protection when identifying the external cable protection for the Proposed Project. The Applicant will ensure it uses all available best practice guidance for cable decommissioning in its decision making. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Partially resolved. GM08 states that the Applicant will 'factor in' the removability of cable protection, this is limited and does not secure any commitments to prefence cable protections which is removable. Therefore, Natural England considers the issue to remain unresolved.
25 | E35 | The EIA lacks transparency in how the sensitivity, value and extent of benthic features have been assessed. Not all relevant biotopes within the zone of influence have been properly considered and it is unclear if assessments are based on the worst case sensitivities described. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Part Resolved. While we welome updates to the Benthic Chapter on the sensitivity of some receptors. Please see Apendix E5 to our Deadline 5 submission where we advise that assessments are updated. | P | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  |  |  |  | The sensitivity of benthic habitats identified by NE have been updated in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029]. Specifically this included changes to the sensitivity for sea caves, reefs, peat and clay exposures and sublittoral chalk. | Unresolved. No change in advice since Deadline 5.
26 | E38 | An Offshore IPMP should be developed and submitted into examination to include monitoring residual concerns in relation to protected habitats and those of conservation importance. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Please see Point E5.9 and E5.32 in Appendix E5 and response to ExQ2 BE 8 and 9 in Appendix K to our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to monitoring commitments |  |  |  |  | The oIPMP (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116]) commits to monitoring any area within the Offshore Scheme where protected habitats (Annex 1, NERC S41), that have the potential to be impacted by the Offshore Scheme, are identified during pre-construction surveys. | Partially resolved. Natural England welcomes the provision of the outline IPMP and updates provided at Deadline 7. However, Natural England advises that further work is required to ensure the IPMP is fit for purpose - refer to Appendix E at Dedline 7. We can also provide further updates on the IPMP submitted at Deadline 7 if required by the SoS at the next RFI deadline, noting that there are further concerns in relation to the timing of potential surveys and issues in relation to creation of scour pits as part of landfall works as identified by the applicant from an engineering perspective which is also relevant to ecology
27 | E39 | Natural England cannot agree with the conclusions of the EIA without a comprehensive assessment of all benthic impacts. We require: - A ecologically relevant understanding of the likely impacts of SSC, deposition and changes to supporting processes from cable protection on features of Goodwin Sands MCZ. - A clearer baseline and quantitative assessment of potential permanent loss of Section 41 NERC Habitats of Principal Importance, especially if avoidance measures are not committed to. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | Partially resolved. Natural England advises that further clarification on the presence and extent of these soft rock habitats would help to inform a quantitative assessment of impacts. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix D5, E5 and J5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to consideration of all impacts |  | Please see Appendix D7 in relation to use of cable protection adjacent to designated sites and Appendix E7 in relation to NERC. Natural England advises areas of sub-cropping chalk and clay, covered by a thin veneer of sediment, which have the potential to be impacted by construction works (temporary disturbance) or placement of infrastructure (permanent habitat loss) should be considered the same as outcropping subtidal chalk and clay exposures. The extent of each habitat should be fully quantified and included within the assessment. Natural England advises that measures to avoid impacts or if not possible, to reduce impacts as far as possible, should apply to shallow sub-cropping chalk and clay when covered by a sediment veneer as outcropping chalk and clay. Natural England advises that clarification is provided regarding the extent and distribution of subtidal chalk across the whole of Offshore Scheme. |  | No | The Applicant can confirm that Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.11 (F) Marine Conservation Zone Assessment submitted at Deadline 7 has been updated to include futher detail on potential effects from sandwave levelling and cable protection and potential impacts on the Goodwin Sands MCZ. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection . Furthermore, in the MCZA it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope. In addition, BE06 wording requires further strengthening to secure avoidance mitigation for Annex I habitats and NERC S41 Habitats of Principal Importance.
28 | E41 | We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see advice provided at Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In Progress. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection on MCZ features. |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to consideration of all impacts |  |  |  |  | The Applicant can confirm that Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.11 (F) Marine Conservation Zone Assessment submitted at Deadline 7 has been updated to include futher detail on potential effects from sandwave levelling and cable protection and potential impacts on the Goodwin Sands MCZ. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Partially resolved. As above.
29 | E43 | While we acknowledge the limited scale of habitat loss, we note that permanent loss of supporting habitat for the Outer Thames Estuary has not been assessed. We advise permanent loss of SPA features' supporting habitat should be screened into the assessment. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Resolved. Please see Point 5/G8 of Tab G of our R&I log where we consider that impacts to losses of supporitng habitat for OTE SPA features will be considered in a separate marine licence for UXO clearance |  | Not Resolved: Please see concerns raised in Appendices D6 and E6 on activities have not been fully assessed |  |  |  |  | The Applicant can confirm that further information on impacts to designated sites including the Outer Thames Estuary SPA from cable protection has been provided in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.6 (I) Habitats Regulations Assessment Report both submitted at Deadline 7. | Resolved
30 | E44 | No mitigation has been proposed for cable protection within or adjacent to designated sites and habitats which support mobile features. Where possible cable protection should avoid benthic supporting habitat. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Resolved. Please see Appendix F5 and Point 5/G8 of Tab G of our R&I log where we consider that impacts to losses of supporitng habitat for mobile features will be considered in a separate marine licence for UXO clearance which is considered to have a greater impact than placement of cable protection. Please note that this is separate issue to intertidal habitat loss covered in Tab J. |  | Not Resolved: Please see concerns raised in Appendices D6 and E6 in relation to cable protection |  |  |  |  | The Applicant can confirm that the following commitments relevant to the use of cable protection within and adjacent to designated sites have been included in in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): GM08 - The Applicant will factor in the removability of cable protection when identifying the external cable protection for the Proposed Project. The Applicant will ensure it uses all available best practice guidance for cable decommissioning in its decision making. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. | Unresolved. Please see previous comments
31 | E46 | We acknowledge that despite the need for further transparent assessment of certain impact pathways as highlighted by comments above, it is unlikely that compensation measures will be necessary as commitments to appropriate mitigation measures are possible. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | Progressed. Please see response to ExQs in Appendix K5 and Appendix E5 of our Deadline 5 where mitigation measures and commitments are discussed in detail |  | No Change to our Deadline 5 advice |  |  |  |  | Although no likely significant effects on benthic ecology have been identifed, the Applicant has included several mitigation commitments within Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) in acknwolegdment of concerns raised by Natural England and to further reduce the potential for any adverse effects to occur . | Partially resolved. Natural England welcomes the mitigation commitments but amendments are required to secure avoidance mitigation for Annex I and NERC S41 habitats.
32 | E47 | The current assessment lacks appropriate quantification and evaluation of impacts from SSC and sediment deposition within nearby MPAs during construction. We recommend that predicted SSC and deposition are considered in light of MarESA impacts thresholds and are used to assess impacts upon the MCZ features, until then there remains reasonable scientific doubt regarding hinderance of the Conservation Objectives of these MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to limited updates to assessments |  |  |  |  | The Applicant can confirm that Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.11 (F) Marine Conservation Zone Assessment submitted at Deadline 7 has been updated to include futher detail on potential effects from sandwave levelling and cable protection on MPAs. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Partially resolved. Natural England has ongoing concerns regarding mitigation for sandwave levelling and deposition, including during the operational phase, and for indirect impacts upon designated sites from cable protection. Refer to previous advice.
33 | E48 | Natural England requires confirmation that no permanent loss is likely within MCZs. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change |  | No change |  | Resolved. The Applicant has confirmed in [REP4-60] and [REP4-90] that there will be no permanent loss of habitat within MCZs | [5 empty] | Yes
34 | E49, E34 | The Applicant has not considered the potential for secondary effects of cable protection adjacent to Goodwin Sands MCZ. A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Goodwin Sands MCZ, followed by secured monitoring via a deemed Marine Licence and an In-Principal Monitoring Plan to determine whether residual impacts are as predicted. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No Change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Appendix E6 to our Deadline 6 submission in relation to monitoring and mitigation commitments |  |  |  |  | The Applicant can confirm that Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.11 (F) Marine Conservation Zone Assessment submitted at Deadline 7 has been updated to include futher detail on potential effects of cable protection and potential impacts on the Goodwin Sands MCZ. The Applicant has also prepared an Outline In-Principle Monitoring Plan (oIPMP) which was submited at Deadline 6 (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116]) and has updated commtiment BE05 as follows: BE05 - In accordance with the Environmental Principles set out in Application Document 9.92 Outline Cable Specification and Installation Plan, where benthic habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities or (NERC) Section 41 habitats and species) are identified during pre-construction surveys and additional mitigation is required to avoid or reduce impacts on these habitats, National Grid must prepare a Benthic Mitigation Plan. Any necessary Benthic Mitigation Plan(s) must be submitted to and approved in writing by the MMO prior to Work 6 in the dML commencing and should include a timetable for implementation of the mitigation and details of any necessary monitoring. Any agreed mitigation and/or monitoring must be implemented in accordance with the agreed timetable. A monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan will be submitted to the MMO (unless otherwise agreed in writing by the MMO) within three months of the 'as-built survey'. | Partially resolved. Natural England welcomes commitment MPE13 but advises that further information and refinement is required to resolve this issue. NE's concerns would remain if it is not possible (or practicable, as per wording) for the offshore cable corridor to maintain a separation distance of at least 100m from the boundary of Goodwin Sands MCZ. In addition, further information is required as to the likely need for rock protection adjacent to the MCZ to understand the potential effects on the MCZ from 500m of cable protection. Furthermore, in the MCZA it was stated that "Where remedial rock protection is required this will either be within in the cable trench (not protruding above the seafloor) or a low berm (shallow slope (1:3) and maximum height". Natural England advises that clarification is required as to whether the rock protection in MPE13 will be installed within the cable trench or have a shallow slope.
35 | E50 | We highlight the absence of designated anchoring areas to minimise seabed disturbance and advise careful selection of anchoring zones to avoid impacts to sensitive habitats or features. We advise impact assessments of cable installation vessels (jack-up barges or cable laying barges with spud legs) and operation and maintenance activities is required. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. Currently no mitigation measures have been proposed for construction. In relation to assessment of operation and maintenance activites and in particular cable protection over the lifetime of the project. We advise this should be considered at the time of consent. If not then there should be a commitment to apply for a separate Operation and Maintenance licence will be applied for prior to the commence of the O&M phase of the project |  | No Change to our Deadline 5 advice |  |  |  |  | The Applicant can confirm that potential effects of the use of jack-up barges / cable lay vessels with spud legs have been assessed in Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology. Further detail on jack-up barges is provided in response to Natural England Deadline 6 Response [REP6-245] – Appendix E6 Additional Comments on Intertidal and Benthic Ecology Advice in Application Document 9.149 Applicant's Comments on Other Submissions Recieved at Deadline 6. The Applicant also confirms that potential effects from the Offshore Scheme during Operation and Maintenence have been assessed in Section 2.9 of Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology which has been updated for submission at Deadline 7 to include further detail on potential effects from the presence of cable protection during operational of the Offshore Scheme. | Unresolved. We weclome the updated dcouments, but key information and impact assessments have not been included. For example no mitigation measures have been proposed for construction. And Impacts have not been considered during the O&M phase.
36 | E53 | Natural England advises against the use of grout bags adjacent to Goodwin Sands MCZ, unless filled with locally sourced sediment similar to that within the placement footprint (due to potential degradation of bags over time altering sediment character). |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change pending review of documents submitted at Deadlines 3 and 3a. |  | No change |  | No Change. We note in the CSIP [REP4-090] that the Applicant has not specified the cable installation tools that will be used and what cable protection will be used in what circumstance. Therefore this issue is not addressed. |  | No Change to our Deadline 5 advice |  |  |  |  | The Applicant can confirm that grout bags will not be used adjacent to the Goodwin Sands MCZ. | Unresolved. Natural England welcomes this update from the Applicant. However, we note that this commitment has not been included within any named plan, and therefore cannot be considered to be secured
37 | E52, E55 | Natural England is unable to agree with the MCZ assessment conclusions without further evidence and assessment, and maintains that there is reasonable scientific doubt regarding the hinderance of Conservation Objectives (alone or in-combination) of Goodwin Sands MCZ, Kentish Knock East MCZ and Thanet Coast MCZ to be hindered both Alone and in-combination. Particular regard should be given to commitments to remove all cable protection laid directly adjacent to the Goodwin Sands MCZ boundary. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Deadline 5 advice remains unchanged. Please also see Apendix D6 and E6 to our Deadline 6 submission in relation to ongoing MCZ concerns |  |  |  |  | The Applicant can confirm that Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology and Application Document 6.11 (F) Marine Conservation Zone Assessment submitted at Deadline 7 has been updated to include futher detail on potential effects from sandwave levelling and cable protection and potential impacts on the Goodwin Sands MCZ and other MCZs. The Applicant also confirms that the following commitment to micrositing has been included in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC): BE06 - All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. MPE13 - The Applicant does not anticipate the need for continuous external cable protection adjacent to the Goodwin Sands MCZ, on the basis of confidence in achieving the required depth of cable lowering. However, if external cable protection is required locally, the Applicant commits to limiting its use to no more than 500 metres in total, whether continuous or cumulative, within sections of the offshore cable corridor adjacent to the Goodwin Sands MCZ (unless otherwise agreed with the MMO, in consultation with Natural England and the MCA). In such circumstances, the installed height of any external cable protection will be limited to a maximum of 1 metre above the surrounding seabed. Furthermore, where reasonably practicable, and in line with the Applicant’s commitment to sensitive routing, the offshore cable corridor will be micro routed to maintain a separation distance of at least 100 metres from the boundary of the Goodwin Sands MCZ. | Unresolved. No change in position please see advice on MPE13
38 | E57 | Further information is required to inform a review of the impact assessments, until then, there remains reasonable scientific doubt of the nature of impacts to the intertidal features of Sandwich Bay to Hacklinge Marshes SSSI |  | No change pending review of documents submitted at Pre-Deadline 1, Deadline 1, and 1A. |  | No change pending review of documents submitted at Pre-Deadline 1, Deadlines 1, 1A, and 2. |  | No change. Please see Appendix J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No Change. Please see our responses to EXQs included in Appendix K5 of our Deadline 5 submission |  | No Change to our Deadline 5 advice |  | Please see Appendices D7 and E7 of our deadline 7 submission where vehicle access, routes, number of return trips and ground pressure is advised upon |  | No | The Applicant can confirm that Appliction Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029] was updated to include outputs from additional sediment dispersion modelling completed for the Kent and Suffolk landfalls (Application Document 9.144 Additional Sediment Dispersion Modelling - Technical Note [REP6120]) which included further information on potential effects on the Pegwell Bay during construction including potential impacts on the intertidal mudflats from scour and increased SSC and deposition. Application Document 6.2.4.2 (G) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology has also been updated following a call with Natural England on 16/04/2026 to provide clarification in relation to the use of cable rollers withinn the intertidal area. | Unresolved: Please see main response letter to RFI 1 | ???
39 | New Issue | Concrete mattresses have the potential to provide suitable substrate for colonisation by INNS. Natural England query whether use of a moonpool or prefabricated cofferdam [REP1-108] may also have the potential to introduce INNS at the Kent landfall and, in turn, present a potential impact pathway to designated site features. Clarification needed. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Issue is resolved. Please see Appendix E5 to our Deadline 5 response. | [5 empty] | Yes
40 | New Issue | Natural England remains uncertain as to the level of recoverability and timeframes to do so where compression impacts upon mudflats occur. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1 and 1A and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about intertidal/supporitng habitat impacts |  | No Change to our Deadline 5 advice |  | Natural England advises that post-consent monitoring is secured to monitor the recovery of the intertidal mudflats morphology and biological communities following landfall construction works, to validate predictions within the ES. Issue can be considered resolved if appropriate monitoring is secured through the IPMP. Natural England advises that the IPMP is updated to include pre-construction and post-construction monitoring of intertidal mudflats to validate predictions for the recovery of mudflat morphology and infaunal communities within the ES and to inform if further monitoring or remedial works are required. Please see our cover letter and Appendix L7 of our Deadline 7 submission for further advice on the IPMP. |  | No | All plant and vehicles operating on the mudflats in Pegwell Bay will be low ground pressure (LGP) vehicles. For example, the typical ground pressure for a 36-ton excavator on standard tracks is approximately 8-9 psi (pounds per square inch), which is lower than the pressure exerted by the average human, of 8 to 16 psi of ground pressure while standing. Thus, disturbance from the movement of LGP plant and vehicles will be limited to tracks and shallow indentations on the surface of the mudflat, which will be undetectable after a single, or at most, a few tidal cycles. The possible placement of protective mats at the Nemo and Thanet cable crossings, between the hoverport and the HDD work area, will also minimise potential disturbance to the existing cables, and hence the mudflat, from transiting plant and vehicles. A detailed description of the construction works in Pegwell Bay is provided in Application Document 9.13 Pegwell Bay Construction Method Technical Note. Benthic surveys at Pegwell Bay, to investigate the effect of cable installation by trenching across the mudflats, were undertaken for the NEMO cable installation project. The Nemo Link Interconnector Year 3 Post-Construction Intertidal Technical Report (EcoMarine, 2020) reported that “following an initial decrease in abundance and diversity in 2018, intertidal communities have been resilient to the physical disturbance resulting from the burial of the cable in 2017. Natural tolerance coupled with fast natural recruitment has resulted in a rapid recovery of faunal communities in 2020’. Furthermore, the monitoring report also states ‘data collected during the year-one and year-three post-construction surveys showed that the loss of intertidal fauna was localised and temporary, and by 2020 faunal communities and habitats present along the cable route reflect those seen during the baseline survey”. This survey was carried in an area of maximum mudfllat disturbance, where trenching occured and where vehichles would also have been present. Therefore, recovery from just the movement of low pressure vehicles is expected to be shorter than this but for the overall construction programme benthic habitats are expected to be indistinguishable from pre-construction conditons within 2 years if not sooner. | Unresolved. Natural England advises that a commitment within the IPMP to undertake monitoring of mudflat recovery (morphology and biological communities) post-construction would resolve issue.
41 | New Issue | Documents should be updated to reflect the highly sensitive nature of soft rock habitats abrasion and physical loss. Every effort should be made to avoid physical impacts to these habitats where possible. This is particularly the case where habitats support rare and/or irreplaceable communities such as boring piddocks. Where impacts cannot be avoided, we advise that evidence will need to be presented to demonstrate how impacts has been minimised as much as possible. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | In progress. Please see responses to ExQ2 BE 9 and 10 in Appendix K5 in our deadline 5 submissions. |  | No Change to our Deadline 5 advice |  | Partly Addressed Natural England advises that the document should be updated to include a ‘high’ sensitivity rating for subtidal chalk to physical disturbance impacts. Section 3.4.9 in REP6-116 states that the requirement for post-construction benthic survey will be informed by results from pre-construction surveys and final engineering of the project. Natural England advises that the final benthic monitoring plan should be agreed with the MMO, in consultation with the relevant SNCBs. If habitats or species of conservation value (e.g. Section 41 habitats or qualifying annex I habitat) are identified during pre-construction surveys, Natural England advises that commitments for post-construction surveys should be secured to demonstrate either avoidance or, where avoidance is not possible, recovery of habitats. Natural England advises that further monitoring and/or remedial works may be required if impacts are not found to be as predicted within the ES. |  | No | A significant update to the baseline and assessment - including quantification - was provided in Application Document 6.2.4.2 (F) Environmental Statement Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP6-029] In addition, the Applicant has updated Commitment BE05 in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) to provide further detail on mitigation measures for benthic habitats of principal importance. The updated wording is provided below for reference: BE05: As secured under the dML, in accordance with the Environmental Principles set out in the Outline Cable Specification and Installation Plan, where benthic habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species) are identified during pre-construction surveys, and additional mitigation is required to avoid or reduce impacts impact on these habitats, the Undertaker must prepare a Benthic Mitigation Plan. Any necessary Benthic Mitigation Plan(s) must be submitted to and approved in writing by the MMO prior to Work 6 in the dML commencing and should include a timetable for implementation of the mitigation and details of any necessary monitoring. Any agreed mitigation and/or monitoring must be implemented in accordance with the agreed timetable. A monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan will be submitted to the MMO (unless otherwise agreed in writing by the MMO) within three months of the 'as-built survey'. The Applicant has also included a new commitment BE06: All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. An outline IPMP (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116] was submitted at Deadline 6. | Unresolved. Whilst peat and clay is considered, no information is provided regarding the highly sensitive nature of subtidal chalk to physical disturbance or direct loss, or the ecological importance and rarity of subtidal chalk. Please also see RFI 1 response letter
42 | New Issue | Further to our Relevant Representation advice [RR-3290], we note that all three HDD exit options appear to be located in areas where Coralline Crag is present yet there is no assessment of potential impacts on the Coralline Crag due to the HDD or cable installation at landfall. Further consideration of the locations requiring cable protection is required to inform potential impacts to sediment transport and benthic receptors. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | Part Resolved. Natural England welcomes the commitment for HDD exit pits to be located >45m from the continuous Crag formation [REP4-102]. Please see Appendix E5 to our Deadline 5 which highlights commitments that are required to resolve this matter |  | No Change to our Deadline 5 advice |  |  |  |  | The Applicant confirms that there are a number of commitments in relation to avoiding impacts on the Coralline Crag found within Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC). These are: MPE07 - Installation of cables should not create pre-cut trenches at the Coralline Crags outcrop (as defined within Application Document 9.113 (A) The Coralline Crag Technical Note [REP4-102]), due to the sensitivity of the system. MPE11 - Cofferdams at the Suffolk Landfall are not included within the Proposed Project. The Landfall HDD exit pits at the Suffolk Landfall are in c. 7.5m (LAT) of water, therefore cofferdams are not required. MPE06 - Over the operational lifetime of the Proposed Project, monitoring of the beach profile and erosion rates will be carried out at both the Suffolk and Kent landfall sites in relation to the trenchless technique construction areas associated with the exit pits. The frequency and scope of monitoring would be dependent on the outcomes of the pre-construction surveys and ‘as-built’ status of the Offshore Scheme. The Applicant will produce a monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan to be submitted to the MMO to cover works below Mean High Water Springs within three months of the 'as-built survey' unless otherwise agreed in writing by the MMO. | Resolved.
43 | New Issue | Justification is required for why the required quantity of rock backfill has increased dramatically. Further information should be provided on where this rock backfill will be placed and the predicted total areas of permanent and/or temporary habitat loss and/or disturbance within and outside of designated sites. Further clarification is also required on the details of cable protection anticipated. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] our Deadline 3a submission |  | No change |  | No Change. Natural England requires further clarification from the Applicant on this matter |  | No Change to our Deadline 5 advice |  |  |  |  | The Applicant can confirm that there has not been a substanital increase in the amount of rock backfill. As per the response provided in Application Document 9.86 (A) Applicant's Comments on Other Submissions Received at Deadlines 3 and 3A [REP4-082] the change in the area of rock back fill was due to a simple calculation error was identified in the calculated area of rock back-fill presented in Table 4.17 of Application Document 6.2.1.4 (D) Part 1 Introduction Chapter 4 Description of the Proposed Project [REP1A-003] . To confirm rock back-fill is required along 38 km of the total offshore route. The total maximum width of the cable trench is 1.2 m which results in a total area of 45,600 m2 (i.e. 1.2 m x 38 km) which is the maximum design parameter for the area of rock back-fill. The calculated total volume of rock back-fill has not changed. The correct maximum area of rock back-fill was updated and a reassessment considered in Application Document 6.2.4.2 (D) Part 4 Marine Chapter 2 Benthic Ecology (Tracked) [REP4-030]. This concluded that the increase as a result of the error was small in relation to the overall assessment and did not change the conclusions of an impact rating of not significant in the assessment. The Applicant can also confirm that the locations where rock back-fill is required were provided in Application Document 6.4.4.2.7 Marine Habitats and Relevant Projected Sites and Areas of Rock Backfill within the Offshore Scheme Boundary - Application Document 6.4.4.2 (B) Environmental Statement Figures Marine Benthic Ecology (Tracked) [REP1-068]. | Resolved.
44 | New Issue | Clarification is required as to why the text securing up to date INNS training, biosecurity measures and embedded mitigation measures has been removed. Removed text also includes the requirement to report suspected INNS and, if necessary, take action to control present INNS. No justification is provided for why these measures have been removed, which could increase the risk of INNS being spread or introduced by the project. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] and J3A [REP3A-028] to our Deadline 3a submission |  | No change |  | Issue is resolved. Please see Appendix E5 to our Deadline 5 response. | [5 empty] | Yes
45 | New Issue | The standard best practice mitigation measures should be adopted where impacts from sandwave levelling could impact within MCZs and/or on NERC Habitat features. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission and Appendix D3 [REP3-118] to our Deadline 3 submission. |  | No change |  | No Change. Please see Advice provided in Appendix D5, E5 and K5 of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to mitigation commitments |  |  |  |  | The Applicant has updated Commitment BE05 in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) submitted at Deadline 7 to provide further detail on mitigation measures for benthic habitats of principal importance. The updated wording is provided below for reference: BE05: As secured under the dML, in accordance with the Environmental Principles set out in the Outline Cable Specification and Installation Plan, where benthic habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species) are identified during pre-construction surveys, and additional mitigation is required to avoid or reduce impacts impact on these habitats, the Undertaker must prepare a Benthic Mitigation Plan. Any necessary Benthic Mitigation Plan(s) must be submitted to and approved in writing by the MMO prior to Work 6 in the dML commencing and should include a timetable for implementation of the mitigation and details of any necessary monitoring. Any agreed mitigation and/or monitoring must be implemented in accordance with the agreed timetable. A monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan will be submitted to the MMO (unless otherwise agreed in writing by the MMO) within three months of the 'as-built survey'. The Applicant has also included a new commitment BE06: All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. An outline IPMP (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116)) was submitted at Deadline 6. | Unresolved. Natural England welcomes the adoption of BE05 and BE06. However, insufficient mitigation has been secured for sandwave levelling and disposal, and for cable protection. Commitment BE06 requires revision.
46 | New Issue | The commitment to the Suffolk Coast HDD should be amended so that the final HDD management plan is agreed with the regulators in consultation with the relevant SNCB, rather than it be for our information only (as per point 59 of [REP 1-103]. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendices E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. As advised in Appendices D5 and E5 of our Deadine 5 submission all landfall document need to be agreed with the regulators in consultation with relevant SNCB prior to construction and these documents should be submitted to the MMO 6 months beforehand. Please see DCO comments |  | No Change to Deadline 5 |  | Resolved at commitment B59 in the REAC [REP6-135] |  | Yes | Commitment B59 was updated for Deadline 6 and states: "B59 In relation to trenchless landfall works at both Suffolk and Kent, the contractor(s) will prepare the following suite of plans: Kent Landfall: HDD Landfall Method Statement and Drilling Fluid Management Plan, in consultation with NE, Kent Wildlife Trust (KWT), Royal Society for the Protection of Birds (RSPB), National Trust, and Thanet District Council, and submit the same for approval by the Marine Management Organisation (MMO) in accordance with the Cable Specification and Installation Plan prior to the commencement of any HDD activities. Undertake HDD landfall hydrofracture modelling which is to be shared for information only with NE, KWT and RSPB when completed. Suffolk Landfall: HDD Landfall Method Statement and Drilling Fluid Management Plan, in consultation with NE, Royal Society for the Protection of Birds (RSPB) and East Suffolk Council (ESC) and submit the same for approval by the Marine Management Organisation (MMO) in accordance with the Cable Specification and Installation Plan prior to the commencement of any HDD activities. Undertake HDD landfall hydrofracture modelling which is to be shared for information only with NE, RSPB and ESC when completed. At each landfall location (Suffolk and Kent) Natural England, ESC, RSPB and KWT (respectively) will be notified of changes to landfall HDD depth or changes to the location of the landfall exit pits. | Unresolved: Please see Deadline 7 responses in relation to the necessary strengthening of these commitments.
47 | New Issue | There should not only be a commitment to agree a mitigation plan for NERC habitats in consultation with relevant SNCB prior to construction, but that unless agreed otherwise impacts to theses habitats are avoided. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix E5, of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change. Please see Apendices D6 and E6 to our Deadline 6 submission in relation to mitigation commitments |  | Commitments to micro-route the cable to avoid or minimise impacts upon habitats of conservation importance (e.g. Section 41 habitats) should be secured. Impacts to S41 habitats should be avoided wherever possible. Where avoidance of impacts is not possible, MMO and the relevant SNCB should be consulted (not just informed) to ensure that impacts are minimised as far as possible. |  | No | The Applicant has updated Commitment BE05 in Application Document 7.5.2 (E) Outline Offshore Construction Environmental Management Plan and Application Document 9.84 (E) Register of Environmental Actions and Commitments (REAC) submited at Deadline 7 to provide further detail on mitigation measures for benthic habitats of principal importance. The updated wording is provided below for reference: | Partially resolved. Natural England advises that further mitigation measures are required, and that BE06 requires revision.
48 | New Issue | All monitoring requirements/hypotheses should be included in an Offshore IPMP at the time of consent. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see Point E5.9 and E5.32 in Appendix E5 and response to ExQ2 BE 8 and 9 in Appendix K to our Deadline 5 submission |  | No Change. Please see Apendix E6 to our Deadline 6 submission in relation to monitoring commitments |  |  |  |  | BE05: As secured under the dML, in accordance with the Environmental Principles set out in the Outline Cable Specification and Installation Plan, where benthic habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species) are identified during pre-construction surveys, and additional mitigation is required to avoid or reduce impacts impact on these habitats, the Undertaker must prepare a Benthic Mitigation Plan. Any necessary Benthic Mitigation Plan(s) must be submitted to and approved in writing by the MMO prior to Work 6 in the dML commencing and should include a timetable for implementation of the mitigation and details of any necessary monitoring. Any agreed mitigation and/or monitoring must be implemented in accordance with the agreed timetable. A monitoring plan, in substantial accordance with the outline In-Principle Monitoring Plan will be submitted to the MMO (unless otherwise agreed in writing by the MMO) within three months of the 'as-built survey'. An outline IPMP (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116]) was submitted at Deadline 6. | Partially resolved. Natural England welcomes the provision of the outline IPMP and updates provided at Deadline 7. However, Natural England advises that further work is required to ensure the IPMP is fit for purpose - refer to Appendix E at Dedline 7. We can also provide further updates on the IPMP submitted at Deadline 7 if required by the SoS at the next RFI deadline, noting that there are further concerns in relation to the timing of potential surveys and issues in relation to creation of scour pits as part of landfall works as identified by the applicant from an engineering perspective which is also relevant to ecology.
49 | New Issue | Further interpretation of the findings of REP2-035 Geophysical and Geotechnical Report is required to demonstrate where cable protection is mostly likely to be needed and once this is known undertake an assessment of the potential direct/indirect impacts from cable protection on designated sites features, irreplaceable geological features, and NERC habitats. | [5 empty] | New issue identified following review of documents submitted at Deadlines 1, 1A and 2 and added to the R&I log for Deadline 3A submission. Please see Appendix E3A [REP3A-027] to our Deadline 3a submission |  | No change |  | No Change. Please see advice provide in response to ExQ2 BE9 and BE10 in Appendix K5 of our Deadline 5 re NERC Section 41 habitats. Please also see Advice provided in Appendix D5 and E5, of our Deadline 5 submission where we have provided more advice about indirect impacts to designated sites from Sandwave Levelling and placement of cable protection |  | No Change to Deadline 5 |  |  |  |  | The Applicant has also included a new commitment BE06: All phases of the cable routing and design will seek to minimise impacts on habitats of principal importance (qualifying as Habitats Regulations Annex I habitats; Natural Environment and Rural Communities (NERC) Section 41 habitats and species), including micrositing and consideration of the use, type and location of cable protection. An outline IPMP (Application Document 9.140 Outline In-Principle Monitoring Plan [REP6-116) was submitted at Deadline 6. | Unresolved. No change in Natural Englands position. Please see comments on the IPMP and BE06 above.
50 | New Issue | The late addition of the Commitment GG45 in the REAC with regards to the use of Hovercraft during emergencies in Pegwell Bay brings the additional risk of disturbance to the interest features of the SPA. There is insufficient information provided on the timings, extent and duration of works as well as the phase of works it is intended to be used (ie, construction, operation or maintenance). Natural England advises there is a risk of an AEoI occurring from visual and noise disturbance from the use of a hover craft. Therefore, further information on the use of the proposed hovercraft is required before we can advise further on the impact to designated sites. |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New Issue |  | New issue identified following review of documents submitted at Deadlines 6. Please see our Cover Letter and Appendix E7 to our Deadline 7 submission. |  | No | No comment from Applicant as this was a new issue at Deadline 7. | Unresolved. Please see main RFI1 response letter