4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jane Louise Golding | 3278 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Louise Golding | 3278 | K564173,K703945 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Barclays Bank plc | 66 | SK328388 | Restrictive Covenant | Restrictive covenants to only use land as a bird sanctuary and/or nature reserve and to erect boundary posts as contained in a Conveyance dated 16 October 1950 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [7 empty] | Agree and in the latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [7 empty] | Agree and in the latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Suffolk County Council | 755 | SK254614 | Restrictive Covenant | Restrictive covenant that the dwelling house shall not be disposed of separately from the adjoining land and shall be occupied by a person employed locally in agriculture or forestry as contained in an Agreement dated 16 August 1989 |  | Category 2 | N/A | Yes | RR-5209 | [7 empty] | Draft under discussion | Not required | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 10.3.2026- The Applicant has been continuing its engagement with SCC. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. The Applicant expects to reach agreement during the period of the examination | 13.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | 29.04.2026- No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5, although these are not yet agreed by SCC. | No voluntary rights are being sought in relation to the subsoil beneath the highway network. The proposed protective provisions for the benefit of the local highways authorities are included in the version of the dDCO submitted at Deadline 5. Negotiations are continuing with SCC | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Steven Neil Pammenter | 92 | SK254614,SK326983 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 7 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Simon Bernard Nicholson | 578 | SK254614,SK335127 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 November 2011 for the benefit of 11 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Shane Louis Hasler | 729 | SK254614,SK304349 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 25 April 2008 for the benefit of 2 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Richard William Jennaway | 735 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Richard Pearce | 577 | SK254614,SK355713 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 4 September 2014 for the benefit of 9 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Peter Henry Marshall | 3569 | SK254614,SK327038 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 12 Chapel Barn Lodges |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/15b | Suffolk Sheet 2 | 9324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20f | Suffolk Sheet 2 | 2,528 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/10a | Suffolk Sheet 2 | 1,975square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/11b | Suffolk Sheet 2 | 860 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/15 | Suffolk Sheet 2 | 21,961 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20b | Suffolk Sheet 2 | 11,242 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK280789,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | James Henry Rogers | 67 | SK290870,SK312683 | Easement Right or Privilege | Rights relating to service media and boundary structures as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/10 | Suffolk Sheet 2 | 1,388 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
2/11 | Suffolk Sheet 2 | 619 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Henry Rogers | 67 | SK290870,SK363555 | Easement Right or Privilege | Rights relating to service media and boundary fences as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | 13.04.2026 - Following the agents group meeting on 23rd March 2026, the Applicant's Agent met with the landowner's agent on the 30th March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. As stated at Deadline 5 and at the Compulsory Acquisition Hearing on 25th March 2026, the rights being sought overlap with a third party development proposal. The cable Limits of Deviation allow flexibility in the cable location due to the interaction with Scottish Power Renewables planting schemes in this area. The Applicant expects that the terms will be agreed in principle by the end of Examination however due to the overlapping development proposals it is not expected that Heads of Terms will be signed until the exact cable route within the Limits of Deviation is confirmed. | 29.04.2026 - The Applicant's Agent continues to engage with the landowner's agent in relation to the rights being sought. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The position as stated at Deadline 6 has not changed however the landowner's agent has confirmed that the landowner will remove their objection to the Project and it is expected that Heads of Terms will be agreed in principle with this landowner. | Relationships with this landowner and agent are positive however, in light of the latest Friston Substation landscape design, it is currently anticipated that the cable route may not be required within this plot, the project is working on detailed design and more information will be known following that process. By agreement with the landowner, formal negotiations are on hold at present, with regular dialogue ongoing between the respective agents. Given the constructive relationship established and the progress made on the template Heads of Terms, the Applicant remains well positioned to progress matters efficiently should this land be required in the future, subject to any necessary site-specific provisions. | Draft under discussion |  | 2026-09-11
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK150493,SK402512 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Anthony Cox | 3496 | SK379333,SK402512 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jacqueline Helen Thompson | 3502 | SK379333,SK411653 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of way as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of way as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Easement Right or Privilege | Right of entry for the purpose of maintaining service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K838442,K868267 | Restrictive Covenant | Restrictive covenants relating to building openings and accessways, the maintenance of a fence and gates as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-2091 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - As raised at the Compulsory Acquisition Hearings on 25th March 2026, the landowner's agent has sought further clarity on the rights being sought within the Heads of Terms relating to the UKPN diversion works. The Applicant continues to work with UKPN and the landowner's agent to provide that clarity but it is not expected this will be concluded to allow Heads of Terms to be agreed by the end of Examination. In addition, the Applicant's Agent emailed the landowner's agent on 24th March 2026, and on 1st April 2026 to request further supporting evidence for their commercial proposal. This information was provided by the landowner's agent on 3rd April 2026 and will be considered by the Applicant. | 29.04.2026 - The Applicant's agent continues to negotiate the commercial terms with the landowner's agent, and the Applicant is working to provide detailed plans in relation to the UKPN diversion. The Applicant will continue to engage and negotiate with the landowner beyond the close of Examination and it is expected that agreement will be reached once clarity has been provided in relation to the UKPN diversion. | Engagement with the landowner's agent has continued constructively since the previous update in April 2026. The landowner's agent has confirmed that progression of the agreement is contingent upon receiving further detail regarding the proposed UKPN diversion. This position was reaffirmed during meetings between the landowner's agent and the Applicant's agent on 1 June and 18th August 2026. The Applicant is actively working with UKPN to obtain the additional information required and will share this with the landowner and their agent as soon as it becomes available. Commercial matters also remain under ongoing consideration alongside the UKPN diversion requirements. Notwithstanding the outstanding points, discussions have remained positive and productive. Given the collaborative engagement to date and the progress achieved with the landowner's agent on related matters, there is confidence that the remaining issues can be resolved and that agreement will be reached prior to a DCO decision being made. | Draft under discussion |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/15b | Suffolk Sheet 2 | 9324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/15 | Suffolk Sheet 2 | 21,961 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Rights relating to service media, boundary fences and support as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20f | Suffolk Sheet 2 | 2,528 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20b | Suffolk Sheet 2 | 11,242 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493,SK379333 | Easement Right or Privilege | Right to pass and repass and unknown rights as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/10a | Suffolk Sheet 2 | 1,975square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/10 | Suffolk Sheet 2 | 1,388 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/11b | Suffolk Sheet 2 | 860 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/11 | Suffolk Sheet 2 | 619 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian Charles Rix | 692 | SK312683,SK363555 | Easement Right or Privilege | Rights relating to drainage and conduits as contained in a Transfer dated 30 September 2015 for the benefit of adjoining land |  | Category 2 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | 13.04.2026 - The Applicant's Agent met with the landowner's agent on 30th March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. There will be a meeting scheduled with the landowner after Deadline 6 to discuss any changes, discuss the outstanding matters and confirm the Applicant's position and the justification in regard to the rights sought in this application. The Applicant's Agent provided the landowner's agent links to relevant examination documents on 9th April 2026, following Compulsory Acquisition Hearing 2 Action Point 9. The Applicants have forwarded another copy of the meeting minutes, held by Teams, with Mr Rix where the justification and purpose of the hedge was explained and listened to the perceived impact to the farm, which we have sought to further quantify. The Applicants will also confirm with Mr Rix the extent of land held under Option to Purchase by SPR. Whilst engagement will continue, an agreement is unlikely to be reached with the landowner before the end of Examination. | 29.04.2026 - The Applicant's Agent has offered to meet with the landowner and their agent however they have declined a meeting at this stage. The Applicant's Agent has been in regular communication with the landowner's agent in relation to their outstanding points of objection. The Applicant's Agent has confirmed to the landowner's agent the Applicant's position in relation to these points and the Applicant has provided a detailed response at Deadline 7. Whilst it was hoped that the revised Heads of Term would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue to engage with the landowner and their agent after the close of Examination in relation to their outstanding points of objection and resolving these issues. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 1 May 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to review and progress the Heads of Terms. On 18 June 2026, the Applicant and its Agent met with the landowner and their agent to discuss the remaining matters outstanding between the parties. These included the ancillary rights required for access and drainage, the extent to which such rights may overlap with third-party development proposals, the potential effects on the Christmas tree crop, and the extent of land proposed for acquisition in connection with the Project. The Applicant's Agent had meetings with the landowner's agent on 22nd July, 21st and 26th August and 3rd September 2026 to finalise the template Heads of Terms and all outstanding points in the template terms have since been agreed. The Applicant's Agent is now working with the landowner and their agent to ensure that the Heads of Terms reflect the circumstances of the individual landholding before being progressed towards agreement with this landowner. | Draft under discussion |  | 2026-09-11
2/32a | Suffolk Sheet 2 | 147 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 29.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/32 | Suffolk Sheet 2 | 2,887 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/29a | Suffolk Sheet 2 | 1,267 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
2/29 | Suffolk Sheet 2 | 881 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HSBC Bank plc | 2282 | SK232978 | Mortgage | as mortgagee to Michael Neil Copinger Mahony in respect of a legal charge dated 1 May 2009 registered under title SK232978 |  | Category 2 | No Agent Known | No | [10 empty] | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 13.04.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-09-18
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Hopkins Homes Limited | 484 | SK336019 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 24 March 2016 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [10 empty] | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Handelsbanken plc | 870 | SK336019 | Mortgage | as mortgagee to William Notcutt Estates Limited in respect of a legal charge dated 9 April 2013 registered under title SK336019 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Guy Miles Alan Smith | 3271 | K564173,TT61402 | Easement Right or Privilege | Rights relating to service media and rights to enter upon the retained land for the purposes of inspecting, cleansing, maintaining and repairing service apparatus and all other rights and quasi-rights which are still capable of being enforced as contained |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Guy Miles Alan Smith | 3271 | K564173,TT61402 | Easement Right or Privilege | Rights relating to service media and rights to enter upon the retained land for the purposes of inspecting, cleansing, maintaining and repairing service apparatus and all other rights and quasi-rights which are still capable of being enforced as contained |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul William Hawkins | 446 | SK254614,SK361255 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 8 July 2015 for the benefit of 10 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Olivia Jane Nicholson | 163 | SK254614,SK335127 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 November 2011 for the benefit of 11 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lisa Gail Hasler | 57 | SK254614,SK304349 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 25 April 2008 for the benefit of 2 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kathryn Alison Hawkins | 175 | SK254614,SK361255 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 8 July 2015 for the benefit of 10 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Karen Pammenter | 129 | SK254614,SK326983 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 7 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Judith Mary McKirdy | 449 | SK254614,SK366967 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 11 March 2016 for the benefit of 5 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | John Graham Panrucker | 432 | SK254614,SK374354 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 July 2016 for the benefit of 6 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | John Duthie Eric Butcher | 176 | SK254614,SK316573 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 27 April 2009 for the benefit of 3 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jens Haustrup | 191 | SK254614,SK326643 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 4 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jenifer Mary Jennaway | 282 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gordon Young | 3440 | SK320579,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gordon Young | 3440 | SK320579,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janet Jennaway | 155 | SK254614,SK361267 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 1 July 2015 for the benefit of 8 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Jane Taylor | 714 | SK254614,SK322506 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 26 February 2010 for the benefit of 1 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Graham McKirdy | 299 | SK254614,SK366967 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 11 March 2016 for the benefit of 5 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Glenda Haustrup | 361 | SK254614,SK326643 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 September 2010 for the benefit of 4 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Frances Margaret Panrucker | 621 | SK254614,SK374354 | Easement Right or Privilege | Rights relating to service media as contained in a Lease dated 13 July 2016 for the benefit of 6 Chapel Barn Lodges |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [10 empty] | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK150493,SK411653 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gary Mark Thompson | 3501 | SK379333,SK411653 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Flagship Housing Limited | 554 | SK379333 | Restrictive Covenant | Restriction against disposition of the freehold estate |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Fiona Clare Cramb | 708 | SK205598,SK312683 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 23 November 1987 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Fernham Homes Limited | 3588 | K564173 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 1 February 2024 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK350196 | Easement Right or Privilege | Rights relating the use and maintenance of pipes and drains as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK350196 | Restrictive Covenant | Restrictive covenants to only use land as a footpath or for agricultural purposes and to not erect structures, plant trees or interfere with the vertical or lateral support of pipes as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK336019 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK336019 | Restrictive Covenant | Restrictive Covenant relating to water apparatus as contained in a Deed dated 15 October 1999 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Erik Martin Collins | 1341 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Erik Martin Collins | 1341 | K816963,K903084 | Easement Right or Privilege | Rights of access as contained in a Transfer dated 1 September 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK150493,SK408279 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eric Winston Woodbine | 3503 | SK379333,SK408279 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Environment Agency | 703 | K335437 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 06 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elizabeth Mary Sneath | 3508 | SK379333,SK407266 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity cables and works as contained in a Deed dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Restrictive Covenant | Restrictive covenants relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | [10 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | [10 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Eastern Power Networks plc | 254 | SK290870 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1987 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Easement Right or Privilege | Rights relating to the use and maintenance of electrical apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK312683 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity cables and works as contained in a Deed dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Eastern Power Networks plc | 254 | SK350290 | Restrictive Covenant | Restrictive covenants relating to electricity apparatus as contained in a Deed of Grant dated 18 February 1997 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Suffolk Council | 548 | SK292493,SK354374 | Easement Right or Privilege | Rights reserved relating to services as contained in a Transfer dated 10 June 2014 |  | Category 2 | N/A | Yes | RR-1420 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | 13.04.2026 - The Applicant's Agent issued revised Heads of Terms to the landowner's agent on 17th March 2026 to address the landowner's concerns in relation to restrictions over the easement at surface level and request comparable land value data. On 26th March 2026, the Applicant's Agent had a Teams meeting with the landowner's agent to discuss the amendments to the Heads of Terms, at this meeting it was agreed further amendments were required. Following this meeting, further revisions to the Heads of Terms were made in relation to restrictions over the easement at surface level and issued to the landowners agent on the same day. The interest here is Aldeburgh beach and as such The Applicant does not perceive the restrictions imposed by the easement to be limiting in the Council's use and control of the land as beach. The Applicant believes that the terms are agreed in principle with the landowner's agent, subject to feedback from the landowner's agent in relation to the commercial proposals. The Applicant's Agent followed up with the landowner's agent for feedback on the commercial proposals on 9th April 2026. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent has not yet received any feedback in relation to the revised Heads of Terms issued to the landowner's agent on 26th March 2026. The Applicant's Agent sent a follow up email on 17th and 24th April 2026 however it is understood that the landowner's agent is out of office until 30th April 2026. The Applicant belives that the revised Heads of Terms issued on 26th March 2026 addressed the landowners outstadning concerns and the Applicant is awaiting feedback on the commercial proposal from the landowner. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent has continued to seek an update from the landowner's agent regarding the revised Heads of Terms issued on 26th March 2026. Follow up correspondence was issued on 7th May, 12th May, 18th May, 29th May, 1st June, 26th June and 13th July 2026, together with several telephone calls and voicemails. Further to this the applicants agent has gone to further representatives of the landowner in an attempt to prompt meaning full response correspondence includes emails on 28th July, 5th August & 11th August 2026. The last substantive response from the landowner's agent was received on 1st June 2026, when they confirmed that they were awaiting instructions from their client and would continue to pursue the matter. Despite repeated attempts to progress negotiations, the Applicant has not received any substantive feedback on the latest revised terms. The Applicant remains willing to continue negotiations with a view to reaching a voluntary agreement. | Draft under discussion |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Suffolk Council | 548 | SK292493,SK354374 | Restrictive Covenant | Restrictive covenant not to use the property for any purpose other than amenity land and nature reserve and ensure that land is kept open to the public at all times as contained in a Transfer dated 10 June 2014 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-1420 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | 13.04.2026 - The Applicant's Agent issued revised Heads of Terms to the landowner's agent on 17th March 2026 to address the landowner's concerns in relation to restrictions over the easement at surface level and request comparable land value data. On 26th March 2026, the Applicant's Agent had a Teams meeting with the landowner's agent to discuss the amendments to the Heads of Terms, at this meeting it was agreed further amendments were required. Following this meeting, further revisions to the Heads of Terms were made in relation to restrictions over the easement at surface level and issued to the landowners agent on the same day. The interest here is Aldeburgh beach and as such The Applicant does not perceive the restrictions imposed by the easement to be limiting in the Council's use and control of the land as beach. The Applicant believes that the terms are agreed in principle with the landowner's agent, subject to feedback from the landowner's agent in relation to the commercial proposals. The Applicant's Agent followed up with the landowner's agent for feedback on the commercial proposals on 9th April 2026. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent has not yet received any feedback in relation to the revised Heads of Terms issued to the landowner's agent on 26th March 2026. The Applicant's Agent sent a follow up email on 17th and 24th April 2026 however it is understood that the landowner's agent is out of office until 30th April 2026. The Applicant belives that the revised Heads of Terms issued on 26th March 2026 addressed the landowners outstadning concerns and the Applicant is awaiting feedback on the commercial proposal from the landowner. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent has continued to seek an update from the landowner's agent regarding the revised Heads of Terms issued on 26th March 2026. Follow up correspondence was issued on 7th May, 12th May, 18th May, 29th May, 1st June, 26th June and 13th July 2026, together with several telephone calls and voicemails. Further to this the applicants agent has gone to further representatives of the landowner in an attempt to prompt meaning full response correspondence includes emails on 28th July, 5th August & 11th August 2026. The last substantive response from the landowner's agent was received on 1st June 2026, when they confirmed that they were awaiting instructions from their client and would continue to pursue the matter. Despite repeated attempts to progress negotiations, the Applicant has not received any substantive feedback on the latest revised terms. The Applicant remains willing to continue negotiations with a view to reaching a voluntary agreement. | Draft under discussion |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | East Anglia Two Limited | 3586 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia Two Limited | 3586 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia Two Limited | 3586 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia Two Limited | 3586 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia Two Limited | 3586 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/36 | Suffolk Sheet 2 | 3,945 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/47 | Suffolk Sheet 2 | 4,352 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK438881 | Restrictive Covenant | Restrictive covenants not to erect buildings or plant trees in the vicinity of electrical apparatus and not to raise or lower the level of ground as contained in a Deed dated 12 October 1965 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | East Anglia One North Limited | 2569 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | East Anglia One North Limited | 2569 | SK290870,SK312683,SK363555 | Easement Right or Privilege | Right of way as contained in a Transfer dated 16 January 2009 for the benefit of adjoining land |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20e | Suffolk Sheet 2 | 94 square metres, or thereabouts, of agricultural land situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia One North Limited | 2569 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia One North Limited | 2569 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | East Anglia One North Limited | 2569 | SK438881 | Easement Right or Privilege | Rights reserved relating to conduits as contained in a Transfer dated 30 September 2015 |  | Category 2 | [10 empty] | Draft Under Discussion | Draft under discussion | 08.10.2025- Protective Provisions Requested, Wider conversations are taking place with this PIL as their Project develops and they start to acquire their land. 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. 04/03/2026- Negotiations are positively ongoing with SPR and their projects EA1N and EA2 in respect of the proposed future maintenance and management of the various components of the Kiln Lane Hub with a view to issuing Heads of Term imminently. To be discussed alongside various commercial agreements, including a Transfer of Benefit Agreement. | 13.04.2026 - Following the meeting on 1st April 2026 between The Applicant and EA2 representatives, an update to the Book of Reference and Land Plans (Suffolk) has been submitted for Deadline 6. The Applicant is aware that EA2 intends to exercise further options and has provided an indication of where they will be and when. Both Parties acknowledge EA2 interests in land have evolved, and will continue to do so through the examination period for Sea Link and beyond. The Applicant will continue to engage with EA2 to understand their land interests. The Applicant proposes to issue Heads of Term to EA2 following the Deadline 6 submissions to seek to acquire the interests it requires and will update these as necessary as the interests further evolve. There are and continue to be many discussions in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | 29.04.2026 - Following the Deadline 6 submission with updated Book of Reference and Land Plans, the landowner has confirmed the updates to be correct as at that date but with further options to be exercised imminently The Applicant continues to engage with EA1N and will issue Heads of Term to seek to acquire the interests it requires. There are and continue to be many negotiations in relation to Kiln Lane, Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side including a TOBA and transfer of the Kiln Lane substation site. | Following the Deadline 7 submission and the close of examination the Applicant has continued to engage with SPR/EA1N/EA2, we have issued Heads of Term to seek to acquire the interests it requires however these are now being revised based on the completion of the TOBA and land purchase as part of the Kiln Lane (Friston) Substation build under the EA2 / EA1N DCO.. There are and continue to be many negotiations in relation to Sea Link, EA1N and EA2 projects and how all parties can ensure they can construct and operate side by side. | Draft under discussion |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Dorcas Muriel Daw | 2370 | K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Dorcas Muriel Daw | 2370 | K77907 | Easement Right or Privilege | Right of access |  | Category 2 | N/A | No | [9 empty] | Not required | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 13.04.2026 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Dominic Richard Upton | 2582 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Disposal Company (Richborough) Limited | 914 | K987175,K273192 | Easement Right or Privilege | Rights to access, maintain and use a rising main as contained in a Conveyance dated 17 August 1966 for the benefit of K987175 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K987175 | Easement Right or Privilege | Right of way as contained in a Conveyance dated 17 May 1950 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K987175 | Easement Right or Privilege | Rights to lay and use a sewer drain for the benefit of K987175 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Disposal Company (Richborough) Limited | 914 | K524623,K750977 | Easement Right or Privilege | Rights to pass and repass with or without vehicles as contained in a Conveyance dated 17 May 1950 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Discovery Park Limited | 635 | K524623,TT23413 | Restrictive Covenant | Restrictive covenant not to use the said property for any purpose which might be or grow to be a nuisance or annoyance as contained in a Conveyance dated 18 June 1948 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Derbyshire County Council | 1842 | SK336019,SK186621,SK97129,SK274324 | Easement Right or Privilege | Rights relating to service media as contained in a Conveyance dated 2 March 1973 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dawn Randell | 287 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Dawn Randell | 287 | K672786,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 10. Land that is not subject to powers of acquisition | Class 10. Land that is not subject to powers of acquisition nor temporary use | Dawn Randell | 287 | K672786,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David Winston Langmead | 45 | SK194564,SK358646 | Restrictive Covenant | Covenants to maintain service media as contained in a Transfer dated 30 January 2015 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard John Balls | 395 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Easement Right or Privilege | Rights relating to service media and support as contained in a Transfer dated 18 July 2008 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jane Elizabeth Balls | 448 | SK111460,SK307283 | Restrictive Covenant | Restrictive covenants not to; erect buildings, use land for any purposes other than those recognised as environmental best practice, crop or graze land for any commercial use, keep livestock, apply pesticide, use land for the storage of equipment and to n |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Network Rail Infrastructure Limited | 1271 | SK266138 | Restrictive Covenant | Covenants to maintain fencing as contained in a Conveyance dated 20 June 1969 for the benefit of adjoining land |  | Category 2 | N/A | Yes | RR-3936 | [7 empty] | Agree and in the latest version of the dDCO |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Zedra Governance Limited | 305 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | John Oliver Watts | 328 | SK328388,RTS Notices | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Gail Lorenza Francis | 343 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | David John Cramp | 331 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cornerstone Telecommunications Infrastructure Limited | 3254 | TT70483,K273192 | Easement Right or Privilege | Rights relating to access and use of a telecommunication site as contained in a Lease dated 24 August 2017 for the benefit of TT70483 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cornerstone Telecommunications Infrastructure Limited | 3254 | TT70483,K273192 | Easement Right or Privilege | Rights relating to access and use of a telecommunication site as contained in a Lease dated 24 August 2017 for the benefit of TT70483 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No |  | RR-0334 REP1-170 | [7 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sir Michael John Hopkins | 556 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Sarah Younger | 2748 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Reginald Anthony Wainwright | 303 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lady Patricia Ann Hopkins | 533 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 | N/A | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Lady Patricia Ann Hopkins | 533 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | N/A | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Joel Hopkins | 2746 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Georgeta Catargiu | 1270 |  | Restrictive Covenant | Restrictive covenant not to keep or breed pigs or poultry or erect buildings for the breeding or keeping of livestock as contained in an Assent dated 18 May 2000 for the benefit of adjoining land | As Personal Representative to the Estate of Martin Peter Handscombe | Category 2 | Sam Jennings, Strutt & Parker | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent, with constructive engagement ongoing since the previous update in April 2026. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by the Suffolk Agents Group. The Applicant’s Agent has also remained in regular correspondence with the landowner’s agent regarding further land acquisitions by SPR. On 25 June 2026, the landowner’s agent confirmed that the final transfer of land to SPR had completed. Subsequently, on 14 July 2026, the Applicant’s Agent issued updated Heads of Terms reflecting the revised freehold acquisition area. The Applicant’s Agent understands that the Heads of Terms are now agreed in principle, subject to agreement on the commercial terms. The Applicant’s Agent is awaiting further feedback in relation to the commercial aspects of the agreement and will continue to engage proactively with the landowner’s agent to progress negotiations. The Applicant remains confident that agreement can be reached prior to the DCO decision being made. | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Edmund Michael Wood | 451 | SK246649,SK356298 | Easement Right or Privilege | Rights relating to services as contained in a Transfer dated 24 November 2003 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Abigail Hopkins | 2747 | SK356298,SK280788 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 2 May 2006 for the benefit of neighbouring land |  | Category 2 |  | Yes | RR-0010 | [8 empty] | Not required | 04.03.2026 - no voluntary agreements are being sought in relation to this plot from this PIL. | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | The Public Trustee | 825 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land | as Personal Representative to the Estate of Terence James Martin Haworth | Category 2 | No Agent Known | Yes | RR-5322 | [8 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent beyond the close of Examination to mitigate any potential disruption. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence taking place since the previous update in April 2026. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to progress the Heads of Terms and work through outstanding matters. The Applicant’s Agent met with the landowner’s agent on 7 July 2026 to further advance negotiations. The principal matters remaining for agreement relate to the commercial terms and the landowner’s desire for greater certainty regarding the potential impacts of construction activities on their property. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point. As set out at Deadline 6, the Applicant remains committed to ongoing engagement with the landowner and their agent to identify and implement appropriate accommodation works that will, where practicable, mitigate disruption during construction. The Applicant will also provide details of the accommodation measures proposed by the Main Works Contractor to minimise the effects of the Project on the landowner’s property and operations. The Applicant considers that any residual and proven disturbance, or any diminution in value arising from the exercise of the rights sought, can be appropriately addressed through the Compensation Code. The Applicant will continue to engage proactively with the landowner and their agent with a view to reaching a voluntary agreement prior to the DCO decision. | Draft under discussion |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Pamela Tile | 1205 | SK329337 | Easement Right or Privilege | Right of way as contained in a Deed dated 16 November 1964 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [10 empty] | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | [10 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/7b | Suffolk Sheet 2 | 419 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/7a | Suffolk Sheet 2 | 1,266 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Colonel Michael Lawrence Riddell-Webster | 1665 | SK258213 | Mortgage | as mortgagee to Ian Charles Rix in respect of a legal charge dated 22 September 2004 registered under title SK258213 | as trustee to Mrs. Ruth Riddell-Webster`s 2000 Trust for Mrs. Ian Rix | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Easement Right or Privilege | Right of access |  | Category 2 | Ali Holmes, Savills | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | 13.04.2026 - On the 18th March 2026, the Applicant's Agent emailed the landowner's agent requesting written feedback on the Heads of Terms. A meeting was proposed for 25th March 2026. On the 23rd March 2026, the landowner's agent responded to confirm no availability for the suggested meeting date. An alternative meeting was arranged for the 7th April 2026. On the 23rd March 2026, the landowner's agent confirmed that their main concerns aligned with their occupier, namely potential contamination and soil compaction. On the 25th March 2026, the Applicant's Agent confirmed that information on these matters was being compiled, and would be provided shortly. On the 7th April 2026, the Applicant's Agent met with the landowner's agent to discuss Heads of Terms and construction related queries. Outstanding areas requiring further discussion include the landowner's ability to grant new rights over the Option Area, ancillary rights for utilities and the drafting of the proposed use of Compulsory Powers. On the 8th April 2026, the Applicant's Agent emailed the landowner's agent following the meeting to provide an editable version of the Heads of Terms, the landowner's agent confirmed that it was their intention to provide a markup version within two weeks. On the 9th April 2026, the Applicant's Agent provided an update to the landowner's agent and their occupier with the requested information relating to contamination and soil compaction. A meeting has been arranged with the landowner's agent for the 27th April 2026 to discuss further feedback on the Heads of Terms. Given these timings it is not expected that Heads of Terms will be signed before the end of Examination. | 29.04.2026 - On the 22nd April 2026, the landowner's agent provided marked up Heads of Terms ahead of their meeting with the Applicant's Agent on the 27th April 2026. The Applicant and their agent met with the landowner's agent on the 27th April 2026 and the marked up terms were discussed with several areas still requiring further discussion to reach agreement including clauses in relation to: - Ancillary Rights for utilities - New Interests The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant’s Agent continues to negotiate Heads of Terms with the landowner’s agent. Revised Heads of Terms were issued on 29 May 2026, addressing outstanding matters relating to ancillary utility rights and the acquisition of new interests. To further progress negotiations, the Applicant’s Agent contacted the landowner’s agent on 13th July, 6th August and 20th August 2026 to request a meeting. The Applicant's Agent is waiting for any additional feedback from the landowner's Agent. The Applicant’s Agent remains committed to progressing discussions and is confident that agreement can be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher John Randall | 3279 | K564173,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 |  | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher John Randall | 3279 | K564173,K65829 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 |  | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Christopher Hirst | 33 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Christopher Hirst | 33 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK150493,SK407266 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Gilbert Sneath | 3507 | SK379333,SK407266 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Christine Louise Fincham | 133 | SK140659,SK290870 | Easement Right or Privilege | Right of entry and rights relating to water pipes as contained in a Conveyance dated 14 August 1989 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK150493,SK407307 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christine Elizabeth Dunn | 3506 | SK379333,SK407307 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cherian Roberts | 551 | SK258064,SK336019 | Easement Right or Privilege | Right to free passage of service media and relating to entry as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cherian Roberts | 551 | SK258064,SK336019 | Restrictive Covenant | Restrictive covenants relating to maintenance of boundary structures as contained in a Transfer dated 2 December 2011 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caron Susan Walsh | 300 | K684903,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caron Susan Walsh | 300 | K684903,K834466 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 10. Land that is not subject to powers of acquisition | Class 10. Land that is not subject to powers of acquisition nor temporary use | Caron Susan Walsh | 300 | K684903,K708841 | Easement Right or Privilege | Rights relating to the abstraction of water and right of entry with or without workmen for the purpose of maintaining apparatus as contained in a Transfer dated 23 March 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Public Trustee | 825 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land | as Personal Representative to the Estate of Terence James Martin Haworth | Category 2 | No Agent Known | Yes | RR-5322 | [8 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614,SK329337 | Easement Right or Privilege | Right of way for the benefit of adjoining land |  | Category 2 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. | 13.04.2026 - The Applicant's Agent issued a revised access and drainage plans to the landowner's agent on 20th March 2026 and feedback is awaited. Although this landowner's agent did not attend the most recent Suffolk Agents meeting on 23rd March 2026, The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The landowner's primary concerns are in relation to construction impacts on their adjoining residential property. The Applicant will continue to engage with this landowner and their agent to apply accommodation works to mitigate disruption where possible and will share the list of accommodation works the Main Works Contractor will enact in order to help mitigate the effect of this project on the landowner. Any remaining proven disturbance or diminution in value can be adequately addressed by the Compensation Code. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent, with the exception of the commercials. As stated at Deadline 6, the Applicant will continue to engage with the landowner and their agent beyond the close of Examination to mitigate any potential disruption. | The Applicant’s Agent and the landowner’s agent have continued to engage constructively in negotiations, with regular correspondence taking place since the previous update in April 2026. Revised Heads of Terms were issued on 30 April 2026, addressing the points raised by both the Suffolk Agents Group and the landowner’s agent. In addition, the parties have held weekly telephone discussions to progress the Heads of Terms and work through outstanding matters. The Applicant’s Agent met with the landowner’s agent on 7 July 2026 to further advance negotiations. The principal matters remaining for agreement relate to the commercial terms and the landowner’s desire for greater certainty regarding the potential impacts of construction activities on their property. The Applicant's Agent continues to negotiate the commercial position with the landowner's Agent and it is expected that agreement will be reached on this point. As set out at Deadline 6, the Applicant remains committed to ongoing engagement with the landowner and their agent to identify and implement appropriate accommodation works that will, where practicable, mitigate disruption during construction. The Applicant will also provide details of the accommodation measures proposed by the Main Works Contractor to minimise the effects of the Project on the landowner’s property and operations. The Applicant considers that any residual and proven disturbance, or any diminution in value arising from the exercise of the rights sought, can be appropriately addressed through the Compensation Code. The Applicant will continue to engage proactively with the landowner and their agent with a view to reaching a voluntary agreement prior to the DCO decision. | Draft under discussion |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Carole Ann Alderman | 3274 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Carole Ann Alderman | 3274 | K564173,K428257 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Canterbury & District Angling Association | 2589 |  | Easement Right or Privilege | Right of access appurtenant to Ebbsfleet Farm, Ebbsfleet Lane, Minster |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7b | Suffolk Sheet 2 | 419 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7b | Suffolk Sheet 2 | 419 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7 | Suffolk Sheet 2 | 12,621 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK438881 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | tbc | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7 | Suffolk Sheet 2 | 12,621 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK438881 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | tbc | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7a | Suffolk Sheet 2 | 1,266 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/7a | Suffolk Sheet 2 | 1,266 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK336019 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Cadent Gas Limited | 1055 | SK336019 | Restrictive Covenant | Restrictive covenant relating to gas apparatus as contained in a Deed dated 28 September 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Easement Right or Privilege | Rights relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Cadent Gas Limited | 1055 | SK258213 | Restrictive Covenant | Restrictive covenants relating to gas apparatus as contained in a Deed dated 30 July 1953 |  | Category 2 | No Agent Known | Yes | RR-0656 | [6 empty] | SU | Agreed and in latest version of the dDCO |  | 08.10.2025- Bespoke Protective Provisions under active negotiation. 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. 10.3.2026- The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. The Applicant understands that these are agreed between the parties, subject to one minor point. It is expected that agreement will be reached on these before the end of the examination, as well as in relation to a separate side agreement. | 13.04.2026 - Subject to internal governance the Applicant has agreed bespoke protective provisions and a side agreement with Cadent. The final version will be included in the dDCO at Deadline 7. | 29.04.2026 - The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | The Applicant and the statutory undertaker have reached agreement on a set of bespoke protective provisions which are included in the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK276346 | Mortgage | as mortgagee to Emma May Alexandra Heald and Andrew Michael Hilliard Heald in respect of a legal charge dated 30 July 2012 registered under title SK276346 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | C. Hoare & Co. | 262 | SK276346 | Mortgage | as mortgagee to Emma May Alexandra Heald and Andrew Michael Hilliard Heald in respect of a legal charge dated 30 July 2012 registered under title SK276346 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | C. Hoare & Co. | 262 | SK194564 | Mortgage | as mortgagee to Michael Guy Hillard Heald and Lucinda Jane Fillerton Heald in respect of a legal charge dated 15 November 2004 registered under title SK194564 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William James Stebbings | 765 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Tamara Dagma Suaris Townend | 43 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Scott Daniel Flint | 205 | SK216869,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Easement Right or Privilege | Right of entry to maintain boundary structures and service media and rights relating to service media as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Samuel John Townend | 5 | SK202435,SK257795 | Restrictive Covenant | Restrictive covenants to not obstruct service media, to maintain hedgerows and trees and not to erect buildings or keep pigs within 400 yards of a residence as contained in a Conveyance dated 31 January 2000 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 14 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Rebecca Jane Willard | 327 | SK222695,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 14 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 21 May 1999 for the benefit of adjoining land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Easement Right or Privilege | Rights to pass water, soil, electricity, communications services, irrigation services and equipment through conducting media, right to enter for maintenance purposes and rights to remove game shot from neighbouring land as contained in a Transfer dated 21 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK194564,SK257795 | Restrictive Covenant | Restrictive covenants not to impede or prevent the free passage of water soil electricity communications services irrigation services and equipment through conducting media as contained in a Transfer dated 21 May 1999 for the benefit of neighbouring land |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK150493,SK379333,SK407461 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 |  | No | [9 empty] | Not required | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Belle Isle Holdings Limited | 3565 | K838948 | Easement Right or Privilege | Right of way and rights relating to service media as contained in a Transfer dated 5 April 2002 for the benefit of Ebbsfleet Farm House |  | Category 2 |  | No | [10 empty] | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Barbara Marion Randall | 3276 | K564173,K67607 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Barbara Marion Randall | 3276 | K564173,K67607 | Easement Right or Privilege | Right of way as contained in a land tinted blue on the filed plan |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Anthony Leonard Rupert Fincham | 415 | SK140659,SK290870,RTS Notices | Easement Right or Privilege | Right of entry and rights relating to water pipes as contained in a Conveyance dated 14 August 1989 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ann Michele Kiceluk | 306 | SK328388 | Mortgage | as mortgagee to The Royal Society For The Protection of Birds in respect to a legal charge dated 31 October 2013 registered under title SK210361 | as trustee to The Royal Society For The Protection Of Birds Pension and Life Assurance Fund | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gorse Developments Limited | 1675 | SK329337,SK217540 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ann Margaret Hirst | 243 | SK281492,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ann Margaret Hirst | 243 | SK281492,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Easement Right or Privilege | Rights relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/85 | Suffolk Sheet 1 | 113 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/85 | Suffolk Sheet 1 | 113 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Gavin Shearer | 164 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Paul Andrew Greenham | 539 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [10 empty] | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Andrew Barr | 540 | SK350290,SK351053 | Restrictive Covenant | Restrictive covenant relating to drainage ditches as contained in a Transfer dated 5 October 2012 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lloyds Bank plc | 38 | SK350290 | Mortgage | as mortgagee to Peter Murray Mann in respect of a legal charge dated 10 December 2020 registered under title SK350290 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Guy Hilliard Heald | 109 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346465 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Megan Emma Stebbings | 80 | SK257795,SK388289 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20d | Suffolk Sheet 2 | 1,857 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity transmission lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/20 | Suffolk Sheet 2 | 215,756 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK311155 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK311155 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed of Grant dated 6 January 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Mark Adrian Haines | 73 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Crispin James Rex Hardy | 1673 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lucinda Jane Fullerton Heald | 766 | SK194564,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Megan Pemberton, Landbridge | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Revised Heads of Terms were issued in August 2025. Negotiations will continue throughout the examination process 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026.The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated into the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is expected that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicants agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. It is believed that the majority of the commercial terms are broadly agreed; however, a small number of commercial matters remain under discussion before terms can be finalised. | Draft under discussion |  | 2026-09-11
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Anne Hardy | 1674 | SK329337,SK404121 (Backdated) | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 13 May 2020 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Right of way as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK111530,SK257795 | Easement Right or Privilege | Rights relating to a water supply and service media as contained in a Conveyance dated 10 March 1986 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/5 | Suffolk Sheet 2 | 1,324 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Laura Sunderland | 165 | SK249821,SK257795 | Easement Right or Privilege | Rights relating to a water supply as contained in a Transfer dated 30 January 2004 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/6 | Suffolk Sheet 2 | 2,008 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Karen Mavis Greenham | 90 | SK190675,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/7b | Suffolk Sheet 2 | 419 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/7b | Suffolk Sheet 2 | 419 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/7 | Suffolk Sheet 2 | 12,621 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/7 | Suffolk Sheet 2 | 12,621 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/7a | Suffolk Sheet 2 | 1,266 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/7a | Suffolk Sheet 2 | 1,266 square metres, or thereabouts, of agricultural land situated to the north of Moor Farm, Suffolk Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK257795,SK87310 | Easement Right or Privilege | Right of entry and rights relating to a water supply and service media as contained in a Conveyance dated 28 April 1989 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Janette Nicola Packard | 51 | SK251386,SK257795 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | George William Barrington-Phillips | 3519 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK346463 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK346463 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 | SK345175 | Restrictive Covenant | Restrictive covenant relating to water apparatus as contained in a Deed dated 16 February 1998 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK258213 | Easement Right or Privilege | Rights relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 | SK258213 | Restrictive Covenant | Restrictive covenants relating to water apparatus as contained in a Deed dated 10 October 1997 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK151617,SK276346 | Easement Right or Privilege | Right to erect buildings as contained in a Conveyance dated 9 June 1948 |  | Category 2 | Megan Pemberton, Landbridge | Yes | RR-0274 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | 13.04.2026 - The Applicant's Agent had email correspondence with the landowner's agent on 13th March and 16th March 2026 in relation to further meeting availability and requesting feedback on the Heads of Terms. The Applicant's Agent had a Teams meeting with the landowner's agent on 1st April 2026 to discuss their feedback on the Heads of Terms after the Suffolk agents group meeting on 23rd March 2026. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes that all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. Commercial elements of the terms are still to be agreed and it is likely that agreement will be reached by the end of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the terms will be agreed in principle with the landowner's agent. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's agent and landowner's agent have continued to engage positively in negotiations, with correspondence ongoing since the update provided in April 2026. A meeting was held on 16th July 2026 to discuss the Heads of Terms and progress the remaining commercial and legal points. The parties have made good progress towards agreement, with the number of outstanding matters continuing to reduce as discussions advance. The principal matters requiring further consideration relate to the extent of the rights across the grantor's land, access tracks, soil management provisions and occupiers consent. The Applicant remains encouraged by the progress made to date and will continue to work collaboratively with the landowner and their agent with the intention of reaching a voluntary agreement by DCO decision. | Draft under discussion |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrew Kevin Charles Cracknell | 1019 | K111468 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Andrew Kevin Charles Cracknell | 1019 | K111468 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrea Robinson-Smith | 437 | SK307231,SK336019 | Restrictive Covenant | Restrictive covenant to not be a nuisance as contained in a Transfer dated 28 July 2006 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/23a | Suffolk Sheet 2 | 746 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/23 | Suffolk Sheet 2 | 10,443 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22b | Suffolk Sheet 2 | 551 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/22a | Suffolk Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Andrea Jane McMillan | 2583 | SK187339,SK268898 | Easement Right or Privilege | Rights relating to service channels and support as contained in a Transfer dated 23 October 1998 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/85 | Suffolk Sheet 1 | 113 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/85 | Suffolk Sheet 1 | 113 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/90 | Suffolk Sheet 1 | 217 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK349245 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Easement Right or Privilege | Rights relating to service media and access as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amyas John Peto | 453 | SK311155,SK349245 | Restrictive Covenant | Restrictive covenant relating to use of buildings as contained in a Transfer dated 11 October 2013 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right of entry and rights relating to service media as contained in a Transfer dated 17 February 2004 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Easement Right or Privilege | Right to relocate a fence as contained in a Deed dated 3 February 1994 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442,K868267 | Restrictive Covenant | Restrictive covenants not to have accessways or openings or more than six windows along the northern elevation of a building and a covenant to construct and maintain a fence as contained in a Transfer dated 17 February 2004 for the benefit of adjoining la |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Easement Right or Privilege | Rights relating to service media, light and construction as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K755310,K838442 | Restrictive Covenant | Restrictive covenant not to use the land for any purpose other than agriculture as contained in a Transfer dated 14 September 1995 for the benefit of neighbouring land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [10 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | 13.04.2026 - On the 23rd March 2026, the Applicant's Agent spoke with the landowner's agent on the phone to request the outstanding comparable evidence and written feedback on the Heads of Terms. On 30th March 2026, the landowner's agent provided outline comparable evidence to facilitate negotiation of the Heads of Terms. On the 1st April 2026, the Applicant's Agent met with the landowner's agent in person to discuss Heads of Terms and comparable evidence. The Applicant's Agent requested that full comparables supporting the landowner's position were provided. On 2nd April 2026, the landowner's agent provided comprehensive comparable data and the Applicant's Agent is in the process of reviewing it to inform negotiation of the commercial terms. It is anticipated that an agreement can be reached prior to the close of Examination. | 29.04.2026 - The Applicant's Agent emailed the landowner's agent on the 14th April 2026 to provide a summary of outstanding actions from their meeting on 1st April 2026. The Applicant's Agent is completing their review of comparable evidence and land values and will revert to the landowner as soon as possible in relation to the commercial terms. The Applicant's Agent called the landowner's agent on the 24th April 2026 and the landowner's agent to discuss the outstanding matters. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent, with engagement ongoing since the last update in April 2026 . Revised Heads of Terms were issued on 11th June 2026 and had a Teams meeting landowner's agent 24th June 2026. The Applicant's Agent believes the Heads of Terms are agreed in principle subject to the commercial terms being accepted. The Applicant's Agent had Teams meetings with the landowner's Agent on 11th and 18th August 2026 with revised terms subsequently issued on 27th August 2026. It is expected that agreement will be reached prior to the DCO decision being made. | Draft under discussion |  | 2026-09-18
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Easement Right or Privilege | Right of entry in relation to works and maintenance as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK150493,SK403456 | Restrictive Covenant | Restrictive covenants not to use land for housing livestock or to do anything that may impede adoption of neighbouring roads or service media as contained in a Transfer dated 31 August 2017 for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Right of support and right of entry for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Right of way for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Adam Peter Holcombe | 3498 | SK379333,SK403456 | Easement Right or Privilege | Rights relating to service media and drainage for the benefit of neighbouring land |  | Category 2 | [11 empty] | Not required | 04.03.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Acorn Homes (Group) Limited | 2316 | TT46646 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights - Access | Acorn Homes (Group) Limited | 2316 | TT46646 | Easement Right or Privilege | Right of access |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 13.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | 29.04.2026 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Easement Right or Privilege | Rights reserved relating to service media as contained in a Transfer dated 2 November 2001 |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Connie Amber Peck | 3520 | SK222694,SK257795 | Restrictive Covenant | Covenants to not obstruct service media and to maintain boundary structures as contained in a Transfer dated 2 November 2001 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [9 empty] | Not required | 08.10.2025 - This land interest relates to subsoil interest. no voluntary rights are being sought in relation to the subsoil without further land rights being sought | 13.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | 29.04.2026- This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795,SK257841 | Easement Right or Privilege | Rights granted relating to service media as contained in a Transfer dated 21 May 1999 |  | Category 2 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | 13.04.2026 -The Applicant's Agent and the landowner's agent exchanged emails in relation to commercial elements of the Heads of Terms on 3rd March, 16th March and 23rd March 2026. The Applicant's Agent met with the landowner's agent on 31st March 2026 following the agents group meeting on 23rd March 2026 to discuss Heads of Terms, in particular the commercial elements, the proposals to mitigate any impact to the irrigation infrastructure and the access and drainage rights. The Applicant's Agent provided an update on the Applicant's position on the requested amendments to the Heads of Terms from this meeting on 9th April 2026. Amended Heads of Terms to reflect these discussions will be issued week commencing 13th April 2026. Whilst the Applicant believes all Heads of Terms points raised have now been adequately addressed, a number of amendments requested by the Suffolk agents group have not been fully incorporated in to the Heads of Terms as it is not appropriate to do so. These points were in relation to obligations on the landowner to declare third party interests, termination provisions and commercial terms. The temporary construction lease and environmental lease terms are agreed with the landowner's agent and the above outstanding points relate to the underground cable terms. It is likely that an agreement will be reached before the close of Examination. | 29.04.2026 - The Applicant's Agent is in regular communication with the landowner's agent in relation to Heads of Terms. Whilst it was hoped that the revised Heads of Terms for the underground cable would be issued week commencing 13th April 2026, a few of the points raised by the Suffolk Agents group require the Applicant to review these points against their national policy. The revised Heads of Terms will be issued as soon as possible once this review has been finalised. The Applicant believes that the revised Heads of Terms address all outstanding points and the underground cable terms will be agreed with the landowner's agent soon after these are issued. The Applicant will continue negotiations beyond the close of Examination with the intention of reaching voluntary agreement prior to the DCO decision being made. | The Applicant's Agent continues to negotiate Heads of Terms with the landowner's agent. Revised Heads of Terms were issued on 29th April 2026 which addressed the points raised by the Suffolk Agents group. The Applicant's Agent has had ongoing discussion with the landowner's agent in relation to the wider access and drainage rights in the Heads of Terms, these points have now been agreed with the landowner's agent. The Applicant's Agent had a Teams meeting with the landowner's agent on 7th July 2026 and met with the landowner's agent in person on 30th July and 26th August 2026. The outstanding point in relation to third party development proposals that the landowner is exploring and how these can work with the Applicant's proposals has also been agreed with the landowner's agent. The Applicant's Agent is due to issue final Heads of Terms for signing week commencing 7th September 2026 with signed Heads of Terms expected shortly after this. | Draft under discussion |  | 2026-09-11
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 | SK257795 | Easement Right or Privilege | Rights relating to the use, inspection and maintenance of water apparatus as contained Deed dated 22 May 1992 |  | Category 2 | No Agent Known | No | [8 empty] | Bespoke PPs |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | No Heads of Terms Required |  | 2026-09-18
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 2 | No Agent Known | No | [7 empty] | SU | Standard PPs as set out in the dDCO |  | 10.03.2026- The Applicant will make any necessary submission addressing the statutory tests for s.126/ s.138 before the end of the examination. The Applicant is continuing its engagement with the statutory undertake At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 13.04.2026 - At this stage and based on discussions with the statutory undertaker including in relation to the signed SoCG [REP1-090] submitted at deadline 1, the Applicant anticipates that the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | 29.04.2026 - A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | A signed SoCG [REP1-090] was submitted at deadline 1 and the statutory undertaker will rely on the standard protective set out in Schedule 15 of the dDCO. | No Heads of Terms Required |  | 2026-09-18
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold | Subsoil | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | Not SU | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 2 | N/A | Yes | RR-3936 | RR-3936 https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026/representations/100005739 | REP1-144 REP3A-029 REP5-200 | REP1-144 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-001199-Written%20Representations%20NRIL%2018.11.25.pdf REP3A-029 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002226-EN020026%20-%20Network%20Rail%20Infrastructure%20Limited's%20Response%20to%20Change%20Request%20dated%2019%20January%202026.pdf REP5-200 https://nsip-documents.planninginspectorate.gov.uk/published-documents/EN020026-002872-EN020026%20-%20NRIL%20response%20to%20ExQ2%20-%20Sea%20Link%20-%2010%20March%202026.pdf |  |  |  | SU kit and apparatus | Agree and in the latest version of the dDCO |  | 10.3.2026- The Applicant will is continuing to pursue engagement with the statutory undertaker but has not yet received comment on its proposed protective provisions. The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5. These are not agreed by the statutory undertaker and the Applicant expects a further meeting will be needed to discuss the outstanding points. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | 13.04.2026 - The Heads of Terms for the land rights are in an approved form and subject to engineering detail these will be taken forward, but in line with the PPs, BAPA and Technical Clearance Certificates. There was a call with the Asset Protection & Optimisation team on 10th April 2026, There has been a personnel replacement . The Applicant provided the new Network Rail team member with an overview of the project and supplied various information previously supplied, to bring him up to speed. Network Rail advised that the Track and Level Crossings team will now need to be brought into the project for discussions over the level crossing enabling works. The Applicant has been informed that the clearances of the OHL over the track, supplied previously from the outline design, had been confirmed as acceptable, this will be taken forward to certification and finalisation and the agreed template Heads of Terms will be updated and re-submitted to Network Rail to start that finalisation and completion of agreed terms. | The Applicant’s lawyers have been in correspondence with NRIL’s lawyers following the close of the Examination. In particular, the Applicant returned a revised version of NRIL’s proposed side agreement in mid-July and a legal meeting took place on 9 September. The focus of that call was on the Applicant’s need to maintain programme and both parties took an action to further pursue conversations in relation to voluntary land rights. Although progress has been made in narrowing the issues, the parties have not reached agreement on a revised set of protective provisions to be included in the dDCO and the Applicant’s position remains as at Deadline 7. The Applicant submitted its preferred set of protective provisions at Deadline 7. Its rationale for the differences between its preferred set and the template protective provisions initially provided by NRIL can be found in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). The Applicant notes the submissions made by NRIL in its representations made at Deadline 7 (REP7-206). The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement at paragraph 5.9. The protective provisions included in the dDCO at Deadline 7 require the Applicant to enter into an asset protection agreement before undertaking any works within 15 metres of railway property or which may adversely affect railway property. The negotiation and agreement of that document will provide NRIL with the appropriate level of control and protection over its railway assets during the Applicant’s works. Similarly, conversations are ongoing between the parties regarding negotiation of a voluntary easement for the overhead line rights over the railway. The Applicant has provided NRIL with details of the indicative overhead line clearance, noting that this is subject to change through detailed design, and confirmation that it must comply with the minimum clearance requirements pursuant to the Electricity, Safety, Quality and Continuity Regulations 2002. The Applicant is awaiting confirmation from NRIL as to whether this is sufficient detail to allow HOTs for the easement to be agreed. | Draft under discussion |  | 2026-09-11
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/20c | Suffolk Sheet 2 | 15,353 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 2 |  | Yes |  | Relevant Representations ¦ Representation by Ward Hadaway LLP acting for Northumbrian Water Limited | [5 empty] | SU | Draft under discussion |  | 04.03.2026-The Applicant is continuing its engagement with the statutory undertaker and has made substantial progress towards agreement on a set of protective provisions. Given the stage in the examination process, the Applicant has included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 although these are not yet agreed by the statutory undertaker. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 13.04/2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoing. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. | 29.04.2026 - The Applicant included its proposed bespoke protective provisions in the version of the dDCO submitted at Deadline 5 and negotiations with the statutory undertaker are ongoinghave been continuing. The Applicant has included an updated set out protective provisions at Deadline 7 although these are not yet agreed. This sets out the Applicant’s understanding of the outstanding points in the draft protective provisions and the Applicant’s justification for its preferred wording. It is expected that agreement will be reached before the end of the examination process. There are also ongoing negotiations relating to an Asset Protection Agreement. The terms are agreed in principle but this is not yet finalised due to the outstand | The Applicant’s lawyers have been in correspondence with NWL’s lawyers following the close of the Examination. This includes a meeting which took place to discuss the outstanding matters between the parties on 15 July. Following ongoing discussions, the Applicant has included some updates to the bespoke protective provisions for NWL in the dDCO to address matters raised by NWL. These are set out in Part 8 of Schedule 15 to the dDCO submitted with this letter. However, the parties have not reached agreement on a revised set of protective provisions. The scope of disagreement between the parties is limited to the cost provisions. The Applicant’s position on its preferred form of drafting is set out in 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions (Version E) (REP7-039). With regards to the inclusion of betterment deductions to account for measurable financial benefits received by NWL, as noted, where the removal or replacement of apparatus is required, the protective provisions require that the Applicant compensate NWL for any costs incurred in connection with those works. The betterment provisions at issue then reduce that liability to the extent NWL receives some benefit from either the residual value of removed apparatus or from the deferment of replacing older apparatus. The inclusion of these provisions ensures that the Applicant is not subsidising any benefit to NWL over the actual impact incurred, while ensuring that Northumbrian Water remain cost neutral. The Applicant therefore considers that these provisions should remain and their inclusion does not cause any serious detriment to NWL’s undertaking. The focus of more recent discussions has been regarding NWL’s position that the cost provisions in the protective provisions must be compatible with s.185(5) of the Water Industry Act 1991 and NWL’s published charging schedule (which NWL’s lawyers assert is not the case). We have included an amendment to the protective provisions to deal with the former point. The Applicant’s position remains that the costs provisions in the protective provision are standard and that s.185(5) does not prevent them from applying. However, requiring the protective provisions to comply with NWL’s published charging schedule is not considered appropriate and would introduce an unacceptable Project risk. NWL's published charging rules are primarily directed at domestic utility connections and minor developments of a different scale and nature to the types of interactions that may apply here. The charging schedule may also be updated by NWL at any time without input from the Applicant, potentially conflicting with the cost provisions in the protective provisions as the Order is made. The Applicant notes the submissions made by NWL in its representations made at Deadline 7 (REP7-207, REP7-304 and REP7-365). Whilst the protective provisions are not agreed by NWL, the Applicant maintains its position set out at Deadline 7, that the s127 and s138 statutory tests are met. The Applicant’s explanation of why it considers the s127 and s138 statutory tests to be met can be found in 9.106.1 The Applicant’s Section 127 and Section 138 Statement (REP 7-165) at paragraph 5.10. Crucially, the protective provisions as set out in the dDCO include a range of protections which will provide NWL with the appropriate level of control and protection over its land and apparatus, including, inter alia, in respect of the Applicant’s exercise of compulsory acquisition powers or powers to remove or alter any apparatus so that NWL will not be affected to the serious detriment of its ability to carry out its undertaking. | No Heads of Terms Required |  | 2026-09-18